## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0662 | With Workgroup | UNC - Transmission | NTS | Revenue Recovery at Combined ASEPs | Oct-19 | Rule & System change | NA | UK Link and Gemini | Potential impacts to UK Link and Gemini. Please note - this is a single event change | NA | Transmission and Shared Services | Steve Pownall | The purpose of this modification is to allow entry capacity booked for the entry of gas into the NTS from storage sites within combined Aggregated System Entry Points (ASEPs), to be treated the same as a “Storage Site” as designated in National Grid’s Licence with respect to the application of any revenue recovery charge based on capacity bookings. The required changes will be captured as part of the EU GB Charging project. Xoserve systems have been impact assessed and the development of the modification solution is relatively simply. The modification is dependent on the 0678 decision.
Mod 0664 | With Workgroup | UNC - UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | Impacts on UK Link to bulk transfer sites from Classes 2 and 3 to Class 4. Invoicing and charging arrangements to be put in place for the CDSP reclassifying sites. Reports required to compare Shipper performance. | NA | Retail & Network | David Addison | Modification looks to create an obligation for Shippers to move Supply Points with low Valid Daily Meter Reading submission performance from Classes 2 and 3 into Class 4 following a consecutive period of poor performance. The CDSP will automatically move any Supply Points note moved by the Shipper in such a scenario (after an allowed period of time). Impacts to UK Link expected. A ROM response has been provided giving an indication of costs and effort. It has been confirmed that this modification will require implementation within a Major Release. Legal text has also been provided. The next available Major Release is November 2020.
Mod 0670R | With Workgroup | UNC - NTSCMF | NTS | Review of the charging methodology to avoid the inefficient bypass of the NTS | Any Modifications as a result of 0670R will be impact assessed and system implications considered. If modification is raised, it is likely to have cross-platform impacts (Gemini and SAP ISU). | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to conduct an assessment of the charging methodology that is a feature of the overall Gas Transportation Charging framework to avoid the inefficient bypass of the NTS (currently the NTS Optional Commodity charge). The review assesses the objectives, identify requirements, analyse potential options and propose an enduring proportionate solution. Currently 3 ideas for a charging methodology to avoid the inefficient bypass of the NTS. If a modification is raised from the review group, it is likely to have central impacts as any new NTS short haul product will be based on NTS capacity rather than commodity. WG report expected by January 2020.
Mod 0672 | With Workgroup | UNC - UIG | Scottish Power | Target, Measure and Reporting Product Class 4 Read Performance | No implementation specified | Reporting | NA | UK Link | New reports required to measure performance | NA | TBC | David Addison | Modification has changed significantly and removed the incentive element. Focus is now on measuring performance. seeks to reduce Unidentified Gas (UIG) volume by providing a target for read submission performance for Product Class 4 sites against overall portfolio. This modification proposes to target and measure performance against an agreed percentage for Energy reconciled after a defined period and provide PAC with a report which will enable them to target shippers whose performance is below the target threshold. The central system impacts are now around creating new reports to measure performance. ROM response provided which details a 4 to 8 week implementation timescale with a upper range cost of £30,000
Mod 0674 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | New reports are required and the incentive regime will need to be developed with considerations around the invoicing element. | TBC | NA | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed. Modification still developing.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. WG extension requested and approved by Panel to February 2020.
Mod 0678 (A-J) Urgent | Awaiting Ofgem Decision | UNC - WG | Various proposers | Amendments to Gas Transmission Charging Regime | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact picked up through the Gemini project team | Oct-20 | Transmission and Shared Services | Steve Pownall | Modification proposal is to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges and to deliver compliance with relevant EU codes (notably the EU Tariff Code). There are currently 11 alternates. Modifications look to address the issues highlighted in the Ofgem rejection letter for 0621 and the alternatives. Impacts to be picked up as part of the project team. Panel did not recommend that 0678 or any of the alternates should be implemented. Panel also indicated no clear majority view on the preference around which modification better facilitates the Relevant Objectives. Modification and alternates are with Ofgem for a decision. Once decision is confirmed, the central changes will be picked up through the Gemini project team. Minded to view has been issued by Ofgem. The view is to approve UNC0678A. A consultation has been issued for industry response closing 24 February 2020.
Mod 0686 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Transmission and Shared Services | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Panel did not recommend the implementation of modification 0686. Currently with Ofgem for a decision. Modification must still be assessed to consider a phased implementation of the 0678.
Mod 0687 | Awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Changes to introduce a new charge type for domestic and non-domestic sites in a SoLR event | TBC | Retail & Network | Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. System impacts expected to introduce a new charge types. High level solution options have been provided with the degree of central system impacts varying depending on the preferred solution option. System delivery is expected by April 2019 which will impact the possible solution. The DSC Change Proposal has been raised (XRN4992). Panel voted to implement the modification and it is currently with Ofgem for a decision. An interim solution for XRN4992 was rejected by ChMC. An enduring solution can be in scope of the November 2020 release but this will need to be agreed by ChMC in February 2020 latest.
Mod 0690 | With Workgroup | UNC - WG | British Gas (on behalf of the UIG Taskforce) | Reduce qualifying period for Class 1 | TBC | Rule and Reporting Change | No | UK Link | ROM response indicated that the data items required for the PAC report are already available therefore it is just utilising these data items for new reports | TBC | Data | James Rigby | This modification proposes that the qualifying period for the requirement for a meter point to become Class 1 is reduced, to limit the time period when very large sites are subject to NDM Demand Estimation, as opposed to being Daily Metered. The modification also proposes a new Performance Assurance report of sites which have met the qualifying criteria for Class 1 but are either Class 3 or Class 4. ROM response indicated that the data items required for the PAC report are already available. A ROM has been completed and confirmed that the report can be implemented as a Minor Enhancement. A DSC CP XRN4867 has been raised to deliver the report. The modification has been issued for Consultation closing on 24 January 2020.
Mod 0691 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | UK Link | System changes will be required to identify and move sites to Class 1 when they meet the qualifying criteria. New reports will be required to identify this. | TBC | Data & R&N | James Rigby | This modification proposes that where the requirement for a Class 2, 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a 28 business day grace period, that the CDSP would take steps to convert the meter point to Class 1. The modification also proposes a new Performance Assurance report of sites where the CDSP has taken action, over the previous 12 months. ROM response has been provided which details two solution options (automated and manual). The automated solution would definitely require a Major Release. It is currently unknown as to whether the manual solution could be a candidate for a Minor Release. A DSC CP has been raised to deliver the system solution (XRN5038). A ROM has been provided which proposed two solution options - an automated solution and a manual solution. The automated solution would definitely require a Major Release. The manual solution could be a Minor Enhancement depending on what is agreed with the reporting functionality.
Mod 0692 IGT131 | Approved Proposed removal from Bubbling Under | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | Jun-20 | Rule and System Change | No | UK Link | System changes required to update the MRF for sites with an AQ over 293,000kWh or with Smart or Advanced Metering equipment in operation | Jun-20 | Retail & Network | Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. XRN4941 has been raised to deliver the system impacts of the modification and is in scope of June 2020 release pending the outcome of this modification. December Panel approved the implementation of modification 0692. Implementation should align with the delivery of the associated DSC Change Proposal XRN4941 which is in scope for June 2020. Proposed removal from Bubbling Under .
Mod 0693R | With Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | James Rigby | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). WG are discussing the request. Any potential solutions from the review will need to be assessed for system impacts.
Mod 0696 | With Workgroup | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | Potential system impacts | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required. System changes may be necessary to prevent the PMSOQ for a site exceeding the NExA SOQ | TBC | Retail & Network | Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. WG report has been completed. System changes are not expected but a process to correct the capacity charges is necessary. Modification issued back to WG by Ofgem to consider further questions. CDSP impacts are being re-considered and a DSC CP would be required to put in place the offline process depending on the Ofgem decision.
Mod 0697 IGT135 | With Workgroup | UNC - DWG | Gazprom Energy | Alignment of the UNC TPD Section V5 and the Data Permissions Matrix | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document and process change only | TBC | N/A | Dave Addison /Ellie Rogers | This modification seeks to rationalise UNC TPD Section V5 and remove inconsistency with the Data Permissions Matrix. No system impacts resulting from this change, just documentational only. WG discussions are continuing.
Mod 0699 | With Workgroup | UNC - DWG | Scottish Power | Incentivise Read Submission Performance using additional Charges | TBC | Reporting and System Change | N/A | UK Link | New reports required to assess Shipper performance. Arrangements for incentivising performance and invoicing required | N/A | N/A | Dave Addison/ Ellie Rogers | To create a Shipper incentive mechanism, which encourages the submission of valid meter readings into settlement through achievement of UNC targets and obligations. A charge will be levied in each retrospective month, to Shippers where performance has not met a set of pre-determined UNC targets. Modification concept was changed. No longer looking to utilise UIG to incentivise performance. Central system impacts are still expected (minimum to add new Charge Types) but needs to be assessed fully once the modification has developed.
Mod 0701 | With Workgroup | UNC - DWG | NGN | Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule and System Change | N/A | UK Link | Changes to UK Link to enhance what is held against NExA sites and add rules for certain data items | TBC | TBC | Ellie Rogers | To improve visibility where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, and to link capacity increased with the NExA so that the allowed capacity does not exceed the capacity as agreed in the NExA. System impacts expected to enhance what is currently held in UK Link against NExAs. New rules and logic also to be applied for NExA sites. ROM response has been provided which indicates the central system impacts. This needs to be updated to align with the amended modification.
Mod 0702 IGT134 | With Workgroup | UNC - DWG | Gazprom Energy | Introducing ‘Research Body’ as a new User type to the Data Permissions Matrix and UNC TPD Section V5 | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document change only to update the DPM | TBC | N/A | Ellie Rogers | This modification seeks to further realise the benefit of the Data Permissions Matrix reflecting the direction to greater data openness by adding ‘Research Body’ as a new user type to UNC TPD Section V5 and the Data Permissions Matrix. No system impacts expected, only documentational. Modification developing in WG.
Mod 0704 | With Workgroup | UNC - DWG | SGN | Review of Transporter Theft Reporting | TBC | Reporting Change | N/A | Potential system impacts | Change to SAP BW to update the current report to the new reporting criteria | TBC | N/A | Ellie Rogers | This modification amends the existing Transporter theft of gas reporting requirements following discussions at the 0677R Shipper and Supplier Theft of Gas reporting arrangements review group. No system impacts expected. The current theft reports are expected to be updated to align with the final Transporter reporting obligations agreed within this modification. IGT equivalent has been raised (IGT133). Currently there is a SAP BW report which is generated in order to produce the Transporter theft reports. This report will need to be updated to reflect the new reporting criteria. Not expected to be a big change but will need to be assessed.
Mod 0705R | With Workgroup | UNC - WG | National Grid | NTS Capacity Access Review | Any modifications as a result of 0705R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | To review the principles and establish long-term strategy for the NTS capacity access regime. Ensuring the regime is appropriate for commercial behaviours experienced today, simplified and adaptable whilst being consistent with relevant obligations. To make recommendations for change and addressing short-term problems in accordance with the long-term ambition. 12 month Review Group has been set up. Central impacts currently unknown and dependent on the Review Group development which will be monitored.
Mod 0706R | Allocated to Workgroup | UNC | Contract Natural Gas | Instances where Shippers can exit commercial agreements with an independent supplier | Any modifications as a result of 0706R will be impact assessed and system implications considered. | [5 empty] | TBC | TBC | A review of the processes and obligations within the UNC and Supply Licence conditions to identify and enable a clear route for the gas Shipper to exit a commercial relationship with a supplier. Review group raised and due to be discussed at the November Panel meeting. Issued to WG.
Mod 0707S | With Workgroup | UNC - DWG | Shell Energy | Introducing ‘Performance Assurance Framework Administrator’ as a new User type to the Data Permissions Matrix and UNC TPD Section V5 | Mar-20 | Permissions Change | N/A | No system impacts | No system impacts. Permissions change only to add PAFA to the DPM | N/A | Data | Ellie Rogers | Currently the Performance Assurance Framework Administrator (PAFA) is provided with then reports defined in the Performance Assurance Report Register (PARR) in order to fulfil their obligations. This modification seeks to amend the Data Permissions Matrix to add the PAFA as a new User type. Assigned a WG for development. No system impacts involved as purely a permissions modification.
Mod 0708 | With Workgroup | UNC | Northern Gas Networks | Re-ordering of the UNC in advance of Faster Switching | No implementation specified | Administrative Change | N/A | No system impacts | No system impacts as it is a recording of UNC legal text only | N/A | N/A | Dave Addison | This modification proposes to realign the UNC to match the re-ordering that is in the proposed Legal Text developed for the Switching Programme and discussed at the Workgroup for Request 0630R - Review of the consequential changes required in UNC as a result of the Ofgem Switching Programme.
Mod 0710 IGT119 | With Workgroup | UNC - DWG | WWU | CDSP provision of Class 1 Read service | 2020 outside of the winter period | Contractual Change | N/A | Minimal system impacts | Minimal system impacts expected as it is a change to the contract only | N/A | Retail & Network | Ellie Rogers / Dave Addison | This modification proposes that the Central Data Service Provider (CDSP) provides the Class 1 Supply Meter Point read service. It will remove the Transporter obligation to provide a Daily Read service to Shippers for non-telemetered Class 1 Supply Meter Points. This does not affect arrangements for directly connected telemetered Supply Meter Points on Distribution Network Operators (DNOs) or National Transmission System networks. Minimal system impacts expected as this is a contractual change.
Mod 0711 | With Workgroup | UNC - DWG | Gazprom Energy | Update of AUG Table to reflect new EUC bands | No implementation specified | System and Contractual Change | N/A | UK Link and Gemini | System impacts to reflect the EUCs within the UIG Share factors | N/A | Retail & Network | Ellie Rogers / Dave Addison | This modification updates the Allocation of Unidentified Gas (AUG) Table set out in UNC TPD Section E Annex E-1 to include the new End User Categories (EUC) brought in by DSC Change Proposal XRN4665 Creation of New End User Categories. WG development ongoing, expected changes to the AUGE and CDSP contract plus system changes to reflect the EUCs within UIG Share factors. A ROM has been requested to assess the system impacts and understand if this can be delivered within for start of gas year 2020.
Mod 0712 | With Workgroup | UNC - Transmission | National Grid | Amending the oxygen content limit in the Network Entry Agreement (NEA) at the St Fergus SAGE plant | No implementation specified | Rule Change | N/A | Unknown | System impacts are not anticipated but needs to be assessed | N/A | TBC | Steve Pownall | This enabling modification will facilitate an increase to the current oxygen content limit at the St Fergus SAGE System Entry Point through modification of the SAGE Network Entry Agreement / Provision.
Mod 0713 | Allocated to Workgroup | UNC - TBC | WWU | Amendments to TPD V3.1.7 Independent Assessment table | No implementation specified | Administrative Change | N/A | No system impacts | No system impacts, update to UNC only | N/A | N/A | N/A | This modification makes changes to a UNC mapping table to reflect changes to the way Graydon determines credit ratings. This is an update to UNC only, no system impacts are anticipated.
Mod IGT133 | With Workgroup | IGT - Workstream | BUUK | Transition of IGT Theft Reporting into the IGT UNC | No implementation specified | Reporting Change | N/A | No system impacts | No system impacts. Changes to the IGT theft reporting | N/A | N/A | Ellie Rogers | Introduction of reporting obligations on Pipeline Operators regarding Theft activities which have previously been held under the SPAA (Supply Point Administration Agreement). No system impacts.
SCP 473 | Deferred | SPAA Change Board | SGN | Reconciliation of Shipperless and Unregistered data by the PPMIP | Nov-19 | Permissions Change | N/A | Potential system impacts | The SCP must be assessed to understand if there are any system impacts | TBC | TBC | James Barlow | This SCP seeks to allow the PPMIP to compare Shipperless and Unregistered Sites data provided by the CDSP against the data that they hold in relation to prepayment Supply Points. Where the PPMIP is able to identify the Supplier for the site, this change will require they return certain data back to the CDSP (including the Supplier ID), to enable the CDSP to register the site within central systems. A DSC CP needs to be raised to assess the system impacts. Due to the comments received during the consultation period, the SCP has been deferred.