## Slide 1: XRN4996 - June 20 Release - Status Update
8th January 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Replan completed following descope of 3 changes, Market Trials inclusion pending confirmation. Delivery: Build is in progress, ST due to commence next week for changes that have completed build. Scope: Change Request for XRN4870B has been approved and is currently in Design phase – no cost implications to the project. Revised BER to be shared for information in February. Implementation: Implementation date of Saturday 27th June proposed. |  |  | 
Risks and Issues | Risk – There is a risk that costs detailed in the BER will change because these are based on estimates following approved scope changes leading to a higher than expected contingency figure. There is a risk that build and unit testing may not complete on time, because of environment set up issues, leading to a delay in the start of system testing. Work is ongoing with the ECMS and Basis teams to mitigate this risk. |  |  | 
Cost | Revised BER will be shared in February detailing firm costs and including xrn4870B. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 2: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion – 19/09/19
Design Completion – 13/12/19
Build & Unit Test Completion – 20/02/20
System & UAT Completion – 24/04/20 (provisional)
Regression Test Completion – 29/05/20
Implementation – 27/06/20
PIS Completion – 25/09/20 (provisional)

## Slide 3: June 20 Release Summary
June 20 Release consists of 8 changes, Implementation is planned for June 2020:
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4941* - Auto updates to meter read frequency (MOD0692)
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs.
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)