## Slide 1: Change Management Committee
12th February 2020

## Slide 2: 2. New Change Proposals – Initial Review

## Slide 3: 2. New Change Proposals – Initial Review
Agenda Item | XRN / Title | Voting |  |  |  |  | Funding | DSC Service Area
 |  | Shipper Y/N | DNO Y/N | GT Y/N | IGT Y/N | NTS Y/N |  | 
2.1 | XRN5072 - Class 4 with AMR/DRE Installed - RGMA Flow received with no RTC count | Y |  |  |  |  | 100% Shipper | Service Area 3: Record, submit data in compliance with UNC
2.2 | XRN5080 Failure to Supply Gas (FSG/GSOP1) – System Changes |  | Y |  |  |  | 100% DNO | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
2.3 | XRN5091 Deferral of creation of Class change reads at transfer of ownership | Y |  |  |  |  | 100% Shipper | Service Area 5: Metered volume and quantity
2.4 | XRN5092 iConversion Phase 2 |  |  |  |  | Y | 100% NTS | Service Area 20: Gemini system services
2.5 | XRN5093 Update of AUG Table to reflect new EUC bands | Y |  |  |  |  | Service Area 15 has a funding split of 50% Shipper and 50% DNO. ChMC to agree to 100% Shipper funded for this change. | Service Area 15: Demand Estimation
2.6 | XRN5097 DSC Service Description Table cosmetic change to service line table v9 | Y | Y | Y | Y | Y | N/A | N/A

## Slide 4: 2.1 XRN5072 - Class 4 with AMR/DRE Installed - RGMA Flow received with no RTC count
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 100%
Distribution Network Operators (DNOs) |  | 
National Grid Transmission |  | 
Independent Gas Transporter |  | 
Impacted Parties:- Shippers |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 3: Record, submit data in compliance with UNC
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
This proposal is required to amend the logic to how the system derives the Round the Clock (RTC) or Though The Zero (TTZ) count.
Change Description
Where there is a Class 4 site with AMR/DRE installed, check to check reconciliation is carried out when Site Visit Reads are received. When an RGMA update is received (ONJOB or ONUPD) these reads are treated as Site Visit Reads. When an ONUPD (asset update) is submitted the shipper does not have to supply any meter reads or Round the Clock (RTC) count or TTZ count (Through The Zeros) so Xoserve will generate estimated reads and derive a RTC if required. If the shipper is submitting an RGMA flow (ONJOB) and where the RTC is not supplied, the system will derive a RTC count. When the system looks to derive the RTC count it will be based on the Read history (last Actual read, last Check Read, AMR/DRE Installation read, Meter Install read, etc) For Project Nexus the RGMA design was taken from legacy CA Rules. The RGMA logic was considered as an ‘As Is’ process and the requirements were not changed. Under source rule 100278 it states “If the RTC is not provided, the RTC would be derived with an increment. We have seen instances where an RTC count of 1 is incorrect, as previous read history shows that the meter has gone round the clock several times. This has generated a reduced volume and energy, so has caused the AQ value to be understated and incorrect Reconciliation. This understated AQ affects all downstream processes that use the AQ value, (EUC assignment, daily allocation and the calculation of unidentified Gas).

## Slide 5: 2.2 XRN5080 Failure to Supply Gas (FSG/GSOP1) – System Changes
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) | Y | 100%
National Grid Transmission |  | 
Independent Gas Transporter |  | 
Impacted Parties:- DNO |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
As part of the RIIO-2 Price Control process Ofgem have indicated that all Guaranteed Standards of Service Payments (GSOP) will be reviewed in relation to the settlement to customers after a GSOP event. A reduction from 20 to 10 working days for all GSOP’s has been indicated in addition to proposed changes to the levels of compensation currently provided.
Change Description
This change requires various amendments to the current FSG/GSOP1 service provided by Xoserve. Scheduled payment frequency from fortnightly to weekly. This would accommodate the reduction from 20 to 10 working days for settlement after an FSG event. The adhoc FSG process should endure in the event of a major incident. UK Link SAP ISU parameter change. The current Ofgem level of compensation (£1,000) will no longer be required as the ceiling on payments will be lifted with no upper compensation level required. Removal of the maximum number of days payable to a customer who has been off gas, this will now be unlimited. All GSOP (1, 2, 3,12 & 13) rates of compensation are to be amended yet to be advised by Ofgem. These changes will require amendments to the validation rules applicable to GSOP1 and the subsequent payment of GSOP12 in the event of a failure to make payments within the 10 working days window. Consideration any changes within the process required to address iGT customer payments i.e. timescales constrictions, payment recipient iGT or Customer and GSOP 12.

## Slide 6: 2.3 XRN5091 Deferral of creation of Class change reads at transfer of ownership
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 100%
Distribution Network Operators (DNOs) |  | 
Independent Gas Transporter |  | 
National Grid Transmission |  | 
Impacted Parties:- Shipper |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 5: Metered volume and quantity
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Shippers are not provided with an Opening Read window when a Change of Class and Shipper occurs at the same time. This means that where an actual transfer reading has been obtained it is more complex for the incoming Shipper to get this reading accepted, which can impact their ability to invoice the end consumer with the correct read. DSP reject potentially valid opening reads where there has been a class change on transfer date.
Change Description
Currently following an accepted class change request the CDSP will issue an estimated read on the effective date of the class change. This is to support downstream processes in closing off the outgoing class period, allowing processes such as allocation and billing to run successfully. During a shipper’s ownership this does not present an issue as the class change timing is within their control and the estimated read issued can be replaced using the appropriate read file. However, where the class change occurs on the same effective date as a Change of Shipper (CoSh) the class change read is issued immediately and closes the opening read window. This prevents a valid opening read from the incoming shipper being accepted. This change seeks to retain the Opening Meter Reading window regardless whether the Change of Shipper event is coincident with a Class change so that the Shipper is able to provide an Opening Meter Reading up until D+10. A further requirement is that the CDSP does not issue the class change read to the shipper on D where the class change is on transfer day. (see CP for full description)

## Slide 7: 2.4 XRN5092 iConversion Phase 2
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) |  | 
Independent Gas Transporter |  | 
National Grid Transmission | Y | 100%
Impacted Parties:- National Grid Transmission |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 20: Gemini system services ASGT-CS SA20-06
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Globalscape, BFTS, Chamois and Revenge are file transfer applications hosted on servers in LDH and HDC. They are used to transfer information between business applications, suppliers, vendors, service providers and partners. These applications are all on legacy Operating Systems and out of support with the vendors. Vital and critical business information are transferred via these services and as they are out of support which poses a security risk to the Business. In the event of failure, National Grid Information Technology (IT) will be unable to meet the agreed Service Level Agreements (SLAs) for many key applications because the applications are out of support and we are not entitled to any security patches. Furthermore, the above-mentioned servers are hosted in LDH and HDC which National Grid must exit by July 2020 in order to meet the conditions of the TSA and avoid a financial impact of circa ~£2m from additional RTB for LDH and HDC.
Change Description
The scope of the project is to migrate all National Grid services running on Globalscape, BFTS, Chamois and Revenge to Oracle Fusion Managed File Transfer (MFT) on the Strategic CIS Platform. The scope also includes the decommissioning of the legacy applications. All file transfers between National Grid and Xoserve via STIG 2 Globalscape will be impacted by this change. The Xoserve non -National Grid interfaces will not be migrated by this project and have to be removed by Xoserve before June 2020 so that the legacy applications can be decommissioned.

## Slide 8: 2.5 XRN5093 Update of AUG Table to reflect new EUC bands
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 100%
Distribution Network Operators (DNOs) |  | 
Independent Gas Transporter |  | 
National Grid Transmission |  | 
Impacted Parties:- Shipper (A vote to agree funding split will also be required along with one for approval into capture) |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 15: Demand Estimation
Service Line Impacts (new, amended, existing, deleted), etc. | Service Area 15 has a funding split of 50% Shipper and 50% DNO. ChMC to agree to 100% Shipper funded for this change.
Link to Change Proposal | Link to CP
Change Details
Problem Statement
At present the AUG Table does not fully reflect the combination of End User Categories (EUC) and Product Classes that are utilised by the CDSP. As a result, not all the EUC bands are reflected within the UIG share factors.
Change Description
When the AUG Table was last revised as part of Project Nexus, there were 9 End User Categories and 4 Product Classes, which the table reflected. This allows the AUGE to align the Adjustment Factors it calculates with each End User Category. Since then, EUC Bands 1 & 2 have each been split into four new categories by Change Proposal XRN4665 Creation of New End User Categories: • Non-Prepayment/Domestic • Prepayment/Domestic • Non-Prepayment I&C • Prepayment I&C Modification 0711 seeks to update the AUG Table contained in UNC TPD Section E Annex E-1 to reflect the new EUC bands listed above. This DSC Change proposal is required to make the associated changes within UK Link systems to ensure the updated EUC bands are reflected in the UIG share factor values.

## Slide 9: 2.6 XRN5097 - DSC Service Description Table cosmetic change to service line table v9
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | N/A
Distribution Network Operators (DNOs) | Y | N/A
National Grid Transmission | Y | N/A
Independent Gas Transporter | Y | N/A
Impacted Parties:- All Parties No funding is required as the proposed changes are cosmetic only and the new service line is part of BAU |  | 
Voting Parties and Funding Split
DSC Service Area: | N/A
Service Line Impacts (new, amended, existing, deleted), etc. | One new Service Line and cosmetic changes to a number of existing lines
Link to Change Proposal | Link to CP
Change Details
Problem Statement
1. Creation of the following new line AGST -CS SA9-14 which details how Xoserve as the CDSP will invoke the Supplier Deed of Undertaking on behalf of Gas Transporters 2. Cosmetic updates made to the DSC Service Description Table to a number of service line as a result of an internal review.
Change Description
The amended Service Description table will be issued to each DSC contract manager for consultation. The CDSP will collate any consultation responses and provide these to the DSC Contract Management committee with recommendations for treatment. Unless there are consultation responses that are considered material, the Contract Management committee can approve the proposed Service Description table at the relevant meeting

## Slide 10: 3. New Change Proposals – Post Initial Review None for this meeting

## Slide 11: 4. New Change Proposals – Post Solution Review

## Slide 12: 4.1 New Change Proposals – Post Solution Review
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution Summary Outcome and implementation date outcome |  |  |  | Comments | Xoserve response (where applicable)
 |  | Organisation | Approve | Defer | Reject |  | 
XRN4645 The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) Proposed for November 2020 Release Link to CP Link to Change Pack ref: 2514.1 – JLR – JR Voting: Shippers High level Solution Option £40-£60k | Option 1 and proposed Release was supported by DSG | EDF | X |  |  | Whilst we support the proposal - we note in the change documentation that an action was taken from DSG to provide shippers with their portfolio relating to this issue | Thank you for your response. We will follow up on the action described and provide the reporting to impacted shippers.
 |  | Npower | X |  |  | We are in support of the 1 solution put forward | 

## Slide 13: 4.2 New Change Proposals – Post Solution Review
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution Summary Outcome and implementation date outcome |  |  |  | Comments | Xoserve response (where applicable)
 |  | Organisation | Approve | Defer | Reject |  | 
XRN4801- Additional Information to be made available on DES Proposed November 2020 Release Link to CP Link to Change Pack ref 2514.4 - JLR – JR Voting: Shipper High Level Solution Option £50-£55k | Option 1 and proposed Release was supported by DSG | EDF | X |  |  | This change will add useful information to DES and we question whether same information is/will be available in the Xoserve APIs, if not we would vote to defer this implementation until they are aligned to each other, however on the assumption that they are aligned we vote to approve for now | Regarding your question relating to the alignment of API access, as it currently stands the data to be added to DES as part of XRN4801 will not be made available via API.
 |  | Npower | X |  |  | We support the solution put forward in the HLIA | 

## Slide 14: 4.3 New Change Proposals – Post Solution Review
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution Summary Outcome and implementation date outcome |  |  |  | Comments | Xoserve response (where applicable)
 |  | Organisation | Approve | Defer | Reject |  | 
XRN5014 - Facilitating HyDeploy Live Trials Proposed November 2020 Release Link to CP Link to Change Pack ref 2514.5 - JLR – JR Voting: DNO & Shippers High Level Solution Option £50-£60k | Option 1, delivering both parts and proposed Release was supported by DSG | EDF |  |  | X | In the change pack you mention ‘The use of a hydrogen blend will result in a lower Calorific Value’. I am unable to see how this proposal has considered the impacts in terms of customer billing by the supplier, how the different calorific values would be considered. If this goes ahead changes will be large at supplier end for the sample subset of customers, which would be unquantifiable in terms of a business case. This is why we have rejected this change until this is explored further. | The materiality of this change was discussed at the DSG Meeting on 27th January. Northern Gas Networks (NGN) clarified that it had undertaken analysis to establish the materiality impact was low: • In a worst case scenario, the injection of 20% hydrogen into the network (pilot area) might affect a reduction of 5.9 in the CV range; the current range is 39.9 to 40.1 • There are approximately 670 MPRNs within the HyDeploy2 Pilot area; the average with AQs ~12,000 kWh • NGN has estimated the financial impact to an end-consumer will be less than £60 for the whole 10-month period • End-consumers will be financially recompensed by NGN through the new GT Voluntary Consumer Payment
 |  | NGN | X |  |  | We would like to note that Part 2: Introduction of a new MPRN ‘Trial Indicator’ mentioned in the Solution Options consultation document relates to a separate change proposal: XRN5048 ‘Make an indicator available where a Supply Meter Point form part of a Network Trial’ and agree that both XRNs should be implemented together. The HyDeploy2 Pilot related to this proposal is scheduled to begin in November/December 2020, we require this and XRN5048 to be implemented prior to this date. | We will contact you prior to ChMC in relation to your comments on Part 2 / XRN5048.
 |  | npower | X |  |  | We support the proposed solution but need to understand the cost vs. benefits of part 2 being delivered. | Thank you for your representation. It should be noted that Part 2 will be wholly funded by the Networks.

## Slide 15: 4.4 New Change Proposals – Post Solution Review
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution Summary Outcome and implementation date outcome |  |  |  | Comments | Xoserve response (where applicable)
 |  | Organisation | Approve | Defer | Reject |  | 
XRN5064 - Meter Asset Enquiry API Enhancements Proposed adhoc Data Release (TBA) Link to CP Link to Change Pack ref 2514.6 - JLR – JR Voting: Shipper, DNO and IGT High Level Solution Option £50-£60k | N/A | EDF | X |  |  |  | 
 |  | npower | X |  |  | Supportive of the 1 solution put forward | 

## Slide 16: 4.5 New Change Proposals – Post Solution Review
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
XRN4780 - PartC - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) Proposed November 2020 Release Link to CP Link to Change Pack ref 2514.6 - JLR – JR Voting: Shipper The following slides provide Xoserve responses to the Reps. | DSG had no input to a preferred option, however Xoserve has encouraged them to submit Reps. | EDF |  |  | X | We believe that any of the options presented here should not be progressed without changes to RGMA processes used by MAPs/MAMs. We cannot see how we as a supplier/shipper can fulfil our obligations to 1 – provide MAP ID as a mandatory data item (option 2), or 2 - uphold industry data quality of metering information inc MAP ID where MAMs are not mastering the data as part of the asset information (referring to option 3 limitations) See Change Pack for full Rep
 |  | OVO |  | X |  | Preferred Solution Option: Overview OVO have chosen the option to defer the implementation date and proposed solutions for reasons that have been set out in the Change Pack rep. See Change Pack for full Rep
 |  | Centrica | X |  |  | Preferred Solution Option: Solution 3 – Centrica Preferred option. It would be preferable, as a Shipper, that we only receive notifications of an update to a MAP ID, i.e. where it has changed, rather than duplicate updates made by MAPs. See Change Pack for full Rep
 |  | SSE | X |  |  | We support this change. Our preference is for solution Option 3. We note that Option 2, although not our preferred option, also has merit in providing a robust method to the update of MAP IDs.
 |  | Npower | X |  |  | We are most supportive of Option 3 (Xoserve's preferred solution), as this covers all elements i.e. control, disputes and a complete process. Currently the MAP is a non-mandatory item, and this has led to this position and the requirement for a solution, which is partly because Suppliers aren't always aware or in a position to manage. Option 3 places more control of this item with the MAM, and they are best placed to take MAP ownership. . See Change Pack for full Rep

## Slide 17: XRN4780-C Rep Summary
We posed two questions in the January Change Pack:
  Should the MAP Id notification be made conditional mandatory in RGMA flows where a new asset is installed, (including exchanges)
      In doing so, we highlighted that this would result in rejection of RGMA transactions that did not include this information
  Which party should update the MAP Id in UK Link systems
      CDSP suggested MAP direct updates
This change is currently scheduled for November 2020 release.
Any decision to defer would mean that this change would be removed from the scope of this release.

## Slide 18: XRN4780-C Rep Summary
We received 5 responses to the Change Pack
All parties confirmed that failure to provide MAP Id should NOT result in rejection of the RGMA transaction, so Option 2 was rejected by all as being the preferred option
3 responses approving the proposed solution of MAP direct update (option 3) but one indicated potential MAM update as an alternative
1 response rejecting all solutions but indicated that MAMs should be solely responsible for updating MAP Id
1 response that proposed deferral but suggested MAMs providing updates, but could see the merits of the MAPs doing so with the appropriate regulatory framework being in place

## Slide 19: XRN4780-C Rep Summary
Option 3 (Direct Updates to MAP Id from non Shipper parties) is the preferred industry solution
Who is to carry out direct updates to MAP Id field within UK Link Systems?
Xoserve has reviewed the responses and considered the following to aid ChMC…

## Slide 20: XRN4780-C Rep Summary
MAP Updates (Original proposal)
  + As a community, MAPs have highlighted that the loss of assets is impacting consumer charges, and consequently this is a pillar of the CSS programme functionality and features in the business case for the Faster Switching Programme.
      In order to achieve these benefits the data needs to be maintained effectively, and we considered that MAPs are best incentivised to do so.
  + MAPs have been engaged and are actively petitioning to update MAP Id directly in UK Link systems
  - We do recognise that this route will present challenges about how obligations are placed on MAPs, and crucially how these are enforced. We have reached out to Ofgem to understand what, if anything, they are proposing in this regard.

## Slide 21: XRN4780-C Rep Summary
MAM Updates (Following Rep responses)
  + We can see benefits in this approach as MAMs are currently mandated to send RGMA flows, so amendment to such obligations to also send a notification should present a reasonably straight forward regulatory change.
    This is particularly true with the Retail Code Consolidation where MAMCOP will be incorporated into REC and MAMs will be subject to REC Performance Assurance measures
  - MAMs have not been engaged to do so, so we would need to assess how this obligation would be applied
  - We would need to assess what further business rules would be required, would we need to validate that the MAM providing notification was recorded as the MAM on UK Link systems? In doing so, any solution efficacy will rely on Suppliers (via their Shippers) maintaining this information, something that has been recognised as an industry issue for many years without being properly resolved.
  IF MAM Update solution option is chosen we would recommend that ANY MAM be allowed to update the MAP Id, not just the MAM recorded as appointed on UK Link systems

## Slide 22: 4.6 New Change Proposals – Post Solution Review
Agenda Item | XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG Preferred Option and date | Solution & Implementation Summary outcome |  |  |  | Comments | Responses
 |  |  | Organisation | Approve | Defer | Reject |  | 
 | XRN4992 MOD 0687 - Creation of new charge to recover Last Resort Supply Payments - Solution Review Implementation date depends on solution option Link to Change Proposal 2456.2 - RT - PO Change Pack Voting: Shipper and DNO High Level Solution Option £ | Interim solution – Option 4 Enduring solution – Option 1 | NGN | X |  |  |  | 
 |  |  | EDF | X |  |  | Stated option 4 however also approved to DSG preferred 2 stage option | 
 |  |  | Npower | X |  |  |  | 
 |  |  | Scottish Power | X |  |  | SP wanted to understand funding implications and if industry will be charged twice with a 2-stage implementation. | Industry would be required to fund implementation of both solutions however the cost for long term solution will not include any work already implemented.
For XRN4992 enduring solution to be delivered within the November 2020 Major Release, the Committee must approve the change being in scope at the February 2020 ChMC meeting. If an Ofgem decision on Modification 0687 is not provided before the February meeting, the Committee would have to approve Xoserve working at risk or alternatively defer the decision and remove the change from November 2020 release.

## Slide 23: 5. Implementation Plan
Please see the following slides for an overview of:
Detail Design Changes for approval
Outages
  No new outages.
  Change of date to the RTP outage (highlighted on slide)
Attached is the full Implementation Plan document.

## Slide 24
Functional Changes |  |  |  |  |  | 
XRN / Title | Solution & Implementation Summary outcome |  |  |  | Comments | Xoserve response
 | Organisation | Approve | Deferred | Reject |  | 
XRN4941 Auto updates to meter read frequency (MOD0692) Change Pack ref: 2489.11 - RT – PO Link to CP June 2020 Release Voting: Shipper | NGN | X |  |  |  | 
 | Npower | X |  |  |  | 
 | Orsted | X |  |  |  | 
 | Scottish Power | X |  |  |  | 
 | eon | X Solution |  | X Date | We are supportive of the solution and have no concerns on this, however, we are not supportive of the implementation date proposed, currently the modification has not been approved nor been given direction on when the principles will become effective in code. We would prefer this approved with the 6 months implementation notice post modification approval, therefore we suggest Nov 2020 implementation instead of June 2020. | Thank you for your representation, we will feed this into ChMC for a final decision.
 | EDF |  |  | X | We approve this where AQ changes above 293000kwh However we reject the other instances - we do not believe that data held by CDSP will always be accurate or within out control and therefore this will lead to problems e.g. decisions on MRF will be potentially based on inaccurate information such as meters which are defined as S2 by some iGTs but will never be in DCC. Also once DCC flag is active it cannot be switched off even if it is apparent that data is wrong so again will never be smart. In these instances we will be expected to read monthly and will not always be able to do so. | Thank you for your representation. Regarding your concerns with the proposed solution, we are, for XRN4941, following the rules set out in the related modification. The determination of SMART enabled Supply Meter Points and the concerns with them should be raised and discussed at UNC Distribution Workgroup.
The Appeal on Modification 0692S Panel Members determined to confirm their original determination, by majority vote (12 out of 13); Therefore, this self-governance Modification is due to be implemented on a date to be confirmed by Transporters, following consultation with the DSC Change Committee. The Appealing Party may raise an Appeal with the Authority no later than 06 February 2020.
The appeal had not been raised when this slide was submitted for publishing, at which point there are 3 possible approval options which will be discussed in the meeting.

## Slide 25: 5. Implementation Plan – Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
4970 | DCC | 28/03/2020 | TBC | 29/03/2020 | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or revice files during the maintainence window as the application is switcheed from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/11/2019
4970 | CMS | 11/04/2020 | TBC | 12/04/2020 | TBC | This is the cutover of the production environment for CMS, the outage will be on the weekend, the impact to the industry should be minor and that the Contact Management System will be unable to send or recieve files, raise contacts and will not allow users to log on during the maintainence window as the application is switcheed from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/11/2019
4970 | RTP | 10/04/2020 | TBC | 10/04/2020 | TBC | This is the cutover of the entire RTP application, the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintainence window as the application is switched from PET/KET to Chess/Cress. | 13/11/2019
4970 | AD & BoKs | 28/03/2020 | TBC | 29/03/2020 | TBC | This will be cutover of the AD & BoKs application, the which includes the Actives Directory (AD), BoKs and Squid proxy the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintenance window as the application is switched from PET/KET to Chess/Cress. | 13/11/2019
4970 | Birst Connector | 11/04/2020 | TBC | 12/04/2020 | TBC | This is the cutover of the entire Birst connector application, the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintainence window as the application is switched from PET/KET to Chess/Cress. | 13/11/2019
4970 | Control M | 16/05/2020 | TBC | 17/05/2020 | TBC | This is the cutover of the entire Control M application, the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintainence window as the application is switched from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/11/2019
4970 | Internet routing for UKLink | 23/05/2020 | TBC | 24/05/2020 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or recieve files to corisonding systems during the maintainence window as the application is switched from PET/KET to Chess/Cress. | 13/11/2019
4550 | Gemini | 05/07/2020 | 03:00 | 05/07/2020 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 11/12/2019

## Slide 26: 6. Approval of Change documents
6.1 CCR for XRN4688 Brownfield AQ Corrections
  Voting: Shipper
6.2 CCR for XRN4789 Updating Shipper Reporting Packs and glossary
  Voting: Shipper
6.3 CCR for XRN4795 Amendments to the PARR (520a) reporting
  Voting: Shipper
6.4 CCR for XRN4980 Change Supply Point Enquiry API to add in extra fields and make certain other fields visible
  Voting: Shipper

## Slide 27: 7. June 2020 Release

## Slide 28: 7.1 XRN4996 - June 20 Release - Status Update
12th February 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Replan completed following descope of 4 changes, Market Trials inclusion pending confirmation. Delivery: Build has completed for 2 changes, these are now being System Tested. The remaining 4 changes are currently in Build and progressing to plan. Scope: Change Request for XRN4780B has been approved and is currently in Design phase – no cost implications to the project. Revised BER being shared for information following descope of xrn4941 on 08/01/20. Implementation: Implementation date of Saturday 27th June confirmed. |  |  | 
Risks and Issues | Risk – There is a risk that SMS set up and configuration costs may increase following design approval and solution because service provided to build logic app and blob storage in Microsoft Azure for integration into SMS/Email service has not yet been confirmed leading to an increase in set up and configuration costs. |  |  | 
Cost | Project delivery costs expected to be within approved range. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 29: 7.2 XRN4996 - June 20 Confirmation to Proceed with Reduced Scope Market Trials
Reduced Scope
6 weeks (Prep – April) (Execution - May) | £101,500 | XRN4772, XRN4850, XRN4932 | AWV, FWV, CNF, CNC, NRL | 15-21 | 8 (4 DN, 2 IGT, 2 Shippers)
Duration | High Level Cost (excludes £20k set up costs) | 3 Changes | Files considered | No. Of Test cases | Participants
XRN Reference | MT - High level Scenarios | No. of Test Cases
XRN4772 | Processing AWV and FWV from weather station with additional fields for Wind, Temperature, Solar and Precipitation | 4-6
XRN4850 | Processing CNF with broadcast contact types Processing CNC with broadcast contact types Exchanging files with SMS/Email provider Sharing broadcast usage and delivery status details | 8-10
XRN4932 | NRL file with Conversion flag update flag Sharing MBR file after read estimation | 3-5
XRN 4941 | De-scoped in January ChMC, no longer in scope for MT | n/a
Test Scenarios Summary
Please note: Based upon timelines, June 20 Market Trials will be need to run in parallel with CSS Market Trials and this will result in increased
pressure on resource availability for all involved parties.

## Slide 30: XRN4996 - June 20 Market Trials for XRN4850 only
5 weeks (April-May) | £55,250 | XRN4850 | CNF,CNC SMS Broadcast | 8-10 | 4 DN
Duration | High Level Cost | 1 Change | Files considered | No. Of Test cases | Participants
XRN Reference | MT - High level Scenarios | No. of Test Cases
XRN4850 | Processing CNF with broadcast contact types Processing CNC with broadcast contact types Exchanging files with SMS/Email provider Sharing broadcast usage and delivery status details | 8-10
Test Scenarios Summary
Please note: Based upon timelines, June 20 Market Trials will be need to run in parallel with CSS Market Trials and this will result in increased
pressure on resource availability for all involved parties.
Preparation
Test Execution
Re-test
2 weeks
1 week
2 weeks

## Slide 31: June 20 Market Trials Timeline

## Slide 32: Following descope of XRN4941 (Auto Updates to Meter Read Frequency MOD0692) at ChMC on 8th January:
XRN4941 Spend Breakdown
Design Spend – £4,298.73
  Design Costs incurred as part of June 20 however, assuming no changes to scope, the design can be reused for delivery as part of November 20
Delivery Spend - £21,509
  Total cost of this change was £61,731, however only a reduction of £40,222 will be realised due to the inclusion of some non change specific costs (i.e. Project Management/Shared Resource costs)
Total Spend - £25,807.73
XRN4941 Saving Breakdown
MT Cost Savings - £12,500
  MT option has been amended to remove XRN4941 from the scope of Market Trials

## Slide 33: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion – 19/09/19
Design Completion – 13/12/19
Build & Unit Test Completion – 31/01/20
System & UAT Completion – 24/04/20
Regression Test Completion – 29/05/20
Implementation – 20/06/20
PIS Completion – 25/09/20 (provisional)

## Slide 34: June 20 Release Summary
June 20 Release consists of 8 changes, Implementation is planned for June 2020:
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4941* - Auto updates to meter read frequency (MOD0692)
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs. Descoped at ChMC on 08/01/20
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)

## Slide 35: 7.3 Supporting Information for Revised BER
Shipper Changes
Shipper costs have decreased because:
XRN4941 descoped – 100% shipper funded (costs are smeared proportionately across the release and are not change specific)
As a result of xrn4941 descope, MT also descoped, inc. Set Up costs.
DN Changes
DN costs have increased because:
XRN4941 descoped – 100% shipper funded (costs are smeared proportionately across the release and are not change specific)
MT Set Up costs smeared across 3 changes not 4
Revised BER
Approved BER
IGT Changes
DN costs have increased because:
XRN4941 descoped – 100% shipper funded (costs are smeared proportionately across the release and are not change specific)
MT Set Up costs smeared across 3 changes not 4
Marked up Revised BER
Clean Revised BER

## Slide 36: Change Training – June Release 2020
Approval required for;
Training needs identified per change
Delivery method identified
  Please note we are also supportive of hosting events and virtual training events should they be deemed beneficial
Notes: For information;
As a baseline we are recommending delivery of all the changes, using E-Learning. As our E-learning tools enable; interactive and engaging content creation including a mix of audio, video, textual and visual content.
Training delivery is scheduled for April 2020

## Slide 37: Change Training – June Release 2020
Change | Training needs identified | Delivery method
XRN 4772 - Composite Weather Variable (CWV) Improvements | Components and definitions of CWV Downstream processes using CWV Gas demand and CWV information / relationship | E learning
XRN 4850 - Notification of customer contact details to transporters | File format changes Accessing portal and new screens Use cases for process and GDPR rules Overall process, timescales and system rules (including rejections) Report & delivery GDN / Supplier sign posting | Blended learning; E learning Classroom
XRN 4865 - Amendment to Treatment and Reporting of CYCL Reads | Clarification on file formats (only allowable data change) CYCL information inclusive of read tolerance Information on any consequential changes to; read replacements, estimates etc. | E learning

## Slide 38
Change | Training needs identified | Delivery method
XRN 4888 - Removing duplicate address update validation for IGT supply meter points via CMS | Report details Process to remove duplicates identified Address update best practice | E learning
XRN 4930 - Requirement to inform Shipper of Meter Link Code Change | File format changes Meter link code amendment & challenge process Roles of stakeholders defined Meter link types defined Invoicing impacts | E learning
XRN 4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Process, timescales and system rules AQ process – related to usage of conversion factor Process to amend conversion factors Information on where to view conversion factor UIG and conversion factor relationship File format changes PAC & Shipper reporting relating to conversion factors | E learning

## Slide 39: 8.1 XRN4665 – EUC Release
12/02/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Post Implementation Support (PIS) All PIS activities successfully completed as planned with all EUC changes handed over to Tech Ops Closedown Work in progress during ‘Closedown’ on a six week delivery plan to resolve identified aggregation issue of CWV & Shrinkage values within the BW report ‘Network Throughput Data’ All Build & Unit Testing Activities Completed as Planned All SIT Activities Completed as Planned All UAT Activities Completed as Planned Fix Deployed Successfully into Production on 31/01 PIS Monitoring Tracking to Plan |  |  | 
Risks and Issues | No key open Risks or Issues |  |  | 
Cost | Project delivery costs are tracking to approved internal budgets (Revised BER to include Financial Risk margin approved at ChMC on 10/07/19) |  |  | 
Resources | No Issues |  |  | 

## Slide 40: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Project now in Closedown
6 week delivery plan in progress to resolve identified aggregation issue of CWV & Shrinkage values error within the BW Report ‘Network Throughput Data’
Network Throughput Data BW Report ‘Fix’ successfully deployed into Production on 31/01
NRL Issued
T67 Issued

## Slide 41: BW Report Fix ‘Network Throughput Data’ High Level Timeline

## Slide 42: 8.2 XRN4828 - Nov 19 Release - Status Update
12/02/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS and First Usage monitoring completed successfully Handover of associated changes to Tech Ops approved and completed Closedown activities ongoing |  |  | 
Risks and Issues | No key Risks or Issues associated |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | No Issues |  |  | 

## Slide 43: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Successful Implementation – 09/11/19
FU & PIS successfully completed with all Nov 19 changes handed over to Tech Ops
Closedown activities commenced and ongoing

## Slide 44: 8.3 XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Progress Update
12th February 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: 8 Shippers participating in the Proof of Concept have now provided files to support the exercise Circa 9 million MPRNs and associated data has been captured and will be used in the comparison and deep dive analysis ‘Steps’ of the Project Step 1 ‘Initial Data Comparison’ exercise has been completed using the data comparison tool Step 1 outputs originally due to be published in January 2020 are now expected to be shared in the first half of February 2020. This delay is due to a large volume of data provided by Shippers and additional time needed to support triage and validation of datasets ahead of uploading into the data comparison tool Step 2 ‘Deep Dive’ build activities are due to commence in the coming weeks Customer Engagement and Communications: Web page now live and fortnightly updates being provided Weekly dialogue with Shippers directly involved in the exercise Plans being developed to define how Step 1 and 2 findings will be shared with wider Customer audience (e.g. ChMC, DSG, PAC) |  |  | 
Risks and Issues | There is a risk that due to the volume of data received, the resource and schedule assigned to the analysis ‘Steps’ may be greater than originally anticipated. Mitigation being deployed is outlined below; Extend timescales of the analysis Steps to ensure data outputs are robustly assured and clearly communicated PoC Project team to understand the size of the remaining tasks of the PoC and request appropriate support |  |  | 
Cost | Remains within Approved BER (£270k) |  |  | 
Resources | Continue to work with internal teams (e.g. SME team) to manage resource demands Additional resource likely to be needed to support Customer engagement and communications over the coming weeks |  |  | 
XRN4914 MOD 0651 - Retrospective Data Update Provision - ChMC Update 12th February

## Slide 45: XRN4914 – Retro proof of concept - timeline
2019 / 2020
November | December | January | February | March
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 1
29th Nov
Design (Step 1)
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
today
Planning
Develop (Step 2)
Testing (Step 2)
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Customer engagement of File receipt
Still ongoing
Actual data files can be accepted
Support
Step 2a Categories
Weekly project update via external communication methods
Test data
files in
Checkpoint 3
21st Feb
Date for slicing data
8th Dec
Output from Step 1
Output from Step 2b
Recommendations
XRN4914 MOD 0651 - Retrospective Data Update Provision
12th February
Develop (Step 1)
Testing (Step 1)
Checkpoint 2
7th Feb
Design (Step 2)
Output from Step 2a
Step 2b MAM
Output from Step 2c
Step 2c RGMA
Step 2d Shipper Fixed
Output from Step 2d
Dates need to be confirmed post Step 1
results as volumes will inform task size

## Slide 46: 8.4 XRN5057 – Minor Release Drop 6- Status Update
12th February 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: MiRD6 consists of 2 changes and both are on plan for delivery on 29/02/2020. Delivery: Build is complete, ST is complete and RT is due to start w/c 03/02/20. Scope: The agreed scope of XRN5057 is for 2 changes XRN 4955 - Amendment of MDD PSR Needs Codes and Needs Codes Descriptions and XRN4997 - Introduction of New Charge Codes for Pro-Active Payment of GSOP 3 and GSOP 13 and GT Voluntary Consumer Payments Implementation: Implementation date of Saturday 29th February has been agreed. |  |  | 
Risks and Issues | Risk – There is a risk that Minor Release Drop 6 and June 2020 projects could be making changes to the same common code objects which could delay the Build and Testing phases of both projects. Both projects are working together to ensure there are no conflicts |  |  | 
Cost | £26K is required to deliver the AMT and BW changes for this Release. Approved by Xoserve IRC and within MiR budget |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 47: XRN5057 – MiRD6 Release Timelines
Key Milestone Dates:
Design Completed – 13/12/19
Build & Functional Unit Test Completion – 03/01/20
System Test & Assurance Completion – 24/01/20
Regression Test & Assurance Completion – 14/02/20
Implementation Date – 29/02/20
PIS Completion – 13/03/20
CR ID | 11-Nov-19 | 18-Nov-19 | 25-Nov-19 | 02-Dec-19 | 09-Dec-19 | 16-Dec-19 | 23-Dec-19 | 30-Dec-19 | 06-Jan-20 | 13-Jan-20 | 20-Jan-20 | 27-Jan-20 | 03-Feb-20 | 10-Feb-20 | 17-Feb-20 | 24-Feb-20 | 02-Mar-20 | 09-Mar-20
 | Pre-Work |  | Wk 1 | Wk 2 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17
XRN 5057 | IA & Approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Design & Approval |  | Build + FUT |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | ST + Assurance |  |  | Code Merge |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | RT + Assurance |  | Contingency | Imp 29/02 | PIS | 

## Slide 48: 8.5 UK Link – Nov 2020 Major Release Scope – for approval
Feb 12th 2020 CHMC

## Slide 49: November 2020 Scope – For Approval
Candidate changes:
  T-shirt sizes
  High level estimates
  Funding arrangements
  Comments
Assumptions

## Slide 50: November 2020 Major Release Candidates
XRN | Description | Relative Size | T-Shirt | High Level Estimates | Finance | Capture Status / Comments
5014 | Hydeploy Trial | 13 | Large | £25,000 | DNO | HLSOs in Review
5036 | Updates to must read process | 5 | Small | £30,000 | DNO | Requirements in Review - Option 1 DSG preferred solution. Change Pack to be issued on 15/02.
4897 / 4899 | Contact details | 21 | X- Large | £45000 (£22,500 each) | Shippers | HLSOs in Review – Cost in review due to additional requirements and therefore increased test scope
4992 | Supplier of last resort charge type | 5 | Medium | £120,000 (option1) | Shippers | DSG Review – Ofgem decision pending for Option 1. Option 4 workaround circa £30K
4931 | Space in SPA files | 8 | Medium | £25,000 | Shippers | DSG Review
4801 | Additional info in DES | 8 | Medium | £55,000 | Shippers | HLSOs in Review
4780c | MAP ID (Part C) | 13 | Large | £130,000 | Shippers (CSS) | Requirements in Review - Change Pack issued (Reps closeout 10/02). CDSP recommends Option 3.
4941 | Auto Updates to Meter Read Frequency | 13 | Large | £65,000 | Shippers | Ready - Descoped from June 20
4691 | CSEPs: CGI Files | 5 | Small | £110,000 | DNO (90%) IGT (10%) | Ready - Descoped from June 20
4692 | CSEPs: CIN Files | 5 | Small | £99,000 | DNO (90%) IGT (10%) | Ready - Descoped from June 20
4871b | Ratchet Regime changes (Part B) | 13 | Large | £120,000 | DNO | Ready - Descoped from June 20
 | Total Estimates | 109 |  | £824,000 |  | 

## Slide 51: Assumptions
Market Trials costs are not included
Market Trials coverage options and associated costs will be presented during Design Phase
User Acceptance Testing costs not included:
  For 4897 and 4899 testing is expected to be extensive as indicated in the T-shirt size. Full costs will be an output of the Design phase
  Where there is a dependency on Ofgem decisions, 4992, 4941, User Acceptance Testing costs will differ based on that decision
For 4691, 4692, 4871b and 4941 costs (excluding work completed) from June 2020 Release have been quoted as per the June SoW. Economies of scale may bring these costs down depending on the output of Design for the other changes

## Slide 52: UK Link Releases Update – For Information
12th Feb 2020 CHMC

## Slide 53: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Assumes that there will be a Major Release in Nov 2020
Please note that this includes potential activity within UK Link over the next 24 months
BER Approval
10/04/18
RETRO
Potential Activity
Governance Approval dates tbc…
On track
At risk
Key:
Complete
Feb-20
Jun - 20
Nov 20
4779
MiR 6
BER Approval
May-20
CSSC activity
CSSC
Scope approval – Feb ChMC
EQR Approval – March ChMC

## Slide 54: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Closedown | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Closedown | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Closedown | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Closedown | November 2019 | Low | Shipper
4779 | 4779 | AQ into PARR reports | In Closedown | Standalone BW | Medium | PAC
Feb 20 | 4896 | Rejection code reword – defect 1492 / End User Categories (EUC file format descriptions | In Delivery | Documentation | N/A | N/A
MiR D6 Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Delivery | MiR D6 | Medium | N/A
 | 4997 | Introducing new charge codes for pro-active payment of GSOP 3 and GSOP 13 | In Delivery | MiR D6 | Small | N/A
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June-2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June-2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June-2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June-2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June-2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | November 2020 | N/A | DNO

## Slide 55: UK Link – Unallocated Changes
XRN# | Description | Capture Status | Release Type | Indicative Release | Complexity | Points
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | In capture | Major | tbc | Tbc | tbc
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In capture | tbc | tbc | tbc | tbc
4896 | Failure to Supply Gas System and Template Amendment | Requirements in review | Minor | tbc | Small | 5
4914 | Retro (MOD 651) | On hold for POC | Standalone | tbc | tbc | tbc
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Requirements in review | Minor | Tbc | tbc | tbc
4978 | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | In capture | tbc | tbc | tbc | tbc
4990 | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | Ready for assignment | Major | tbc | tbc | tbc
5027 | UK Link data cleanse of conversion factor in line with MOD681s | In capture | tbc | tbc | tbc | Tbc
5038 | Convert class 2, 3, 4 to class 1 (MOD691) | In Capture | Tbc | Tbc | Tbc | Tbc
5070 | Amendment to isolation flag | In Capture | Tbc | Tbc | Tbc | Tbc
5072 | Class 4 with AMR/D4 installed. RGMA flow received with no RTC count | In Capture | Tbc | Tbc | Tbc | Tbc
Notes: I have removed all of the line items that we have detailed within the Nov 20 Release slide to remove duplication and ‘clutter from this slide’.
Customer team need to include all of the changes that they have on their books (I hear rumours that Simon has 37 changes) so that DSG / Change Management can provide some direction on priorities. We can then use this list as Industry priorities to use going forward. This should be re-visited every month and new changes slotted in based on DSG / Change Management priority so that we are only ever looking at high priority items as per the direction provided by our customers. Just a thought.

## Slide 56: Glossary / RAG
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)
RAG Status | Description
RED | Change at high risk for Nov 20 inclusion as not sufficiently developed
AMBER | Change may be ready for Nov 20 release if governance completed in time
GREEN | Change ready for inclusion in Nov 20
GREY | Change not being considered for Nov 20

## Slide 57: 8.6 UK Link POAP

## Slide 58: 8.7.1 Data Office Changes

## Slide 59
8.7.1 Customer Impacting Data Changes: XRNs
Change Proposals | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Comments
4738: Shipper portfolio update of proposed Formula Year AQ/SOQ |  |  |  |  |  | On target for delivery
4859: Increasing MAM Access to CDSP Data to Mitigate Reduced MAM Appointment Timescales |  |  |  |  |  | Data Strategy to confirm start up for product user case
4860: National ‘Temporary’ UIG Monitoring |  |  |  |  |  | Data Strategy to confirm start up for product user case
4779: UNC Modification 0657S - Adding AQ reporting to the PARR |  |  |  |  |  | Change due for delivery for January PARR Report run
4713: Actual read following estimated transfer read calculating AQ of 1 |  |  |  |  |  | Further DSG discussion required
5004 – Golden Bullet Report |  |  |  |  |  | Part B no longer required. Pricing Managers to approve solution w/c 10th Feb
4874 – Must Read Invoicing Validation |  |  |  |  |  | Due for delivery end February
Capture
**Estimated Delivery
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.

## Slide 60
Customer Impacting Data Changes: XRNs
Change Proposals | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Comments
XRN4929: BG Request for IGT Elected Sites |  |  |  |  |  | Report ready for February run
Capture
**Estimated Delivery
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.

## Slide 61: 8.7.2 Data DISCOVERY platform - Updates

## Slide 62: DDP Drop 3 / PAFA update
PAFA Sprint
Delivered as planned on the 17th January
Shipper Sprint 3
The sprint is on schedule to implement by COB 31st January as planned.
Shipper stretch targets
Increase download limit to 500k – to all customers
Rebrand of Portfolio dashboard
Enhanced Warband reports
Enhancements to existing read dashboards
Beta Team have signed off the dashboards and we are in the process of implementation
PAFA access goes to MOD panel in February, post approval their access will be switched on
All scope delivered and signed off by PAFA.

## Slide 63
Work To Date:
Validated Asset User Stories for customer teams to define suggested scope
Ring fenced delivery team
Commenced Enduring Data Model
Approach:
Agile delivery approach utilising insight from a customer Beta Team (yet to be established)
Methodologies and best practices gained from previous drops will be used.
A product backlog will be produced and maintain overall delivery and plan future drops.
What are we delivering:
An online BI portal for Shippers to access Asset Data
Provide Shippers with Business Insights
To produce a set of pre-defined dashboards
Increase the available data within the data discovery platform
Shippers will be able to:
Access dashboards / data via an online portal for No Meter Recorded / No Meter Recorded with Data flow.
Gain insight from predefined dashboards to assist in their day to day operations.
The users will be able to drill down to Meter Point level information.
All dashboards and reports will be downloadable as a pdf or excel file
Data will be updated daily to give up to a more up to date view of their business
Data Discovery Platform – Drop 4 Asset

## Slide 64: 9. Central Switching Service Consequential & DSC Change Management Committee

## Slide 65
New XRN
Approval into capture
Solution Review
Review of solution options
Implementation Plan
Approval of solution
BER
Approval of design costs
CCR
Approval to close project down
BAU Major Release Touchpoints (ChMC and DSG)
Dashboard updates
The Change Management Committee (ChMC) and it’s advisory Delivery Sub Group (DSG) steer major releases from the point of accepting individual Change Proposals (XRNs) into the CDSP ‘Capture’ phase through to approval of project close down
The drawing below depicts this process at a high level

## Slide 66
New XRN
Approval into capture
Solution Review
Review of solution options
Implementation Plan
Approval of solution
BER
Approval of design costs
CCR
Approval to close project down
Interactions with CSSC to date (ChMC, DSG & CoMC)
ChMC & CoMC Dashboard updates
CSSC is being funded by its own unique budget line as defined and approved in the Business Plan and not via the DSC Change Budget
As such the BAU approach to drawing down funding doesn’t follow the same route as in the previously slide
However, elements of the BAU approach have been utilised to agree solutions
Spend draw-down is approved at Xoserve Board level with updates taken into CoMC (and planned for ChMC)

## Slide 67
Summary & Next Steps
Xoserve CSSC programme is funded by its own unique budget line as defined and approved in the Business Plan and not via the DSC Change Budget, but updates will continue to be shared in monthly DSC Change and Contact Committees
Significant CSS dates aren’t controlled by Xoserve, however all dates that impact other parties (such as Market Trial period) are communicated as soon as possible
Consideration over the impact of BAU change on CSSC is being undertaken and this will require an appropriate debate in ChMC (planned for March 2020)

## Slide 68: 10. UIG Task Force Progress Report
Change Management Committee 12/02/2020

## Slide 69: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  UIG Task Force Activities migration post October 19

## Slide 70: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Attend January Change Management Committee | 08/01/20 | Complete
Attend January Contract Management Committee | 15/01/20 | Complete
Attend January UIG Work Group | 21/01/20 | Complete
Attend Work Group 674 | 27/01/20 | Complete
Executive Summary Update | W/c 03/02/20 | On target
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Support Mod development (All) | ongoing | G
Development of automated UIG reporting | End of Feb 20 | Revised target
Attend February Change Management Committee | 12/02/20 | G
Attend February Contract Management Committee | 19/02/20 | G
Updated UIG Investigation Guide | w/c 24/02/20 | G
Attend February UIG Work Group | 25/02/20 | G
Attend WorkGroup 0674 February meeting | 26/02/20 | G

## Slide 71: Plan on Page Updated
 | October |  |  |  | November |  |  |  | December |  |  |  | January 2020 |  |  |  | February 2020 |  |  |  | March 2020 |  |  |  | 
 | 07/10 | 14/10 | 21/10 | 28/10 | 04/11 | 11/11 | 18/11 | 25/11 | 2/12 | 09/12 | 16/12 | 20/12 | 06/01 | 13/01 | 20/01 | 27/01 | 03/02 | 10/02 | 17/02 | 24/02 | 2/03 | 09/03 | 16/03 | 23/03 | 30/3
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
Issue analysis and tracking
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Support Mod development
Review/draft updates to UIG user guide ongoing
BAU Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan
I
09/10 DSC ChMC
I
16/10 CoMC
w/c 11/11 Exec Summary
I
22/10 UIG WG
I
20/11 CoMC
I
26/11 UIG WG
I
13/11 DSC ChMC
Rescheduled
w/c 16/12 Exec Summary
I
11/12 DSC ChMC
I
18/12 CoMC
I
12/12 UIG WG
I
15/01 CoMC
I
21/01 UIG WG
w/c 03/02Exec Summary
I
12/02 DSC ChMC
I
19/02 CoMC
I
25/02 UIG WG
Final phase of Machine Learning complete
C
C
I
08/01 DSC ChMC
I
18/03 CoMC
I
17/03 UIG WG
I
11/03 DSC ChMC
Present Close-down Summary
Transition to BAU
Transition to BAU
Transition to BAU
Activity Complete
Activity Complete
Transition to BAU
Complete

## Slide 72: Recommendations - where we are
4 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692*), 2 sponsored British Gas 0690 & 0691
4 Future review
75 CLOSED
As at 18/12/19
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored 0693R
11 do nothing
3 BAU
21 completed
40 - other options progressed
3 review February
1 review March
14 finding & recommendations = 95 recommendation lines
2 lines Xoserve drafted MODs 3.2.5
1 line MOD 0699 Scottish Power
* UNC Mod 0692 now approved, awaiting UKLink Release

## Slide 73: Overview Of Task Force Funding

## Slide 74: Reminder – UIG Task Force Activities migration post October 19
Pre November Task Force | Post October Customer Support Services Team | Post Oct Customer Change Team
Existing activities which will migrate Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources creation UIG modification alignment creation & publication Machine Learning new analysis Budget mapping and forecast . Support development of new online UIG interactive reporting Activities which will cease Representation at ChMC & CoMC | Existing activities which will be migrated Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources maintenance UIG modification alignment pack maintenance Machine Learning outstanding analysis Budget monitoring for UIG activities Outstanding CP 4853 Interim process to monitor and manually load rejected reads into UK Link where the read was rejected for reason MRE00458 only. Manual work around to be closed out end of October 19. UIG brochure version 2 creation & publication Re-purpose the existing "Lines of investigation tracker" Work with Customer Change team to develop formal project close down New activities which will commence Support maintenance of new online UIG interactive reporting Adhoc new UIG related requests One off activities e.g. simulations/adhoc UIG reporting requests – considered by Customer Support Services and/or directed to raise CP | Live CP4866 Removal of validation on uncorrected read due November release Work with Customer Team complete outstanding UIG related CR's. Newly identified Modifications & CRs

## Slide 75: 11.1 Bubbling Under Report

## Slide 76: 11.2 Gemini Horizon Planning

## Slide 77: 12 Finance and General Change Budget Update

## Slide 78: 13. AOB

## Slide 79: 13.1 Xoserve IX Refresh
Customer Update
12/02/2020

## Slide 80: IX Refresh Customer Update
The project has experienced slippage in the original migration plan. This has resulted in a revised completion date of August 2020
  Key factors:-
    The replacement of all IX servers was introduced into the scope of the project during 2019. This delayed the project moving into implementation. Implementation commenced on 23rd August 2019.
    During implementation, the installation of lines has been more complex then envisaged. (Line availability and Data Centre access)
Gamma have introduced a new senior project team to manage the delivery moving forward
  A deep-dive review has been conducted
  A new implementation approach has been finalised and the project has been broken down into workstreams. Additional resources added.
  A revised project plan has been produced
The legacy Vodafone support contract has been extended to ensure that all customers have a fully supported IX service as the migrations progress
We take this opportunity to thank you for your valued support and patience. Please be assured of our continued commitment to have the IX migration delivered as efficiently and cost- effectively as possible
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 82: 13.2 KVI Change Management Survey Feedback
January 2020

## Slide 83: KVI Change Management Survey – January 2020
8 responses received by customers.
October - achieved a KVI of 100% against our target of 90% rated as ‘Always’ or ‘Usually’
January - achieved a KVI of 87.5% against our target of 90% rated as ‘Always’ or ‘Usually’
Final year end performance = 93%
  Year end performance calculated as the average of the 4 scores received this financial year.
2 reviewers provided further comments on the Change management process in January– see following slides

## Slide 84: Overview
4th Survey completed for year 2019/2020 (Jan)
Issued to approx. 450 Industry contacts
Chart: 
| Apr 2019 | Jan 2019 | July 2019 | Oct 2018 | Oct 2019 | Jan 2020
Total | 0.95 | 0.867 | 0.897 | 0.678 | 1 | 0.873
Sum of % score
month

## Slide 85: I receive timely and fit for purpose information to enable me to manage new changes that impact my organisation
Jan 20 (8)
Oct 19
(6)
Individual question responses Oct19 vs Jan 20
Xoserve presents a range of solution options for each change to enable choice
I trust Xoserve to identify solutions that benefit the whole Industry where possible
Xoserve supports the ability for me to fully engage me in the change process, should I choose to
I trust Xoserve to deliver changes to agreed costs, timescales and quality
Chart: 
Chart: 
Chart: 
| Usually
Total | 6
Chart: 
Chart: 
| Usually
Total | 6
Chart: 
| Always | Usually
Total | 1 | 5
Chart: 
| Usually
Total | 6
Chart: 
| Always | Rarely | Usually
Total | 2 | 1 | 5
Chart: 
| Usually | Always
Total | 7 | 1
Chart: 
| Always | Rarely | Usually
Total | 1 | 1 | 6
Chart: 
| Always | Rarely | Usually
Total | 2 | 1 | 5
Chart: 
| Rarely | Usually
Total | 3 | 5
Chart: 
| Usually
Total | 6

## Slide 86: You said – We did – January 2020
You Said | We Did
I believe Xoserve are exceptional in change management area. My personal engagement has been in DSG capacity and Xoserve ensure that right people are in attendant for the relevant changes to be discussed in session. Paul Orsler and James Rigby are consistently seeking ways to improve the session and customer experience, so that is great to see. | We appreciate you taking the time to provide feedback and are pleased to hear that you are happy with the level of engagement you have experienced from members of the Customer Change Team. We are continually looking to improve our processes so as to enhance customer experience and hope that you continue to provide feedback via the surveys to allow for us to continue the positive engagement with all our customers.
Changes are taking too long to implement. More consideration needs to be given to impacts of change on IGT files and processes as this is an area that is still largely overlooked and we have evidence of invalid data being sent to IGTs as a consequence of fixes that have been implemented to benefit Shippers. | We acknowledge your concerns regarding the length of time it takes to deliver change. We have improved the process around scaling of releases and have recently implemented a ‘t-shirt sizing’ process for change to help plan for change and be able to identify the most efficient and appropriate route for delivery with the intention of implementing change as quickly as customers would want us to whilst ensuring stability of the system and minimal impact to customers down stream. We continually monitor the impacts of change at the point of implementation through the warranty period. We appreciate your feed back in relation to post implementation impacts and will ensure that route cause is identified and you are informed of the steps we are taking to mitigate the risk of similar issues happening in the future.

## Slide 87: 13.3 - External Change Register
January 2020

## Slide 88: Background
The External Change Register is a repository of information relating to the Xoserve change pipeline and its sole purpose is to provide a high level view of the status of changes in the pipeline.
Based on customer feedback we took an action to attempt to simplify the register whilst ensuring it added value to customers and could be used to track change.
The attached provides a view of the amended register along with some initial customer feedback incorporated.
We would ask that you review and provide any further feedback/additions to the register by the end of February to allow for the register to be amended and updated.

## Slide 89: 13.4 DSG Meeting Update
The below table indicates the input we received from DSG on 27th January:
Change and decision required | Impacted Parties | Input from DSG Attendees
XRN5064 – Meter Asset Enquiry API Enhancements – Approval of prioritisation score | Shipper DNs IGTs | Approved
XRN5065 – Addition of Email Address to DES Last Accessed Report – Approval of prioritisation score | Shipper | Approved
XRN5038 – Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD0691) – Approval of prioritisation score | Shipper IGT DNs DMSPs | Approved
XRN5014 – Facilitating HyDeploy2 Live Pilot Slides – Input for Solution Development | Shipper DNs | No comments from attendees
XRN4990 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) – Input for Solution Development | Shipper | DSG agreed with proposed ideas
XRN5036 – Updates to must read process - Solution Option Recommendation | DNs | DSG recommended Option 1
XRN4801 – Additional information to be made viewable on DES – Solution Option Recommendation | Shipper | DSG agreed with proposed solution option
XRN4780(C) – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) – Solution Option Recommendation | Shipper | No comments from attendees

## Slide 90: Number of DSG attendees per Constituency
Chart: 
| GT | Other | Shipper
British Gas | 1
Generis | 1
NGN | 1
Npower | 1
OVO | 1
SGN | 1
Shell Energy | 1
Utiligroup | 1