## Slide 1: CSSC Programme Dashboard
March 2020

## Slide 2
Executive Summary
Programme continues to be at amber trending status, active mitigation of issues and risks is in place in order to maintain the return to green plan. • Internal SIT - commencement hit a few roadblocks with connectivity issues, these have been resolved and SIT is in progress • Performance/NFR Testing - testing focus is currently on Phase 1 (external NFR’s) in order to meet PIT Exit criteria. • Networks - the SI has confirmed that IX will not be required for SIT, however clarity on IX uptake is still required to enable Xoserve to plan for the remaining test phases • Service Management – process baseline requirements still pending from DCC. We continue to escalate the requirement for a CR to be formally raised to account for the change in SIT scope to include Service Management • Data Migration. Late changes to scope and requirements have been tabled by SI. CR to be raised and issued to parties for IA.
Programme Health - RAG |  | 
Overall Programme Status | Current | Current
Programme Plan – On Track | Current | Current
Risk Profile | Current | Current
Resources | Previous | Current
Decisions Required |  | 
Progress (Last Month)
Internal Stage Gate C+ approved First set of Primary APIs delivered UK Link System Test complete Internal SIT testing commenced Smoke Testing with CSSP completed successfully (external milestone) SIT Data Extraction completed All environments delivered Gemini SIT scheduled baselined and SIT execution commenced Market Trials engagement continues to define low level processes (UK Link & Gemini).
Priorities (Next Month)
Continue internal SIT execution, commence NFR Testing. Achieve PIT Exit Continue DES/API deliverables –Remaining Primary, Secondary APIs and DES for SIT Continue Data Migration ST and Data Provision activities Gemini: Continue SIT execution Gemini: UAT planning with the Test team Continue Market Trials engagement with customers Continue preparatory activities for external testing (SIT & DMT)
Programme Update

## Slide 3: CSSC Programme Workstream Updates
RAG Prev MONTH | RAG Curr MONTH | WORK STREAM | SUMMARY
 |  | Data Migration & Provision | Amber status reflective of Switching Programme baselined Data Migration Solution & reconciliation solution has had several changes in-flight that requires to be implemented ahead of external Data Migration Testing. These need to be impact assessed and planned across the relevant workstreams. Data provision has had a knock on impact on timelines as a result of environment readiness issues which caused a delay in commencement of data extraction activities. Activities now complete and pending the CSSP to provide connection details in order for data to be issued.
 |  | Internal Testing (PIT) Internal SIT Performance Testing | Amber status reflective of 5 day delay to the commencement of SIT due to connectivity issues between SAP and API solution. This is now resolved and return to green actions are in place Performance Testing preparation activities are complete and Phase 1 is ready to commence. Phase 1 is focused on PIT Exit criteria, remaining phases will be looking at complete internal scope e.g. API components, UK Link and Data Enquiry Our interim PIT test report has been reviewed by the SI and been signed off with no concerns raised
 |  | Market Trials | Green status: Consequential market trials approach has been signed off. Workshops will continue with our customers to refine the next level phases. Consequential market trials commences on the 29th June 2020
 |  | Service Management | Amber Status. Awaiting confirmed timeline to integrate the Incident and Request processes from the XoS instance to the DCC instance. DCC have requested that Xoserve participate in SIT testing as part of cycle 3 of SIT, but currently this is not in scope for the Xoserve CSSC programme, We have requested a formal CR raised by DCC to incorporate SM into Cycle 3 of SIT.
 |  | Reporting | Green status: No new reporting requirements have been identified following exit of detailed design. No changes to existing reports identified, analysis into three production reports is in progress to understand the underlying data model.
 |  | Networks | Amber Status trending to green. Currently no update on whether any LPs/MPs have selected the IX option. The SI has confirmed that IX is not required for SIT. Full testing of the IX connection will not be possible without involvement of at least one LP/MP during future test phases. Any LPs/MPS selecting IX will also be required to migrate from Vodafone to Gamma ahead of completing the CSS IX connection. Pending confirmation from switching Programme as to usage of IX.
 |  | DES & API | Amber status: Environmental issues, resource constraints and PIT defects, have caused the DES/API workstream to be approximately five days behind schedule for entry into SIT. Additional resources are being sourced with immediate to mitigate resource shortage. Environment issues
 |  | UK Link | Amber status. Secondary API delivery 5 days slippage due to resources addressing SAP API issues.This is not a significant issue as secondary interfaces are not required for SIT entry. RTG: Secure final approval for Secondary API design and complete review of TCS secondary API plan.
 |  | Gemini | Green status: Workstream is on plan and is currently progressing through PIT activities progressing towards UAT
 |  | Business Change | Green status: We are on track to meet all programme milestones and internal business change requirements.
 |  | Environments & Release Management | Green Status Key environments for programme delivered, new environment requirements are being progressed. Release schedule approach has been created and issued to the SI

## Slide 4: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55942 | 48 | Testing | There is a risk that the Xoserve will not be able to carry out the necessary smoke testing of the SIT environment because of the lack of clarity on smoke testing requirements from the SI. | Detailed discussions with the SI to agree requirements for the full period. | Xoserve believe that phase 1 of smoke testing has been completed. SI is yet to confirm that this is the case so the risk can not be closed. | 27/03/20
56367 | 48 | Data | There is a risk of changes to Xoserve DM built solution because of topics being designed at TDWG after the sign off of the DM Solution design document. | Ensure changes to Xoserve are kept at minimum through TDWG discussions. | New process for reconciliation agreed with SI / DCC will require an Xoserve CR for development and testing of solution. Risk profile increased until impact assessment carried out. | 13/03/20
55572 | 48 | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available | Awaiting confirmation of whether ay MPs are have opted for the IX to connect to CSS. | 01/04/20
55549 | 48 | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This continues to be a risk. The discussions at the Business rules workshop on 13/02 highlighted the gaps in the assumptions and understanding that stemmed from the lack of these being agreed and documented at a Programme level. | 14/04/20
55964 | 36 | Testing | There is a risk that the date for the SIT (non Functional) test plan cannot be met because of lack of clarity of the requirements of each of the components and confusion regarding scope SIT(non functional) plus smoke test period leading to duplication of activities and timescales being missed, | Detailed discussions with the SI to clarify the SIT smoke period and the SIT period | SI has provided Draft External SIT Non Functional Test Plan. | 27/03/20

## Slide 5: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55965 | 36 | Testing | There is a risk that the test plan for SIT (non functional) will not be confirmed until 06/03 because of lack of clarity of all requirements in sufficient timescales and inadequate preparation time. | Detailed discussions with SI to clarify scope and requirements. | NFT Test plan still not provided by the SI. | 27/03/20
56424 | 36 | Data | There is a risk that Xoserve will not be able to meet the timeline for delivery of data to Landmark for external SIT prep, because the timeline provided does not take into account the 10 weeks that Xoserve have previously advised is necessary to complete data extract work. | Work through planning for delivery, investigate other options. | Date for delivery of data agreed with SI as 06/03. | 06/03/20
55951 | 36 | Testing | There is a risk that the Pre-prod (NFR) environment and data will not be verified because of lack of requirements for the environment and lack of visibility of the readiness list for the smoke test period. | Detailed discussions with the SI to agree the readiness list and timescales | Currently in discussion with the SI to agree NFRs. SI have requested Xoserve's opinion on NFRs. Testing are currently drafting up Xoserve's opinion, which will be reviewed internally and sent to the SI w/c 09/03. | 27/03/20

## Slide 6: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61429 |  | Data | DMT - Industry parties have not developed against the same version of the design | To be raised with the SI and Ofgem | 03/03: No change to status - no updates from SI | 27/03/2020

## Slide 7
High Level Plan