## Slide 1: Amendment Invoice Update

## Slide 2: Summary
151 unique MPRNs with ASP mismatch.
ASP file merge activities included 149 of the 151 MPRNS that were originally missed.
2 customers had 1 Prime MPRN each with mismatch. These were corrected for both customers.
The issues encountered last month with the AML file extraction and delivery were avoided tis month. A change to the extraction job ensured the file extraction was more efficient and files were delivered earlier (deliver commenced 1 day after invoice issue date).
Cataloguing of Exception resolution process steps now concluded. Approval of the resolution documentation is ongoing.
Defect resolution and deployment has been affected by re-prioritisation and focus on AQ issues and test environment availability issues causing bottle necks through-out the process. RTG forecast to be TBC.

## Slide 3: Summary Resolution Plan
Apr
May
Jun
Jul
Aug
Sept
Mobilise
Oct
Nov onwards
ASP / AML Mismatches
Exclusions
Defects
MI / Reporting
Backlog Clearance
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
RCA activities
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
Backlog Clearance
Operating within SLA
Deploy MI solution
Operating within SLA
Exceptions (LSPs)
Exceptions (SSPs)

## Slide 4: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
GREEN
RAG Justification
151 MPRNs out of the 206,203 LSPs (0.07%) that were billed incurred an ASP mismatch.
151 unique MPRNs with ASP mismatch. File merge activities ensured mismatch data was included in ASP file issue on the invoice issue date (with the exception of 2 Prime MPRNs)
All AML files were delivered ahead of the SLA date.
 |  |  | ASP Mismatches |  | AML Mismatches |  | 
Billing Month | Billed Contracts | LSP Invoiced | Unique LSP MPRNs causing ASP mismatch | % of invoiced LSPs causing ASP mismatches | SSP Invoiced | Unique SSP MPRNs causing AML mismatch | % of invoiced SSP causing AML mismatches
Jan-19 | 9,541,221 | 258,859 | 557 | 0.22% | 9,282,362 | Not reported at the time | 
Feb-19 | 9,015,766 | 173,688 | 509 | 0.29% | 8,842,078 |  | 
Mar-19 | 9,399,210 | 174,114 | 109 | 0.06% |  | 12,946 | 
Apr-19 | 8,896,444 | 184,562 | 264 | 0.14% | 8,711,882 | 5,594 | 0.06%
May-19 | 9,648,261 | 168,267 | 118 | 0.07% | 9,479,994 | 7,493 | 0.08%
Jun-19 | 9,653,613 | 178,064 | 65 | 0.04% | 9,475,549 | 1,882,702 | 19.87%
Jul-19 | 9,895,118 | 180,536 | 92 | 0.05% | 9,714,582 | 250 | 0.00%
Aug-19 | 9,977,884 | 230,802 | 254 | 0.11% | 9,747,082 | 208 | 0.00%
Sep-19 | 11,133,817 | 310,321 | 284 | 0.09% | 10,823,496 | 2,701 | 0.02%
Oct-19 | 11,067,074 | 252,181 | 855 | 0.34% | 10,814,893 | 9,235 | 0.09%
Nov-19 | 10,746,544 | 235,402 | 110 | 0.05% | 10,511,142 | 585 | 0.01%
Dec-19 | 9,907,903 | 227,508 | 133 | 0.06% | 9,680,395 | 2019 | 0.02%
Jan-20 | 11,143,336 | 190,009 | 189 | 0.10% | 10,953,327 | 1521 | 0.01%
Feb-20 | 10,672,939 | 206,203 | 151 | 0.07% | 10,466,736 | 247 | 0.002%

## Slide 5: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
AMBER
RAG Justification
All workable exceptions classified as Backlog and Transition exceptions have now been cleared. A number of exceptions BAU (raised between 1st August and current date) continue to miss the 2 month SLA Cataloguing of Exception resolution steps has now been completed and the documents in the process of being approved.
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
219,491 distinct MPRNs currently have unresolved exceptions within our systems (as of 31st Mar).
(Nov-19 =124,152, Dec-19 = 161,024, Jan-20 208,037)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 6: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
GREEN
RAG Justification
Cataloguing of all scenario resolution steps to ensure accuracy now completed – review and approval ongoing
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
TBC distinct MPRNs for the January 2020 billing period currently have bill blocks placed upon them (as at 4th March 2020). Bill blocks are placed on MPRNs where there are known issues that will result in incorrect charges being calculated.
(Nov-19 = 247, Dec-19 = 2,104, Jan-20 = 2,894)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers

## Slide 7: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
3 Defects did not meet March SLA: 1513 – Defect needs to be bulk tested which cannot be executed in the test environment. Options are being explored on how to progress 1520 is object locked with 3 other defects that need to be deployed before fix can be completed for 1520. 1522 – Previous Issues with the testing approach which is being alleviated by testing in pre-prod the test environment
10 open ASP/AML related defects as of 2nd April 2020
(9 defects open at last month’s update)
Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
Issue with class 3 read upload process - Non-opening read is inserted between two reads through UBR process and next read has a TTZ of 1, volume is calculated incorrectly through UBR process | 13/09/2019 | TBC | 06/12/2019
MR15 exception not created when the variance volume was negative but total volumes was positive and vice versa | 17/12/2019 | TBC | 06/03/2020
Incorrect Volume in SAP due to multiple check read processing on same day in incorrect sequence | 07/01/2020 | TBC | 06/03/2020
ASP Merged File & Prime Meters | 09/01/2020 | 06/03/2020 | 06/03/2020
Incorrect volume sent to CMS from retrieve adjustment details service for class 4 sites | 10/01/2020 | 06/03/2020 | 03/04/2020
Class change from 4 to 1 not updating total check to check volume and energy against MRD | 24/01/2020 | 27/03/2020 | 03/04/2020
Rec is not happening for Prime and sub site when there is RGMA or class change or shipper transfer estimated read | 19/02/2020 | 08/05/2020 | 08/05/2020
Issue in Reconciliation for Prime Sub sites : Total deemed volume and total deemed energy is populated incorrectly in case of Read replacement and read insertion scenario | 19/02/2020 | 08/05/2020 | 08/05/2020
High Value rec report is not displaying data properly and requires some code changes | 20/03/2020 | 27/04/2020 | 05/06/2020
Check to Check rec is not happening for a particular MPRN | 25/03/2020 | 30/04/2020 | 05/06/2020

## Slide 8: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Reports shared with all customers and general and individual WebEx’s are ongoing
MI reports continue to be shared with our customers 2 business days after Amendment invoice issue date.
Ongoing WebEx’s are being held to discuss general questions our customers have with the reports.
Ongoing individual customer WebEx's to discuss what the MI means specifically to them.

## Slide 9: Summary Resolution One Pager
Mismatches | Exceptions | Exclusions | Defects | MI / Reporting
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age. | Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old. | Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection. | Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised. | All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA |  |  |  | 
September 2019 | August 2019 | July 2019 | August 2019 | August 2019
Current SLA RAG Status |  |  |  | 
GREEN | AMBER | GREEN | RED | GREEN
RAG Justification |  |  |  | 
151 MPRNs with ASP mismatch ASP file merge activities ensured the mismatch data for the affected MPRNs were included in the ASP online file (with the exception of 2 Prime MPRNs). All customers received their AML files ahead of the SLA date | All workable exceptions classified as Backlog and Transition exceptions have now been cleared. A number of exceptions BAU (raised between 1st August and current date) continue to miss the 2 month SLA Cataloguing of Exception resolution steps planned to be completed by end of Feb-20. This should improve the exception resolution process. | c.25,000 distinct sites released from bill blocks over the last six months. TBC unique MPRNs excluded from January 2020 invoice cycle. | 3 Defects did not meet March SLA: 1513 – Defect needs to be bulk tested which cannot be executed in the test environment. Options are being explored on how to progress 1520 is object locked with 3 other defects that need to be deployed before fix can be completed for 1520. 1522 – Previous Issues with the testing approach which is being alleviated by testing in pre-prod the test environment | Reports shared with all customers 2 business days after Amendment invoice issue date. Ongoing WebEx’s are being held to discuss general questions our customers have with the reports Ongoing individual customer WebEx's to discuss what the MI means specifically to them