## Slide 1: CSSC Programme Dashboard
27th March 2020

## Slide 2
Executive Summary
Programme continues to be at amber trending status, active mitigation of issues and risks is in place in order to maintain the return to green plan. DES: Changes required to DES to meet the 1hr RTO NFR continue to be progressed in order to meet both internal and external NFR timelines. NFR: Xoserve have discussed and agreed with the SI, that PIT exit criteria for DES Non functional testing of DES will not be completed by the 13/04. DES is expected to be functionally ready, but not tested to the non functional volumes stated. REGID & CCMT: Xoserve require “valid” REGID data for its consequential change testing. Xoserve have discussed this with the SI as to when files with valid REGIDs will be produced and available for future testing. CCMT: Continued engagement with customers, in relation to consequential market trials. ​ Data: Ofgem CR has been received to realign the Data Migration (DM) Solution document. ​All data extracts for MPL extract and Alliance data has been issued to Landmark as per plan. Xoserve are still pending the data from Landmark to confirm when REL data will be provided in readiness for SIT. Xoserve continue to be on track for the 2nd REL extract submission. Service Management: It has been confirmed by the DCC (via SI) that Xoserve are not mandated to integrate with the switching service management system, any parties not integrating will be provided with direct access. Xoserve are reviewing this option, in the meantime engagement continues between Xoserve and Cap Gemini to discuss integration activities. PIT: PIT execution continues​ to plan Environments: The programme have confirmed the need for three additional Xoserve environments. These are being processed. The environments are required for external DM testing, User Entry Process Testing (UEPT) and External NFR testing.
Programme Health - RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Progress (Last Month) |  | 
All Primary APIs delivered for Internal SIT All UK Link System Test complete including Meter Reads Internal SIT testing progressing in earnest SIT environment internal set up completed – pending external connectivity with Landmark All Test Data Extraction completed Gemini SIT execution continues Market Trials engagement continues NFR Testing commenced PIT completion activities including reporting to SI continues |  | 
Priorities (Next Month)
Continue internal SIT execution and NFR Testing. Achieve PIT Exit Continue DES/API deliverables – Secondary APIs and DES for SIT Complete Data Migration ST and Data Provision activities Gemini: Complete SIT execution Gemini: UAT planning with the Test team Continue Market Trials engagement with customers Continue preparatory activities for external testing (SIT & DMT)
Programme Update

## Slide 3: CSSC Programme Workstream Updates
RAG Prev MONTH | RAG Curr MONTH | WORK STREAM | SUMMARY
 |  | Data Migration & Provision | Amber Status: Reflective of Switching Programme CR’s against the baselined Data Migration Solution & reconciliation solution. Impact assessment and re- planning is underway. Pre Integration Testing nearing completion and test preparation in progress for external testing. Data provision ongoing to support performance testing, external SIT preparation and market trials. REL Cycle 2 data extraction is on track for April delivery.
 |  | Internal Testing (PIT) | Amber Status: PPTE3 Test environment has minor functional issues. Schedule is Amber due to later execution of DES related tests. will commence without DES. Performance Testing execution has commenced
 |  | Market Trials | Green Status: Workshop schedule continues to further detail the CCMT Approach. Switching Programme CR to move MT execution to the end of June was raised approval pending
 |  | Service Management | Green Status: Internal assessment continues to ascertain if Xoserve will integrate with Switching Service Management system.
 |  | Reporting | Green Status: No new reporting requirements have been identified following exit of detailed design. No changes to existing reports identified, analysis into three production reports is in progress to understand the underlying data model.
 |  | Networks | Amber Status: Waiting for confirmation of whether any Licenced Parties have selected IX as a network option.
 |  | DES & API | Amber Status: All primary API’s have been delivered for system integration testing. Smoke testing with CSSP is complete. Secondary API’s are in progress. Delays have been seen against the DES re-platform which has caused a delay into functional testing. This has been re-planned with the SI and mitigation actions in place.
 |  | UK Link | Amber Status: Additional ST Scenarios executed. Meter Read review completed. A number of tests were re-executed and defects resolved. Programme CR’s are currently being analysed to understand re-work required.
 |  | Gemini | Green Status: New dates for NGIT SIT have been agreed internally and externally and will take place w/c 27/04, for one week. A defect raised impacted the test schedule. This defect has now been fixed and the schedule has been re-planned, there are no downstream impacts on any other workstreams.
 |  | Business Change | Green Status: We are on track to meet all programme milestones and internal business change requirements.
 |  | Environments & Release Management | Green Status Key environments for programme delivered, new environment requirements are being progressed. Release schedule approach has been created and issued to the SI

## Slide 4: Current Test Status Summary
SIT Test execution Event Summary
Original Start date moved from 6th January to 17th January to 24th February
Entry in to SIT failed as API system test was not completed hence delayed until 27th February
0n the 27th Feb SIT smoke test commenced but failed due to defects found between API – PO interface and API – CSS interface
API defects were fixed and testing re- commenced on the 6th March
DES – Differed - 30th March 2020
All P1 (Blockers are fixed
Test execution team extended to work weekends
62 out 153 Test scenarios completed
Predicted end date due to delays – 10th April 2020
SIT – Status/Forecast
Total defects to date = 87
Total defects resolved =71
SIT Defect Summary
UK LINK – Total 79
  All Blockers are closed
Gemini – Total 1
  closed
API – Total 7
  All Blockers are closed
Chart: SIT Test Execution

## Slide 5: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | No response to Email sent to Joe Lamerton on 19/3 requesting confirmation of whether Xoserve are to proceed with the IX connection to CSS. Follow up Emails to Joe Lamerton around a mechanism to provide IP addresses to Xoserve and whether IX remains in scope. Without this information it is not possible to make any further progress. | 01/04/20
61933 |  | Data | There is a risk that Xoserve may not be able to take a copy of production data on 30/05 for UEPT because Xoserve TechOps are considering imposing a change freeze due to Covid19 lockdowns in UK and India. Leading to Xoserve being unable to take the data copy to align with industry testing. | Discussions with Tech Ops to understand any change freeze. | Potential change freeze is being reviewed daily by major incident management team. | 10/04/20
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This continues to be a risk. The discussions at the Business rules workshop on 13/02 highlighted the gaps in the assumptions and understanding that stemmed from the lack of these being agreed and documented at a Programme level. | 14/04/20
61861 |  | Data | There is a risk that Xoserve will not have test data loaded ready for DMT as the SI have yet to issue requirements, and have only allowed 13 days on the CSSIP for parties to develop, test and execute data filters. Leading to insufficient time and therefore delay in DMT readiness. | Discuss with SI. | Issue raised at TDWG on 17/03. Xoserve have requested that Elliot schedule a meeting asap to discuss | 28/03/20

## Slide 6: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61903 |  | Testing | There is a risk that PPTE2 test environment may not be ready for External SIT because of we do not currently have a plan for Xoserve/CSS connectivity. leading to missing milestone for SIT entry. | Request information regarding the webhook registration process to CSS from SI. | Request information regarding the webhook registration process to CSS from SI. 24/3 - Email requesting information sent to Mark Lane | 27/03/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | Business rules now shared. Xoserve reviewing and will monitor throughout test phases. | 14/04/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | This continues to be a risk. The discussions at the Business rules workshop on 13/02 highlighted the gaps in the assumptions and understanding that stemmed from the lack of these being agreed and documented at a Programme level. | 14/04/20

## Slide 7: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61429 | Major | Data | DMT - Industry parties have not developed against the same version of the design | To be raised with the SI and Ofgem | 20/03: CR has been issued for approval | 08/05/20

## Slide 8
High Level Plan