## Slide 1: Change Management Committee
8th April 2020

## Slide 2: Action 0208 - Xoserve (PO) will create consolidated change proposal concentrating on problem statements for DDP issues.
Approval needed from GT’s & IGT’s
We would like approval for the following Change Proposals to be withdrawn.
XRN4691 CSEPs: IGT and GT File Formats (CGI Files)
XRN4692 CSEPs: IGT and GT File Formats (CIN Files)
XRN4693 CSEPs: IGT and GT File FormatsFiles Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN.
XRN4694 CSEPs: IGT and GT File Formats (Create new data validations)
A new consolidated Change Proposal is currently under review and we expect it to be formally raised soon.

## Slide 3: Action 0209 & 0210 supporting papers. XRN4871B – Modification 0665 – Changes to Ratchet Regime
Scope and Funding
ChMC – April 2020

## Slide 4: Background
XRN4871 was raised to deliver the system requirements set out within UNC Modification 0665, implemented 01 July 2019 .The modification has two purposes:
  It amends the current Class 2 Ratchet Charging Arrangement
  It allows DNs to identify Supply Meter Points (SMP) that should, in addition to mandatory Class 1 SMP, be subject to the existing Class 1 Ratchet Charging Arrangement
Due to the timescales set out within the Modification, the delivery of XRN4871 was agreed by ChMC to be spilt into Part A and Part B.
XRN4871 Part A
  Part A of XRN4871 was delivered within Minor Release Drop 5 (September 2019) and included the minimum scope to comply with modification 0665.
XRN4871 Part B
  This is due to be implemented within November 2020 Major Release and looks to deliver the enduring solution.

## Slide 5: XRN4871 Part B Scope
XRN4871B encompasses three main elements which are detailed below:
Change | Beneficiary | Reason
Automated calculation & issue of Class 2 Ratchet Invoice | Shippers & DNs | Currently the CDSP manually calculate the Ratchet charge for Class 2 sites and raise this via a Request to Bill. This is not included within the Capacity Invoice or within the ZCS or CZI files. This change will ensure the Class 2 Ratchet charges will be generated from the system and included within the Capacity invoice as per the Class 1 Ratchet charges.
Automated forced Class change | Shippers | Currently where Shippers do not reclassify a network designated site, the CDSP do so on their behalf by manually creating and submitting the Class change file. This change will create a Class change tool to automate the Class change process. Please note, there are several changes currently in development which involve CDSP reclassifying sites on Shippers behalf. The solution delivered under XRN4871B will be built to be utilised for these changes also.
Visibility of network designated sites within DES and file formats | Shippers | Currently Shippers have no visibility of where a site (outside of their portfolio) is network designated. This change will make it visible to Shippers where a site is network designated and therefore must be within or remain within Product Class 1.

## Slide 6: XRN4871 Part B Funding
XRN4871B is currently 100% DN funded
Costs for Design is £12,840
  This cost has fully been spent as the change design was completed under June 2020 before being de-scoped.
Cost for Delivery (Build and PIS) is circa £100,000
  None of this cost has occurred yet as delivery will not commence until post May (following the design approval)

## Slide 7: 2. New Change Proposals – Initial Review

## Slide 8: 2. New Change Proposals – Initial Review
Agenda Item | XRN / Title | Voting |  |  |  | Funding | DSC Service Area
 |  | Shipper Y/N | DNO Y/N | IGT Y/N | NTS Y/N |  | 
2.1 | XRN5142 New Allowable Values for DCC Service Flag in DXI File From DCC |  | Y | Y |  | 100% DNO & IGT funded | Service Area 16: Provision of supply point information services and other services required to be provided under condition of the GT Licence
2.2 | XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP |  | Y |  |  | 100% DNO | Service Area 15: Demand Estimation Service Area funding is 50% Shipper and 50% DNO. ChMC in April to agree 100% DNO funded.
2.3 | XRN5145 DSC Service Description Table cosmetic change to Service Line Table v11 | Y | Y | Y | Y | N/A | 
2.4 | XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) |  | Y |  |  | 100% DNO | Service Area 11: NExA Supply Meter Points
2.5 | XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Y | Y | Y | Y | CSSC Change | 
2.6 | XRN5147 Optimising the Must Read process for IGT Customers |  |  |  |  | Potentially other customers may benefit from this change. Funding to be discussed and agreed at ChMC meeting. | Service Area 22: Part E Specific Services

## Slide 9: 2.1 XRN5142 New Allowable Values for DCC Service Flag in DXI File From DCC
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) | Y | 90%
National Grid Transmission |  | 
IGT’s | Y | 10%
Impacted Parties:- DCC |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 16: Provision of supply point information services and other services required to be provided under condition of the GT Licence
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The allowable values for the ‘DCC Service Flag’ data item in the DXI File Format, E46 record, need to be updated to be in line with those proposed by SEC MP077 ‘DCC Service Flagging’. The new DCC Service Flag states should align to what is written in the SEC and allow Users to tell the difference between Devices on a Smart Metering System (SMS) that are Active, installed but not commissioned or decommissioned. The SEC proposal is seeking to remove the allowable values of “S” - Suspended and “W” – Withdrawn and replace them with values of “N” – Non-Active and “I” – InstalledNotCommissioned. SEC MP077 is currently out for Refinement (Workgroup) Consultation, and is not yet an approved modification; however, we do not foresee any reason this will not be approved. The proposal is currently seeking a June 2021 implementation. Please see CP for table
Sponsor Representative | NGN

## Slide 10: 2.2 XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y? | 
Distribution Network Operators (DNOs) | Y | 100%
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- Shippers & DNO |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 15: Demand Estimation
Service Line Impacts (new, amended, existing, deleted), etc. | Service Area funding is 50% Shipper and 50% DNO. ChMC in April to agree 100% DNO funded.
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Xoserve are closer to the NDM demand estimation process than the DNs and have a close relationship with Shippers in this regard, they are therefore better placed to ensure the correct coverage across each EUC Band and Class
Change Description
Transfer the EUC Bands 3-9 NDM Sampling UNC obligations, currently incumbent on Transporters (as per UNC TPD Section H1.6) to the CDSP. Note the CDSP already carries out NDM sampling for EUC Bands 1 and 2 so this change is simply an extension to the current CDSP process.
Sponsor Representative | Cadent

## Slide 11: 2.3 XRN5145 DSC Service Description Table cosmetic change to Service Line Table v11
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | N/A
Distribution Network Operators (DNOs) | Y | N/A
National Grid Transmission | Y | N/A
IGT’s | Y | N/A
Impacted Parties:- |  | 
Voting Parties and Funding Split
DSC Service Area: | See problem statement
Service Line Impacts (new, amended, existing, deleted), etc. | Removing and amending
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The Service Description table needs to be updated as follows:- 1) Removal of Service Line DS-NCS SA3 -02 which relates to the UIG Taskforce. The removal of this line was approved at the CoMC on March 18th 2020 who gave approval to its removal as detailed in the CCR - XRN 4695 2) Cosmetic Changes to lines within Service Area 20 – UK Link System ASGT-CS SA20-01 – new wording as merged with ASGT-CS SA20-02 and ASGT-CS SA20-03 which can now be removed ASGT-CS SA20-05 – minor updates to references ASGT-CS SA20-11 - minor updates to references 3) Cosmetic Changes to lines within Service Area 22 SS SA22 77 and SS SA22 78 – updated references within other corresponding requirements field
Change Description
The amended Service Description table will be issued to each DSC contract manager for consultation. The CDSP will collate any consultation responses and provide these to the DSC Contract Management committee with recommendations for treatment. Unless there are consultation responses that are considered material, the Contract Management committee can approve the proposed Service Description table at the relevant meeting
Sponsor Representative | Xoserve

## Slide 12: 2.4 XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES)
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) | Y | 100%
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 11: NExA Supply Meter Points
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, this should be recorded in UK Link and made visible to Shippers, DNs and IGTs within DES. The data currently held in UK Link and visible within DES needs to be updated to ensure the latest position in terms of NExA sites is reflected and available. The ongoing process must be in place to ensure this information can be updated and reflected correctly within DES.
Change Description
This change seeks to conduct a data cleanse against the information held in UK Link and DES for NExA sites and to ensure the ongoing process is put in place to allow Transporters to confirm where there are any updates and for this to be recorded accurately within UK Link and DES. This will ensure that the indicator within DES remain as per the latest position.
Sponsor Representative | Northern Gas

## Slide 13: 2.5 XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 
Distribution Network Operators (DNOs) | Y | 
National Grid Transmission | Y | 
IGT’s | Y | 
Impacted Parties:- All |  | 
Voting Parties and Funding Split
DSC Service Area: | CSSC Change
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The Ofgem Switching Programme Design Baseline 4 published in June 2018 indicated that following the implementation of the Central Switching Service (CSS), the preferred implementation of SoLR directions would be given effect using a Market Participant Identifier (MPID) transfer e.g. re-assignment of the failing supplier’s short code to the appointed SoLR. This would effectively transfer responsibility for all supply meter points registered against the failing supplier’s short code to the SoLR. Please see the change Proposal for the full statement.
Change Description
The Change Proposal will require changes to the MDD Market Participant Identity Verification Approach Document. This includes changes to the business rules in section 4 to clarify that supplier short codes can be re-assigned as part of a SoLR event and that a single Market Participant Identity could be assigned to different legal entities where the associated supplier and shipper are different.
Sponsor Representative | Xoserve
Xoserve recommend that this change to go out in an Initial Review Change Packs with a 20 working day consultation period, to understand the impacts and risks to the industry.

## Slide 14: 2.6 XRN5147 Optimising the Must Read process for IGT Customers
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) |  | 
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- Potentially other customers may benefit from this change. Funding to be discussed and agreed at ChMC meeting. |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 22: Part E Specific Services
Service Line Impacts (new, amended, existing, deleted), etc. | SS SA22 05 SS SA22 06
Link to Change Proposal | Link to CP
Change Details
Problem Statement
As an IGT I want the most up to date information available to help ensure I am only arranging Must Reads to be precured for sites that are still outstanding meter reads within UK Link systems
Change Description
Changes to the generation logic of current Must Read reports to IGT customers. Also, a monthly reconciliation is required to account for all contacts raised. Assessment is needed to understand whether any changes to the Must Read process are also required – this is to ensure any sites that have subsequently had a successful meter read from the registered Shipper are no longer flagged as being outstanding within the Must Read process for the relevant IGT.
Sponsor Representative | BUUK

## Slide 15: 3. New Change Proposals – Post Initial Review None for this meeting

## Slide 16: 4. New Change Proposals – Post Solution Review None for this meeting

## Slide 17: 5. Implementation Plan
Please see the following slides for an overview of:
Detail Design Changes for approval
Outages
  No new outages.
Attached is the full Implementation Plan document.

## Slide 18
Functional Changes |  |  |  |  |  | 
XRN / Title | Solution & Implementation Summary outcome |  |  |  | Comments | Xoserve response
 | Organisation | Approve | Deferred | Reject |  | 
XRN4850 - Notification of Customer Contact Details to Transporters Revised Change Pack ref: 2552.2 – JLR – JR Original Change Pack ref: 2489.14 – RT - PO June 2020 Release Voting: Shipper, Supplier, DNs and iGTs | npower | X |  |  | No comment | 
 | EDF |  |  |  | Currently the proposed S66 record indicates that the Contact_Tel_Number and Contact_Email_Address data items are mandatory when submitting the BRO Contact Type if the no other contact information is provided (Contact_Email_Address, Customer_Email, Contact_Tel_Number or Customer_Tel). However, when submitting the BRO Contact Type in the S66 within the CNC to remove the details currently held for a site, these data items should be optional. The description within the S66 record should be updated to differentiate when the data items are mandatory and when they are optional. | Thank you for your representation. You are correct that the data items you have highlighted are both optional and mandatory depending on the circumstance they are used within. When BRO Contact Type is used within the CNC to remove the details held for a site, the data items are optional as we would expect the BRO contact to be submitted with all other fields blank. However when BRO Contact Type is used to add or amend details held for a site, the data items would be mandatory if no other contact information is provided. This is to ensure where BRO Contact Type is submitted to add or amend details, the CDSP has at least one contact point (email or telephone) to store in UK Link. We agree it would be beneficial to add this clarification to the description within the S66 record. It is proposed to add the following clarification to the data items within the S66 which currently only describe where they are mandatory: O – Optional where CONTACT_TYPE = BRO is provided to remove contact details held for broadcast or extract within the CNC. Following discussion at ChMC, we propose the updated S66 with this additional description clarification is circulated and added to the UK Link SharePoint site.

## Slide 19
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
4970 | DCC | 11/04/2020 | TBC | 12/04/2020 | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | 13/11/2019
4970 | AD & BoKs | 28/03/2020 | TBC | 29/03/2020 | TBC | This will be cutover of the AD & BoKs application, the which includes the Actives Directory (AD), BoKs and Squid proxy the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintenance window as the application is switched from our Legacy DC to TCS ECP.. | 13/11/2019
4970 | CMS | 11/04/2020 | TBC | 12/04/2020 | TBC | This is the cutover of the production environment for CMS, the outage will be on the weekend, the impact to the industry should be minor and that the Contact Management System will be unable to send or recieve files, raise contacts and will not allow users to log on during the maintainence window as the application is switcheed from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/11/2019
4970 | CMS | 25/04/2020 | 00:00:00 | 26/04/2020 | 07:00:00 | This is the outage for CMS DR testing this will be on the weekend, the impact to the industry will be minor as this will be conducted through the scheduled maintenance window. During this window CMS will be unavailable as such users will be unable to log into the system and files that would normally be processed daily are unaffected as they are planned/scheduled for outside this window. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 11th March
4970 | Birst Connector | 11/04/2020 | TBC | 12/04/2020 | TBC | This is the cutover of the entire Birst connector application, the outage will be on the weekend and the impact will be little to none and will unable to be utilised during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | 13/11/2019
4970 | DCC | 02/05/2020 | TBC | 03/05/2020 | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 11th March
4550 | Control M | 16/05/2020 | TBC | 17/05/2020 | TBC | This is the cutover of the entire Control M application, the outage will be on the weekend and the impact will be minimal, batch jobs that will utilise the application will be delayed during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/11/2019
 | Internet routing for UKLink | 23/05/2020 | TBC | 24/05/2020 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or receive files to corresponding systems during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | 13/11/2019
 | Gemini | 05/07/2020 | 03:00 | 05/07/2020 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 11/12/2019

## Slide 20: 6. Approval of Change documents
6.1 Revised CCR for XRN4665 End User Categories (EUC) Update
  Voting: Shippers
6.2 CCR for XRN5057 Minor Release Drop 6
  Voting: All
6.3 EQR for XRN5122 Gemini System Enhancements – Delivery
  Voting: NTS
6.4 Revised BER for XRN4996 June 20
  Voting: All

## Slide 21: XRN4996 - June 20 Release - Status Update
8th April 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Market Trials was confirmed for xrn4850 at eChMC on 5th March, expected execution window is beginning of June. Delivery: Build and System Testing (ST) has completed for all changes. User Acceptance Testing (UAT) has been completed for 1 change and is in progress for 5 changes. Market Trials: Detailed planning in progress, MT Approach and prep activities to be shared with DSG for discussion. Scope: Scope is unchanged from meeting in February, please refer to slide 7 for confirmed scope of release. Implementation: Implementation date of Saturday 27th June confirmed. |  |  | 
Risks and Issues | Risk – The remaining risk budget will be used up on additional, as yet unidentified, costs being incurred for the integration of the SMS service with Xoserve systems. There is a risk that the progress of June 20 project phases and Market Trials for XRN4850 will be impacted because of the impacts of the spread of COVID-19 leading to a delay to the implementation of the release. |  |  | 
Cost | Costs for the SMS set up and configuration for xrn4850 - Notification of Customer Contact Details to Transporters have been confirmed and were shared with ChMC on 11th March, a revised BER will be shared in April. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 22: XRN4996 - June 20 Release - Implementation Scenarios
The COVID-19 pandemic presents the entire gas industry with an unprecedented working environment
As a responsible CDSP, Xoserve has considered some alternative implementation scenarios for the June 20 major release in order to:
Identify potential related risks for Xoserve / our customers particularly from a resource perspective
Prompt discussion in ChMC as to how implementation of June-20 major release scope could be adapted if required / we are instructed
Discuss how BAU interactions (cycle of ChMC, DSG, comms) might need to be adapted to provide sufficient opportunities for all parties to remain aligned in readiness for this release
We are not looking for you to approve any ‘option’, rather this is a chance to discuss potential scenarios in case optioneering becomes required.

## Slide 23: XRN4996 - June 20 Release - Scenario 1
Do Nothing – Implement as Planned
June 20 timeline remains unchanged and full implementation proceeds as planned for the 27th June
Pro’s | Con’s
Implements June 20 changes as planned on 26-28 June No additional delivery costs No impacts on other projects No rework required | Does not allow all parties (Xoserve, Xoserve’s suppliers, Industry) to mitigate the impacts of COVID-19 on resource availability / focus on BAU activities MT preparation will need to be conducted during the COVID-19 predicted April/May peak Training for the new service for xrn4850 will need to be conducted during the COVID-19 predicted April/May peak New broadcast functionality implemented as part of xrn4850 will be of limited value until customer contact details are held in Xoserve systems Potential Xoserve system impacts if industry submits broadcast data in bulk

## Slide 24: XRN4996 - June 20 Release - Scenario 2
Delay Implementation to November
Due to resource constraints being experienced by all parties, spread the testing activities over a longer duration to ensure quality impacts are mitigated, push November 20 release out into 2012 and reschedule June 20 implementation for November.
Pro’s | Con’s
Enables all parties (Xoserve, Xoserve’s suppliers, Industry) to mitigate the impacts of COVID-19 on resource availability by pushing activities away from the predicted April/May peak therefore protecting BAU activities Provides all parties with additional time to complete the preparation necessary for implementation Implementation will still align to the electricity release Pushes MT later in the year to avoid the predicted peak in COVID-19 cases, providing more time to prepare for MT Allows more time to carry out training minimising the risk that people cannot attend due to illness | Significant increase in costs of delivery (HLE circa £200-£250k) Significant impacts on other inflight projects – environment and code conflicts (Gemini, November 20) Potential rework required, additional testing, due to impact on code changes from other projects (i.e. CSSC) Delays availability of latest June 20 code for CSSC and other projects Pushes implementation of November 20 changes into 2021

## Slide 25: XRN4996 - June 20 Release - Scenario 3
Split Implementation
Implement all 6 changes as planned with the exception of the SMS/Email integration of xrn4850. Implement the SMS/Email Integration at a later date giving industry time to submit broadcast data with customer contact details
Pro’s | Con’s
Enables all parties (Xoserve, Xoserve’s suppliers, Industry) to mitigate the impacts of COVID-19 on resource availability by pushing activities away from the predicted April/May peak therefore protecting BAU activities Provides all parties with additional time to complete the preparation necessary for implementation of xrn4850 Approach would ensure the latest code would still be available for CSSC and other projects Pushes MT later in the year to avoid the predicted peak in COVID-19 cases, provides industry more time to prepare for MT Minimises Xoserve system impacts from the uploading of customer contact details by spreading over 3 month period Allows time for industry to submit broadcast data, in a phased manor, with customer details Allows more time to carry out training (particularly for xrn4850) minimising the risk that people cannot attend due to illness Minimises impact to all parties as broadcast functionality is of limited value until all of the contact details have been uploaded | Increase in costs of delivery (HLE circa £100k) Extended PIS for xrn4850

## Slide 26: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion
- 19/09/19
Design completion
- 13/12/19
Build & Unit Test completion
- 31/01/20
System & UAT completion
- 24/04/20
Regression Test completion
- 29/05/20
Market Trials completion
- 19/06/20 (provisional)
Implementation
- 27/06/20
PIS Completion
- 25/09/20 (provisional)

## Slide 27: June 20 Release Summary
June 20 Release consists of 7 changes, Implementation is planned for June 2020:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs. Descoped at ChMC on 08/01/20
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)

## Slide 28: 7.2 XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Progress update
8th April 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Step 1 Results published to all participating shippers and market level view presented to ChMC. Generation of results for Step 2 and initial sanity checks and data assurance completed Deep Dive analysis of Step 2 results has commenced (delayed slightly due to no remote SAS access). Once end to end execution of one shipper data set has been completed, Step 2 plan will be reviewed to confirm whether execution can be completed by the end of April Plan as of last month was to publish step 2 results and recommendations in May (on basis deep dive can be completed in April), however based on the current ongoing situation with Coronavirus we believe there is a risk that the messages and recommendations coming out of this POC may not be fully consumed, understood and supported. On this basis the timing of the Retro POC output will need to be considered and agreed with the industry. Customer Engagement and Communications: Ongoing communication with POC participating members on progress of Step 2 deep dive External Communication approach for Step 2 to be agreed and finalised |  |  | 
Risks and Issues | There is a risk that the timing of the Retro Step 2 Decks and Recommendations will result in them not being appropriately consumed, understood and supported due to current national circumstances Mitigation: Prior to the issue of all Result Decks and recommendations our customers and involved Xoserve parties will be consulted as to when is appropriate for their release i.e. when they have the resource and time to consume and support |  |  | 
Cost | Approval received from DN’s for BER of £270k for proof of concept. Currently engaging with project sponsors on costs. |  |  | 
Resources | Working with SME team and other business areas to agree resource allocation for Step 2. There is a risk that SME resources required for Step 2 are not wholly available due to commitment to other in flight projects and support of BAU activities. |  |  | 
XRN4914 MOD 0651 - Retrospective Data Update Provision - ChMC Update 8th April

## Slide 29: XRN4914 – Retro proof of concept - timeline
2019 / 2020
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 1
29th Nov
Design (Step 1)
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
today
Planning
Develop (Step 2)
Testing (Step 2)
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Initial Customer engagement of File receipt
Still ongoing
Actual data files can be accepted
Support
Step 2a Categories & 2b MAM
Weekly project update via external communication methods
Test data
files in
Checkpoint 3
TBC
Date for slicing data
8th Dec
Output from Step 1
Output from Step 2a & 2b
Recommendations
XRN4914 MOD 0651 - Retrospective Data Update Provision
8th April
Develop (Step 1)
Testing (Step 1)
Checkpoint 2
7th Feb
Design (Step 2)
Step 2c RGMA & 2d Deep Dive
Output from Step 2c & 2d
Business Rules for Shipper Fixed Anomalies awaiting SME Review and Input, Design Step 2 then complete
Dates need to be confirmed post Step 1
results as volumes will inform task size
November | December | January | February | March | April

## Slide 30: 7.3 XRN5057 – Minor Release Drop 6 - Status Update
April 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: MiRD6 consists of 2 changes and to be delivered on 29/02/20. Delivery: Minor Release Drop 6 Implemented as planned on 29/02/20 and PIS First Usage completed 13/03/20 for one change XRN4955 but as First Usage for XRN4997 will not occur until the end of April - early May it will be monitored as part of Minor Release Drop 7. Scope: The agreed scope of XRN5057 is for 2 changes XRN 4955 - Amendment of MDD PSR Needs Codes and Needs Codes Descriptions and XRN4997 - Introduction of New Charge Codes for Pro-Active Payment of GSOP 3 and GSOP 13 and GT Voluntary Consumer Payments Implementation: The change was implemented on Saturday 29th February. |  |  | 
Risks and Issues | Risk – A risk has been raised that there is no guarantee that First Usage for XRN4995 will occur during MiRD 7. |  |  | 
Cost | Changes are being delivered as part of the Minor Release budget. |  |  | 
Resources | N/A |  |  | 

## Slide 31: XRN5057 – MiRD6 Release Timelines
Key Milestone Dates:
Design Completed – 13/12/19
Build & Functional Unit Test Completion – 03/01/20
System Test & Assurance Completion – 24/01/20
Regression Test & Assurance Completion – 14/02/20
Implementation Complete – 29/02/20
PIS Complete – 13/03/20
CR ID | 11-Nov-19 | 18-Nov-19 | 25-Nov-19 | 02-Dec-19 | 09-Dec-19 | 16-Dec-19 | 23-Dec-19 | 30-Dec-19 | 06-Jan-20 | 13-Jan-20 | 20-Jan-20 | 27-Jan-20 | 03-Feb-20 | 10-Feb-20 | 17-Feb-20 | 24-Feb-20 | 02-Mar-20 | 09-Mar-20
 | Pre-Work |  | Wk 1 | Wk 2 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17
XRN 5057 | IA & Approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Design & Approval |  | Build + FUT |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | ST + Assurance |  |  | Code Merge |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | RT + Assurance |  | Contingency | Imp 29/02 | PIS | 

## Slide 32: 7.4 Minor Release Drop 7 – for approval
April 2020 CHMC

## Slide 33: Approval required for Minor Release Drop 7
Proposed scope XRNs:-
XRN5036 – Updates to Must Read Process (removes AMR and SMART from Must Read contacts - precursor to Nov 2020)
XRN4989 – Online Solution for Credit Interest Process (to automatically issue the supporting info through IX)
XRN5065* – Addition of Email Address to DES Last Accessed Report (security enhancement).
Timeline:-
*Inclusion Subject to IA approval

## Slide 34: Timeline Clarification
Initial plan was to deliver MIR7 in May
We will now be working to a July 4th implementation so we can:
Protect June-20 major release
Assure viability to deliver XRN4989 outside of a major release - April change pack & DSG discussion will confirm impacts to customer systems and processes

## Slide 35: XRN5065 Addition of Email Address to DES Last Accessed Report

## Slide 36: 2.4 XRN5065 – Addition of Email Address to DES Last Accessed Report
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | TBC
Distribution Network Operators (DNOs) | Y | TBC
National Grid Transmission |  | 
Independent Gas Transporter |  | 
Impacted Parties:- Shippers & DNOs The current report is issued to Shippers and DNOs who are DES users, outlining the user accounts on DES and what was the last time they logged in. |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 18: Provision of user reports and information
Service Line Impacts (new, amended, existing, deleted), etc. | Service Area is currently split Shipper 34%, DNO & IGT 59% and NTS 7%. ChMC to agree funding split between Shippers and DNOs *see comments
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The current DES Last Accessed report (SS SA22 50 to 53) contains the list of users with the DES username. This username is constructed of a conjunction of the users first and last names. It makes the use of this report to validate the users more difficult that it needs to be as we are unable to match these (which may be subtly different to the users first name and last name in the company users accounts) directly to our own records. We would like to be able to use the report to more readily match users in DES against current company employee records.
Change Description
Propose the addition of the user email address to the report as an additional field The DES Last Accessed Report is sent out to Shippers & DN’s at various times throughout the month (depending on recipient)
Comments
It is being proposed that XRN5065 is to be placed in scope of MiR7. It should also be noted that since the last ChMC, it has been advised that the DES Last Accessed Report is also sent out to DN’s. This means that the previously agreed funding split of 100% Shipper funded may need to be revisited.

## Slide 37: 7.5 History and Scope of November-2020 (XRN5110)
November 2020 Major Release was firstly earmarked for delivery of Retro, a project that subsequently required a detailed Proof Of Concept exercise
An alternative November-20 major release was scoped, based on priority (regulatory, customer benefits) and readiness (progress through the governance cycle) to make use of the delivery capacity
In Feb-20 ChMC approved a scope of 9 changes under parent XRN5110 including:
- 4780c MAP ID: CSSC
- 4801 Additional Info in DES
- 4871b Ratchet regime changes
- 4897 Contact Details
- 4899 Contact Details
- 4931 Space in SPA Files
- 4941 MOD 692 - Auto Updates to Meter Read Frequency
- 4992 Supplier of last resort charge type
- 5014 Hydeploy trial
Xoserve is currently tracking against the reported plan for this release but there is growing risk that progress (for Xoserve and its customers) could be derailed due to current world events (see next slide)
Release Service Provider will be stood up in May (post-design phase) to begin development with associated costs being incurred from this point

## Slide 38: Changes since February ChMC – Coronavirus
The emergence of Covid-19 has created an unprecedented risk to resource availability for the foreseeable future
This is forcing all market participants into making decisions as to how its resources are utilized and where priority lies while Covid-19 continues to impact each organisation
As a responsible CDSP, Xoserve's approach is to protect ‘Business As Usual’ (BAU) operations first and also (from a change delivery perspective) our CSS programme
As such we are reviewing how to approach 'BAU' (non-CSS) change delivery cycle to protect our customers best interests while continuing to deliver change
We think it appropriate to have a 'check point' with ChMC to ask if delaying delivery of Nov-20 scope to the next available industry release window (Feb-21) is required. We proposed to do this either at at the cyclic 13th May ChMC or an extraordinary ChMC (see next slide)

## Slide 39: Proposed Way Forward
Detailed Design Change Packs will be available on-line from Tuesday 14th April. Ordinarily for a consultation period of 10 days, this would close out on Tuesday 28th April.
If change managers wish to extend this period to provide more time to respond, there would be less than 6 months between design approval and implementation (if a Nov-20 release was preserved). In this instance we would not require an extraordinary ChMC.
In the event of ChMC wishing to preserve the 6-month window, we request that an extraordinary ChMC is convened ahead of May's cyclic ChMC to:
Seek ChMC approval of the change packs associated with the release (to allow for a 6-month period between design approval and implementation we would need to gain approval by 5th May)*
Hold a 'check point' vote to either proceed with current Nov-20 plan or defer changes to Feb-21 to help mitigate the potential future impacts of Covid -19
* If it is decided to move release content to another delivery window, this work won't be wasted

## Slide 40: XRN5110 - Nov 20 Release - Status Update
08/04/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Nine changes in scope for the November 20 release Change 5036 was agreed to be removed from scope at the March ChMC Analysis and Design activities commenced from the 2nd March 2020 All validation of captured Requirements workshops completed Solution workshops in progress |  |  | 
Risks and Issues | Risk identified that due to COVID-19 availability of required resources may be impacted for project delivery |  |  | 
Cost | The cost to deliver the Design phase has been agreed with the preferred Supplier with the EQR previously submitted to ChMC and approved Full delivery costs to be confirmed once contractual arrangements agreed for full delivery of the release. BER containing the full project delivery costs to be presented for approval at May 2020 ChMC |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing. No current concerns |  |  | 

## Slide 41: XRN5110 - Nov 20 Delivery Timeline
Key Milestone Dates:
Analysis & Design activities commenced on 02/03/20 and are planned for completion by 15/05/20
Requirements validation workshops completed for all in scope changes with Solution workshops in flight
Delivery dates captured below to be validated during Build activities

## Slide 42: 7.6 UK Link Releases Update – For Information
April 2020 CHMC

## Slide 43: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Assumes that there will be a Major Release in November 2020
Please note that this includes potential activity within UK Link over the next 24 months
BER Approval
10/04/18
RETRO
Potential Activity
Governance Approval dates tbc…
On track
At risk
Key:
Complete
Feb-20
Jun - 20
Nov 20
4779
MiR 6
BER Approval
May-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
MiR 7
Potential Activity
Scope Approval – April ChMC

## Slide 44: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Feb 20 | 4896 | Rejection code reword – defect 1492 / End User Categories (EUC file format descriptions | In Delivery | Documentation | N/A | N/A
MiR D6 Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In PiS | MiR D6 | Medium | N/A
 | 4997 | Introducing new charge codes for pro-active payment of GSOP 3 and GSOP 13 | In PiS | MiR D6 | Small | N/A
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 5036 | Updates to must read process | In Delivery | Nov 2020 | Small | DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4992 | Supplier of last resort charge type | In Delivery | Nov 2020 | Medium | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4780c | MAP ID part C (CSSC) | In Delivery | Nov 2020 | Large | CSS
 | 4941 | Auto updates to meter read frequency | In Delivery | Nov 2020 | Large | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO

## Slide 45: UK Link – Unallocated Changes
XRN# | Change Title | Current Status | Release Type | UK Link Release | Complexity | Points
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | In capture | Major | - | - | -
4691 | CSEPs – to be consolidated to one XRN | On hold | Major | - | Medium | 8
4692 | CSEPs – to be consolidated to one XRN | On hold | Major | - | Medium | 8
4693 | CSEPs – to be consolidated to one XRN | On hold | Major | - | - | -
4694 | CSEPs – to be consolidated to one XRN | On hold | Major | - | - | -
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | On hold | tbc | - | - | -
4896 | Failure to Supply Gas System and Template Amendment | Requirements in review | Minor | - | Small | 5
4914 | Retro (MOD 651) | On hold for POC | Standalone | - | - | -
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Requirements in review | Minor | - | - | -
4978 | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | In capture | - | - | - | -
4990 | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | Ready for assignment | Major | - | - | -
5000 | CZI +COI supporting information files | Ready for assignment | - | - | - | -
5027 | UK Link data cleanse of conversion factor in line with MOD681s | In capture | - | - | - | -
5038 | Convert class 2, 3, 4 to class 1 (MOD691) | Requirements gathering | - | - | - | -
5070 | Amendment to isolation flag | Requirements gathering | - | - | - | -
5072 | Class 4 with AMR/D4 installed. RGMA flow received with no RTC count | Requirements gathering | - | - | - | -
5091 | Deferral of creation of class change reads at transfer of ownership | Requirements gathering | Minor | - | - | -
5093 | Update of AUG table to reflect new EUC bands | In capture | - | - | - | -
5116 | Domestic report – must read pre-notification | In capture | - | - | - | -
5117 | Correct to failure to supply gas invoicing | In capture | - | - | - | -
5118 | Change to how Actual MR date field is populated | In capture | - | - | - | -

## Slide 46: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)

## Slide 47: 7.7 UK Link POAP

## Slide 48
7.8.1 Customer Impacting Data Changes: XRNs
Change Proposals | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Comments
4738: Shipper portfolio update of proposed Formula Year AQ/SOQ |  |  |  |  | On target for delivery
4860: National ‘Temporary’ UIG Monitoring |  |  |  |  | Data Strategy start date 16th March if Capture complete.
4713: Actual read following estimated transfer read calculating AQ of 1 |  |  |  |  | At risk due to SAP fix - internal cross platform dependencies
5004 – Golden Bullet Report |  |  |  |  | Feedback due 3rd April. Presented at March DN Consortium Meeting.
4874 – Must Read Invoicing Validation |  |  |  |  | Delivery planned for April
Capture
**Estimated Delivery
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.
4929: BG Request for IGT Elected Sites |  |  |  |  | Delivered February

## Slide 49: 7.8.2 DDP update
Verbal update to be presented by David Newman

## Slide 50: 8. CSSC Update

## Slide 51
Executive Summary
Programme continues to be at amber trending status, active mitigation of issues and risks is in place in order to maintain the return to green plan. DES: Changes required to DES to meet the 1hr RTO NFR continue to be progressed in order to meet both internal and external NFR timelines. NFR: Xoserve have discussed and agreed with the SI, that PIT exit criteria for DES Non functional testing of DES will not be completed by the 13/04. DES is expected to be functionally ready, but not tested to the non functional volumes stated. REGID & CCMT: Xoserve require “valid” REGID data for its consequential change testing. Xoserve have discussed this with the SI as to when files with valid REGIDs will be produced and available for future testing. CCMT: Continued engagement with customers, in relation to consequential market trials. ​ Data: Ofgem CR has been received to realign the Data Migration (DM) Solution document. ​All data extracts for MPL extract and Alliance data has been issued to Landmark as per plan. Xoserve are still pending the data from Landmark to confirm when REL data will be provided in readiness for SIT. Xoserve continue to be on track for the 2nd REL extract submission. Service Management: It has been confirmed by the DCC (via SI) that Xoserve are not mandated to integrate with the switching service management system, any parties not integrating will be provided with direct access. Xoserve are reviewing this option, in the meantime engagement continues between Xoserve and Cap Gemini to discuss integration activities. PIT: PIT execution continues​ to plan Environments: The programme have confirmed the need for three additional Xoserve environments. These are being processed. The environments are required for external DM testing, User Entry Process Testing (UEPT) and External NFR testing.
Programme Health - RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Progress (Last Month) |  | 
All Primary APIs delivered for Internal SIT All UK Link System Test complete including Meter Reads Internal SIT testing progressing in earnest SIT environment internal set up completed – pending external connectivity with Landmark All Test Data Extraction completed Gemini SIT execution continues Market Trials engagement continues NFR Testing commenced PIT completion activities including reporting to SI continues |  | 
Priorities (Next Month)
Continue internal SIT execution and NFR Testing. Achieve PIT Exit Continue DES/API deliverables – Secondary APIs and DES for SIT Complete Data Migration ST and Data Provision activities Gemini: Complete SIT execution Gemini: UAT planning with the Test team Continue Market Trials engagement with customers Continue preparatory activities for external testing (SIT & DMT)
Programme Update

## Slide 52: CSSC Programme Workstream Updates
RAG Prev MONTH | RAG Curr MONTH | WORK STREAM | SUMMARY
 |  | Data Migration & Provision | Amber Status: Reflective of Switching Programme CR’s against the baselined Data Migration Solution & reconciliation solution. Impact assessment and re- planning is underway. Pre Integration Testing nearing completion and test preparation in progress for external testing. Data provision ongoing to support performance testing, external SIT preparation and market trials. REL Cycle 2 data extraction is on track for April delivery.
 |  | Internal Testing (PIT) | Amber Status: PPTE3 Test environment has minor functional issues. Schedule is Amber due to later execution of DES related tests. will commence without DES. Performance Testing execution has commenced
 |  | Market Trials | Green Status: Workshop schedule continues to further detail the CCMT Approach. Switching Programme CR to move MT execution to the end of June was raised approval pending
 |  | Service Management | Green Status: Internal assessment continues to ascertain if Xoserve will integrate with Switching Service Management system.
 |  | Reporting | Green Status: No new reporting requirements have been identified following exit of detailed design. No changes to existing reports identified, analysis into three production reports is in progress to understand the underlying data model.
 |  | Networks | Amber Status: Waiting for confirmation of whether any Licenced Parties have selected IX as a network option.
 |  | DES & API | Amber Status: All primary API’s have been delivered for system integration testing. Smoke testing with CSSP is complete. Secondary API’s are in progress. Delays have been seen against the DES re-platform which has caused a delay into functional testing. This has been re-planned with the SI and mitigation actions in place.
 |  | UK Link | Amber Status: Additional ST Scenarios executed. Meter Read review completed. A number of tests were re-executed and defects resolved. Programme CR’s are currently being analysed to understand re-work required.
 |  | Gemini | Green Status: New dates for NGIT SIT have been agreed internally and externally and will take place w/c 27/04, for one week. A defect raised impacted the test schedule. This defect has now been fixed and the schedule has been re-planned, there are no downstream impacts on any other workstreams.
 |  | Business Change | Green Status: We are on track to meet all programme milestones and internal business change requirements.
 |  | Environments & Release Management | Green Status Key environments for programme delivered, new environment requirements are being progressed. Release schedule approach has been created and issued to the SI

## Slide 53: Current Test Status Summary
SIT Test execution Event Summary
Original Start date moved from 6th January to 17th January to 24th February
Entry in to SIT failed as API system test was not completed hence delayed until 27th February
0n the 27th Feb SIT smoke test commenced but failed due to defects found between API – PO interface and API – CSS interface
API defects were fixed and testing re- commenced on the 6th March
DES – Differed - 30th March 2020
All P1 (Blockers are fixed
Test execution team extended to work weekends
62 out 153 Test scenarios completed
Predicted end date due to delays – 10th April 2020
SIT – Status/Forecast
Total defects to date = 87
Total defects resolved =71
SIT Defect Summary
UK LINK – Total 79
  All Blockers are closed
Gemini – Total 1
  closed
API – Total 7
  All Blockers are closed
Chart: SIT Test Execution

## Slide 54: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | No response to Email sent to Joe Lamerton on 19/3 requesting confirmation of whether Xoserve are to proceed with the IX connection to CSS. Follow up Emails to Joe Lamerton around a mechanism to provide IP addresses to Xoserve and whether IX remains in scope. Without this information it is not possible to make any further progress. | 01/04/20
61933 |  | Data | There is a risk that Xoserve may not be able to take a copy of production data on 30/05 for UEPT because Xoserve TechOps are considering imposing a change freeze due to Covid19 lockdowns in UK and India. Leading to Xoserve being unable to take the data copy to align with industry testing. | Discussions with Tech Ops to understand any change freeze. | Potential change freeze is being reviewed daily by major incident management team. | 10/04/20
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This continues to be a risk. The discussions at the Business rules workshop on 13/02 highlighted the gaps in the assumptions and understanding that stemmed from the lack of these being agreed and documented at a Programme level. | 14/04/20
61861 |  | Data | There is a risk that Xoserve will not have test data loaded ready for DMT as the SI have yet to issue requirements, and have only allowed 13 days on the CSSIP for parties to develop, test and execute data filters. Leading to insufficient time and therefore delay in DMT readiness. | Discuss with SI. | Issue raised at TDWG on 17/03. Xoserve have requested that Elliot schedule a meeting asap to discuss | 28/03/20

## Slide 55: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61903 |  | Testing | There is a risk that PPTE2 test environment may not be ready for External SIT because of we do not currently have a plan for Xoserve/CSS connectivity. leading to missing milestone for SIT entry. | Request information regarding the webhook registration process to CSS from SI. | Request information regarding the webhook registration process to CSS from SI. 24/3 - Email requesting information sent to Mark Lane | 27/03/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | Business rules now shared. Xoserve reviewing and will monitor throughout test phases. | 14/04/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | This continues to be a risk. The discussions at the Business rules workshop on 13/02 highlighted the gaps in the assumptions and understanding that stemmed from the lack of these being agreed and documented at a Programme level. | 14/04/20

## Slide 56: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61429 | Major | Data | DMT - Industry parties have not developed against the same version of the design | To be raised with the SI and Ofgem | 20/03: CR has been issued for approval | 08/05/20

## Slide 57
High Level Plan

## Slide 58: 9.1 Bubbling Under Report

## Slide 59: 9.2 Gemini Horizon Planning

## Slide 60: 10 Finance and General Change Budget Update

## Slide 61: 11. AOB

## Slide 62: 11.1 Xoserve IX Refresh

## Slide 63: IX Refresh Customer Update
There has been a significate impact on the project regarding COVID-19. This is due to customer site access restrictions as part of government recommendations
  70% of all remaining customers have requested a hold on their migration due to business continuity arrangements
  Project continuing where possible with remaining customers
Overall project RAG status has moved to Red
  Network Lines, Server and Router installations all require site access which has been limited
  Customer migrations dependent on all physical infrastructure being in place
Project team have engaged with legacy service provider to ensure all customers remain on a fully supported solution
  Agreement in place to extend support past August 2020, if needed
  Minimum 3 month extension
  Extension can be triggered at the end of June 2020
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com