## Slide 1: Xoserve IX Refresh
Customer Update
15/04/2020

## Slide 2: IX Refresh Customer Update
There continues to be a significate impact on the project regarding COVID-19. This is due to customer site access restrictions being in place following government recommendations
  90% of all remaining customers are on hold due to business continuity arrangements or restrictions in place with BT Openreach
  Project continuing where possible with remaining customers
Overall project RAG status has remains at Red
  Network Lines, Server and Router installations all require site access which has been limited
  Customer migrations dependent on all physical infrastructure being in place
Project team have engaged with legacy service provider to ensure all customers remain on a fully supported solution
  Agreement in place to extend support past August 2020, if needed
  Minimum 3 month extension
  Extension can be triggered at the end of June 2020
Once lockdown restrictions begin to ease, following government guidance, the project will re-plan and confirm new project milestone dates.
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com