## Slide 1: CSSC Programme Dashboard
27th April 2020

## Slide 2
Executive Summary
Programme currently tracking Amber, primarily due to the uncertainties around the Switching Programme re-plan, dependencies on CSSP & DES NFR delivery. Key Programme Updates The Programme has successfully exited the "PIT" phase. External "SIT" phase has been delayed by a day to 29th April due to a message signing defect. This was worked through between Xoserve & Landmark and closed on 29/04 Internal Non-Functional Testing continues, with a completion of early June. External Non-Functional Testing continues as per the Work Off Plan to meet the DES 1 hr RTO NFR (agreed with the SI). Internal SIT phases 2&3 continues to track to plan. Preparation continues for UAT and other internal phases continue with replanning in line with the revised Ofgem timelines. Options re being explored with regards to Market Trials. These will be agreed with the Market Trials workgroups and Ofgem Data Migration activities in preparation for external DMT continues to plan and Xoserve is on track to hit programme milestones. General Programme Update Re-plan: Ofgem have advised a 6-month delay to the Switching programme with UEPT moved out up to 6m, due to COVID-19 impacts on suppliers. Xoserve activities are expected to continue to current plan Quality: Internal Gate C++ has been achieved and passed. KPMG continue to assure our programme, on an independent with their draft report issued in support of Stage Gate C++. Findings are being addressed within the programme team. have issued their draft report. Switching Programme Assurance by Expleo has been conducted with a report received with queries. These have since been answered and evidence provided where required Programme Costs: Activity underway to reflect the impacts on CSSC Budget as a result of the re-plan. This activity has a lot of dependencies on clarity from the Switching programme. External Change Request: A number of change requests have been going through programme governance, Xoserve have been assessing them against Functional aspects and high level ROMs have been provided. Costs are being in our budget and will be shared with the Board. These will be shared in conjunction with the budget re-assessment following the re-plan.
Programme Health – RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Return To Green Plan |  | 
Awaiting Switching Programme re-plan (baselined in September 2020) Completion of development for DES NFR to meet the SI "Work Off Plan“ |  | 
KEY Progress (Last Month) |  | 
DMT PIT completed, 1m ahead of plan All data extract changes requested by SI to support Switching Programme completed Team continue working well from home location with no impacts on delivery External audits completed and successfully passed Primary API solution delivered including Smoke testing NFR testing (Phase 1) started Gemini SUPT successfully completed Achieved PIT EXIT and entered external SIT RA020 Readiness Assessment Complete (Business Change Milestone) Internal SIT (Phase 1), focussed on Switching Programme requirements completed, Phase 2 started which will concentrate on Consequential requirements |  | 
Programme Update

## Slide 3: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Provision & Migration | All external & internal data provision to date, have been completed to plan. Internal data migration testing is on track to complete. Preparatory activities are on track to complete ahead of external Data Migration activities. Amber RAG is reflective of the dependency on Landmark to provide REL Data for migration into the external SIT environment. This date has moved a few times; the uncertainty is reflected in the RAG.
 |  | DES & API | Overall RAG Amber. Work continues for DES to meet the 1hr RTO NF and is being actively managed. Agreed "Work Off Plan" in place with SI, in order to meet external NFR testing API: All primary APIs have been delivered and successfully tested. Secondary API delivery is underway and on track to be delivered.
 |  | UK Link | Overall RAG Amber only due to dependency on internal re-planning to align with external programme delay as well as external change requests that are underway. RTG actions: Completion of re-planning and incorporation of Change Requests
 |  | Networks | Overall RAG Amber: Awaiting confirmation from Ofgem on the use of IX by market participants. If IX is descoped, Ofgem will need to raise a CR
 |  | Testing | PIT exit has been successfully met by the programme, caveated by the work-off plan for DES Non-Functional Requirements. Overall RAG Amber due to dependency on completing internal re-planning to align with external programme delay
 |  | Market Trials | Overall RAG Amber. The programme continues engagement with industry, in relation to consequential market trials. Due to the deferral of UEPT, the programme is reviewing the CCMT date and have withdrawn the Switching Programme change (CRD015) submitted to Ofgem, whilst planning reviews and discussions are taking place with market participants and Ofge,
 |  | Service Management | Overall RAG Green. Decision required around the option to integrate Incident Management and Service Request processes once IA has been completed. Placeholders for 4 workshops agreed with DCC to validate the core processes starting 23/04.
 |  | Gemini | Overall RAG Green. Schedule is amber until details of the Programme re-plan are available. NGIT Test Cases for SIT have been received and sent for RQM upload.
 |  | Business Change | Overall RAG Green. The business change assessment pack to support BC020 has been completed and sent to Ofgem and the SI on 09/04​. A re-plan will be conducted once the SI issue a revised CSS IP which incorporates the 6-month extension announced by Ofgem.
 |  | Environments & Release Mgt. | Overall RAG Green: Work continues to assess future requirements and synergise the use of environments in order to reduce spend. Additional environment requirements have also surfaced from the SI.

## Slide 4: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | Description and probability updated to reflect the re-planning if UEPT. No update received on the mechanism to provide IP addresses to Xoserve or whether any MPs have signed up to use IX to connect to CSS. | 30/06/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 29/05/20
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | This continues to be actively monitored and managed - no changes to the status has been identified that could alter the probability or impact. | 30/09/20

## Slide 5: Status at PIT exit and Current test phase(s)
Current Status
PIT Exit
Lost 54 days due to:
  late delivery of code (Mainly API/DES)
  Issues relating to environments
  System test defects appearing in SIT
Successfully met PIT exit milestone for functional test
Completed 153 Test scripts and all defects were fixed and retested
NFR PIT exit is currently ongoing to be completed on the 9th June. Performance test to commence on the 15th May when DES solution is delivered and deployed to the test environment – Project on track
Total no of scripts = 132
Total no of defects to date = 25, 15 fixed and retested
Total no of scripts executed to date = 44
Project on Track
SIT Phase 2
Test Automation
Total no of scripts = 135
Total no of scripts completed to date 80
Project on track
CSSC UAT (Currently in test prep)
Total no of scripts = 200 (Completed)
SME assurance 80% complete (Remaining 20% Scripts have reviewed and the test team are in the process of updating)
On Track
June release UAT
Bottleneck with test execution support. Go live is at risk