## RISK LOG
PAC Risk no. | Risk date | Risk status and RAG | Risk Title | Category | Estimated AQ at risk | Estimated value
PACR001 | 2017-09-25 | LIVE | Theft of gas: The consumption recorded at and by the meter does not record the actual consumption at the premise because of theft of gas at that premise | THEFT OF GAS | 2066044 | 21422
PACR002 | 2017-09-25 | LIVE | AQ correction process: The process to correct AQ's is not used correctly or appropriately thereby applying a bias to the AQ corrections which is not reflective of the AQ corrections needed in any shipper portfolio | DATA CORRECTIONS | 6829517 | 69237
PACR003 | 2017-09-25 | LIVE | Use of estimated reads for Daily Metered sites (Product class 1 and 2) due to an actual daily reading not being loaded into UK Link | DATA CORRECTIONS/ METER READ PERFORMANCE | 2123751 | 22700
PACR004 | 2017-09-25 | LIVE | Identified LDZ Offtake measurement errors: The gas measured into the network has been identified as being incorrect | THEFT OF GAS | 180017 | 12009
PACR005 | 2017-09-25 | LIVE | Incorrect or absent meter asset data: Consumptions are inaccurately derived from the meter billing attributes provided | METER ASSET DATA / DATA CORRECTIONS | 3596924 | 36793
PACR006 | 2017-09-25 | LIVE | Site-specific winter annual ratio (WAR) bands: site specific WAR bands are not available for End User Category (EUC) 03-08 sites | VOLUME CONVERSION | 169480 | 1822
PACR007 | 2017-07-11 | LIVE | Undetected LDZ offtake measurement errors: The gas measured into the network is incorrect and remains undetected | THEFT OF GAS | 90009 | 6005
PACR008 | 2017-07-11 | LIVE | Unregistered Supply points: The supply point is not registered, but is consuming gas | Meter asset data/theft of gas | 372544 | 3922
PACR009 | 2017-07-11 | LIVE | Shipperless Supply points: The supply point exists on the Supply Point Register with no registered Shipper whilst consuming gas | Meter asset data/theft of gas | 52389 | 553
PACR010 | 2017-07-11 | LIVE | Meter readings fail validation (product class 3 and 4): Insufficient reads are loading into UK Link eroding the accuracy of the AQ | METER READ PERFORMANCE | 1565154 | 16615
PACR011 | 2017-07-11 | LIVE | Derived meter read drift: The consumption derived from automatic reads is not reflective of the actual consumption recorded on the meter and this is not identified | METER READ PERFORMANCE | TBC | TBC
PACR012 | 2017-07-11 | LIVE | Required meter read frequency for product 4 meters: the differing required frequency in meter read provision between product class 3 and 4 sites | METER READ PREFORMANCE | 1057761 | 11280
PACR013 | 2017-07-11 | LIVE | Change of Shipper reads: Estimated change of shipper reads are used and rather than actual reads, creating inaccurate reconcilliation to the shippers involved | METER READ PERFORMANCE | 259831 | 2804
PACR014 | 2017-07-11 | LIVE | Meter readings not provided within the settlement window: Sites do not have any reads loaded in the settlement window | METER READ PERFORMANCE | 16628 | 179
PACR015 | 2017-07-11 | LIVE | Retrospective updates: Application of an inconsistent approach by Shippers and the industry to retrospective updates | DATA CORRECTIONS | 353 | 4
PACR016 | 2018-09-11 | LIVE | Correction factors (CF) - incorrect use of standard CF above 732,000 kwh | VOLUME CONVERSION | 854,791 (for risks 16/17 and 18) | 9,212 (for risks 16, 17 & 18)
PACR017 | 2018-09-11 | LIVE | Correction factors (CF) - incorrect use of standard CF for sites consuming on or below 73,200 kwh | VOLUME CONVERSION
PACR018 | 2018-09-11 | LIVE | Correction factors (CF) - incorrect use of non-standard CF below 732,000 kwh | VOLUME CONVERSION
PACR019 | 2018-11-20 | DRAFT | Smart meter exchanges - Late meter exchanges involving smart meters | METER TECHNOLOGY | TBC | TBC
PACR020 | 2018-11-20 | LIVE | Issues with UK link post New UK Link implementation | CENTRAL SYSTEMS | TBC | TBC
PACR021 | 2019-03-18 | LIVE | AMR data provision: there is a risk that poor meter read services and data provision will distort settlement accuracy | METER TECHNOLOGY | TBC | TBC
PACR022 | 2019-03-18 | LIVE | Use of meter bi-pass: Inappropriate use of meter bi-pass and/or inaccurate records kept | THEFT OF GAS | TBC | TBC
PACR023 | 2019-03-18 | ISSUE | Post New UK Link implementation reconciliations: delay in finalising 'pot 2' reconciliations | CENTRAL SYSTEMS / DATA CORRECTIONS | TBC | TBC
PACR024 | 2019-06-09 | ISSUE | understated Aqs on 177,000 PC3 meters | CENTRAL SYSTEMS | TBC | TBC
PACR025 | 2019-08-01 | ISSUE | Impact on performance assurance reporting of change to PC3 settlement process for EUC01 | CENTRAL SYSTEMS / METER READ PERFORMANCE | TBC | TBC
PACR026 | 2020-02-14 | LIVE | Removal and/or non-replacement of correction equiptment | METER ASSET DATA/DATA CORRECTION / VOLUME CONVERSION | TBC | TBC
PACR027 | 2020-03-24 | LIVE | COVID-19 - impact on the operation of the PAC |  | TBC | TBC
PACR028 | 2020-04-21 | LIVE | COVID-19 - related UNC modifications | METER READ PERFORMANCE/VOLUME CONVERSION | TBC | TBC

## METER READ PERFORMANCE
Title: |  | Meter Read Performance
Effective From | 2019-04-01 | Last update | 2020-05-01 | Risk Status (Active/ Monitoring/Closed) | Active |  | as presented to March 2020 PAC
RELATED RISKS |  |  |  | Additional Risks
|  | PACR002: AQ Correction Process (RM 12) |  |  | Withdrawal of DM transporter obligation (647)
|  | PACR003: Use of estimated reads for DM sites PAR 2A.1 (PC1) |  |  | DM consumption adjustments
|  | PACR003: Use of estimated reads for DM sites PAR 2A.1 (PC2) |  |  | Read submission targets outdated
|  | PACR014: Meter readings not provided within the settlement window |  |  | Dec'19 - Development of the DDP has highlighted issues with report accuracy - ongoing
|  | PACR010: Meter readings fail validation (RM 3) |  |  | PACR027 and PACR028 - COVID related risks - Changes to the UNC as a result of urgent modifications will need to be carefully monitored, working with CDSP to achieve this.
PACR011: Derived meter read drift
PACR012: Required meter read frequency for product 4 meters: the differing required frequency in meter read provision between product class 3 and 4 sites
PACR013: Change of Shipper reads: Estimated change of shipper reads are used and rather than actual reads, creating inaccurate reconciliation to the shippers involved
CONTROLS |  | PAC Actions |  | Initial contact | Review | comments/resolution
2A.1 Estimated and Check Reads |  | Performance improvement Initial Letter sent Nov-18 |  | 28/11/2018: Harwich, Southsea Clarence, Mumbles, Morecambe Central | Monthly review at PAC | dec-19 - concerns with the accuracy of the estimated reads reporting.
2A.5 Read Performance PC3 |  | PC3: Performance observation Initial Letter sent Nov-18, PC2 and PC4: performance observation intial letters sent Nov-18, PC2: Performance observation initial letter sent March 2019 |  | 26/11/2018: 21 PC3 shippers contacted, 29/01/2019: 48 PC2 and PC4 shippers contacted, 12/03/2019: Harwich contacted for 12months zero PC2 reads | 12/03/2019: further monitoring agreed
2A.5 Read Performance PC2 |  | Performance observation letter sent to ALL PC2 shippers |  | March 2019 | Focus on targeting shippers for improvement actions | performance improvements seen across PC2
|  | Performance improvement targeting to x5 Shippers |  | June 2019 | PAC review in November 2019 | Plans provided and improvements seen
2A.5 Read Performance PC2 &3 |  | Improvement targetting for single shipper PC2 and PC3 |  | August 2019 | Plan review in September 2019 - include monitoring for a number of months into 2020 | Plans provided and improvements seen
2A.5 Read Performance PC2, 3 and 4 |  | Single Shipper targetted for read performance improvement across 3 classes |  | November 2019 | Report on plan in December, monitor into 2020 until targets are met. | Plans provided and improvements seen
2A.5 Read Performance PC2, and 4 |  | Single shipper targetting for poor read performance across PC2 and 4 |  | January 2020 | Improvements seen - CAMS continue work with the Shipper | Nolonger under review
2A.5 Read performance PC4 |  | Performance observation letters sent to 10 PC4 monthly read Shippers |  | 07/02/20 - observation letters advising Shippers that they were now on the Radar of PAC and should look to improve performance in the coming months before further performance improvement action is taken | Performance to be reviewed in May. **** Due to Corona virus, monitoring will continue but no action will be taken at this time****
2A.6 Meter read Validity monitoring |  | NONE TO DATE
2A.7 No reads for 1,2,3 or 4 years |  | NONE TO DATE |  | Agreed to target overall meter read performance first
2A.4 Shipper Transfer Read Performance |  | data cleanliness observations sent to x3 Shippers |  | 2019-04-01 | PAC review in September 2019 | working with CDSP on report improvements
2A.10: Replaced Meter Reads |  | NONE TO DATE
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****
Additional information:
XRN4079 raised to correct issues in the current suite of PARR reports - implement July-19??
0657 - implemented and PARR report created
0700 reporting - still being developed. Initial reports presented at Ocotber 2019 PAC. As at 30/01/20 - still issues with the data within the reports

## DATA CORRECTIONS
Title: |  | DATA CORRECTIONS
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | Active
RELATED RISKS |  | PACR015: Retrospective updates |  | Additional Risks | PACR003 - DEC-19 issues with the accuracy of estimated meter read reporting
PACR002:Use of the AQ correction process
PACR003: use of estimated daily meter reads
PACR026: Removal and/or non-replacement of correction equipment
CONTROLS |  | PAC Actions |  | Initial contact | Review | comments/resolution
2A.8 Annual Quantity correction by reason code |  | Letter sent to 4 Shippers |  | 2018-12-14 | 01/05/2019 - CLOSED | All shippers responded giving insight to their portfolio and use of the AQ correction process
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****
Additional information:
AUGE report 2019/2020 published: https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/book/2019-03/Final%20AUGS%20for%202019_20%20v1.0.pdf
PACR026: March'20, confirmed that there was no requirement for a corrector to be installed on a site. There is however an obliation to maintain any equipment that is in place

## METER ASSET DATA
Title: |  | Meter Asset Data
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | Active
RELATED RISKS |  | PACR005: Incorrect or absent meter asset data: Consumptions are inaccurately derived from the meter billing attributes provided |  | Additional Risks
|  | PACR008: Unregistered Supply points: The supply point is not registered, but is consuming gas |  |  | Contracts between supplier and MAM
|  | PACR009: Shipperless Supply points: The supply point exists on the Supply Point Register with no registered Shipper whilst consuming gas |  |  | Shipper/Supplier relationship
PACR011: Derived meter read drift: The consumption derived from automatic reads is not reflective of the actual consumption recorded on the meter and this is not identified
PACR021: AMR data provision: there is a risk that poor meter read services and data provision will distort settlement accuracy
PACR026: Removal and/or non-replacement of Gas Correctors
CONTROLS |  | PAC Actions |  | Initial contact | Review | Comments/resolution
2A.2: No meter recorded in the supply point register |  |  |  | none to date
2A.3: No meter recorded in the supply point register and data flows received |  | Data cleanliness observation to x4 shippers |  | 2018-12-01 | 2019-05-01
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****
Additional information:
PACR026: March'20, confirmed that there was no requirement for a corrector to be installed on a site. There is however an obliation to maintain any equipment that is in place

## THEFT OF GAS
Title: |  | THEFT OF GAS
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) |  | MONITORING
RELATED RISKS |  | PACR001: Theft of gas: The consumption recorded at and by the meter does not record the actual consumption at the premise because of theft of gas at that premise |  | Additional Risks |  | AQ corrections following fault reporting
|  | PACR004: Identified LDZ Offtake measurement errors: The gas measured into the network has been identified as being incorrect |  |  |  | Shipper systems being updated
|  | PACR007: Undetected LDZ offtake measurement errors: The gas measured into the network is incorrect and remains undetected |  |  |  | Shipper/supplier relationship
|  | PACR008: Unregistered Supply points: The supply point is not registered, but is consuming gas |  |  |  | meter bi-pass and faulty meter flag and ability to report on its use (report in Sept-19 PAC minutes)
PACR009: Shipperless Supply points: The supply point exists on the Supply Point Register with no registered Shipper whilst consuming gas
PACR022: Use of meter bi-pass: Inappropriate use of meter bi-pass and/or inaccurate records kept
CONTROLS |  | PAC Actions |  | Initial contact |  | Review | Comments/resolution
UIG Taskforce |  | PAFA monitoring taskforce outcomes in relation to theft
AUG |  | PAFA monitoring AUG work in relation to theft
TRAS |  | PAFA monitoring TRAS work through the SPAA
10/09/2019 -PAC meeting |  | Actions around meter bi-pass discussed. Xoserve to continue to provide updates to the PAC |  | Xoserve and CAMS |  | monthly at PAC
01/11/2019 - UNC667R (review complete) |  | UNC0677R contains 16 recommendations
Additional information:
Monthly theft reports are available on the JO website (both Shipper and Transporter)
UNC0677R: Shipper and Supplier theft of Gas Reporting Arrangements - completed 01/11/2019
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****
0667R - recommendations. Owner and progress
number | description |  |  | owner | update
1 | Transporters have proposed to make amendments to TPD v in light of the removal of the SPAA schedule 33 reporting requirements and to better align UNC reporting with regulatory reporting packs |  |  | SGN
2 | IGTs have proposed that amendments are made to the IGTUNC to require that IGTs submit theft data to Ofgem on request, inlight of the removal of the schedule 33 reporting requirements |  |  | Alex Travell to consider | 23/01/2019 - IGTUNC change is in flight
3 | Obligations should be placed on Shippers in the UNC to ensure confirmed Theft information reported by Suppliers, is entered into Settlement systems for Settlement purposes, and that AQ corrections are carried out as may be required.
4 | The Joint Workgroup recommends that only confirmed theft investigation outcomes are entered into settlement systems
5 | UNC/DSC parties shall cooperate with Suppliers in reviewing how AQ corrections are carried out and make a recommendation for improvement as may be necessary, including consideration of whether performance assurance is required in relation to the update of AQs following confirmed theft |  |  |  | PAC to consider required reporting
6 | Any new obligations on Shippers to ensure confirmed theft information reported by Suppliers is entered into Settlement systems for Settlement purposes should be achieved through changes to Settlement systems to enable the automated input of TRAS data into settlement systems, where theft is confirmed by the Supplier in TRAS
7 | Shippers should be provided with the opportunity to review any confirmed theft data that is output from TRAS prior to final Settlement and Shippers should work with Suppliers to develop prescribed grounds and timescales upon which objections and/or queries may be raised and resolved
8 | Changes should be made to Settlement systems to reduce the mandatory data items required to confirm theft in Settlement systems to the minimum required to assist the automatic inout of confirmed theft information from TRAS to Settelment systems
9 | To enable the automated input of thft volume information from TRAS into settlement systems, the JTRR recommends that a standard conversion if applied and the point at which the conversion from KWh to M3 is carried out is fixed - this could be achieved through instructing the TRAS service provider to undertake the conversion prior to transmitting the TRAS confirmed theft output file, or through a conversion by Xoserve following receipt of the confirmed theft output file from TRAS
10 | UNC/DSC Parties should work with SPAA Parties to determine what process is undertaken to carry out the conversion of KWH to M3 to facilitate the input of TRAS confirmed theft data into Settlement systems, with industry parties being consulted prior to implementation
11 | Obligations should be placed on Shippers in the UNC to require that suspected or alleged theft information is provided to the relevant supplier, and shippliers and shippers should work together to determine the process and timescales by which this is undertaken
12 | Changes should be made to settlement systems to improve the way in which suspected theft records are treated, where these are raised by either the Shipper or Transporter, with the records no longer remaining 'open' until an outcome is provided or 'auto-closing' where no outcome is provided but instead closing once the Shipper confirms the information has been passed to the Supplier by providing the Supplier Investigation ID once it is returned by the Supplier |  |  |  | PAC to consider required reporting
13 | Consideration should be given by UNC Parties as to whether there is a need to provide assurance of Shipper performance with respect to any obligations to provide suspected theft information to suppliers, potentially via the UNC PAC and/or via a periodic comparison of TRAS and Settlement systems data, with the support of the TRAS service provider and SPAA parties |  |  |  | PAC to consider required reporting
14 | UNC/DSC Parties should cooperate with SPAA Parties in reviewing whether and how historic confirmed theft information in TRAS that does not appear in Settlement systems should be retrospectively added to Settlement systems and, should UNC/DSC Parties elect to do this, SPAA Parties should assist in the resolution of any queries that may arise from Shippers |  |  |  | PAC to consider required reporting
15 | UNC/DSC Parties should consider whether historic confirmed theft information in TRAS that does not appear in Settlement systems should be retrospectively added to Settlement systems and, should UNC/DSC Parties elect to do this, SPAA Parties should assist in the resolution of any queries that may arise from Shippers
16 | UNC/DSC Parties should review the UNC Reasonable Endeavours scheme in conjunction with SPAA Parties and consider whether this is operating appropriately and whether changes are requried to enable Suppliers to better access the scheme |  |  |  | Xoserve to follow up

## VOLUME CONVERSION
Title: |  | Volume Conversion
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
RELATED RISKS |  | PACR006: Site-specific winter annual ratio (WAR) bands: site specific WAR bands are not available for End User Category (EUC) 03-08 sites |  | Additional Risks
PACR016: Correction factors (CF) - incorrect use of standard CF above 732,000 kwh
PACR017 :Correction factors (CF) - use of standard CF for sites consuming on or below 73,200 kwh
PACR018 :Correction factors (CF) - incorrect use of standard CF below 732,000 kwh
PACR002: AQ correction process: The process to correct AQ's is not used correctly or appropriately thereby applying a bias to the AQ corrections which is not reflective of the AQ corrections needed in any shipper portfolio
PACR026: Removal and/or non-replacement of correction equiptment
CONTROLS |  | PAC Actions |  | Initial contact | Review | Comments/resolution
2A.9: Standard correction factor for sites with AQ >732MWH |  | Data cleanliness observation to x3 shippers |  | 2018-11-01 | 2019-04-01
|  | following improvements from initial communications data cleanliness observation to further x4 shippers |  | 2019-03-01 | 2019-07-01
|  | Single Performance improvement letter sent to performance being significantly out of line with industry |  | 2019-07-01 | 2019-11-01
2A.8: AQ correction by reason code |  | Performance letters sent to x1 shipper following high numbers of AQ corrections |  | 2018-12-01 | 2019-04-01
Additional information:
PACR026: March'20, confirmed that there was no requirement for a corrector to be installed on a site. There is however an obliation to maintain any equipment that is in place
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****

## CENTRAL SYSTEMS
Title: |  | CENTRAL SYSTEMS
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
RELATED RISKS |  | PACR023: Post New UK Link implementation reconciliations: delay in finalising 'pot 2' reconciliations |  | Additional Risks
PACR020: Issues with UK link post New UK Link implementation
PACR025: Impact on performance assurance reporting of change to PC3 settlement process for EUC01
PACR024: understated Aqs on 177,000 PC3 meters
CONTROLS |  | PAC Actions |  | Initial contact | Review | Comments/resolution
Additional information:
Dec'19 - PAFA are working closely with CDSP on development of the DDP. Some issues have been identified with the DDP and alignment with the current PARR.
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****

## METER TECHNOLOGY
Title: |  | METER TECHNOLOGY
Effective From | 2019-04-01 | Last update | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
RELATED RISKS |  | PACR021: AMR data provision: there is a risk that poor meter read services and data provision will distort settlement accuracy |  | Additional Risks | May 2020 - PAC are currently looking in to the requirement for a corrector to be installed at a site
PACR019: Smart meter exchanges - Late meter exchanges involving smart meters
CONTROLS |  | PAC Actions |  | Initial contact | Review | Comments/resolution
Additional information:
XRN4079 raised to correct issues in the current suite of PARR reports - implement Nov-19
***** 30 March 2020 - PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP****

## PACR001
Risk Number | PACR001 | Risk Title: | Theft of Gas: The consumption recorded at and by the meter does not record the actual consumption at the premise because of theft of gas at that premise
|  | Risk Description: | The consumption recorded at and by the meter does not record the actual consumption at the premise because of theft of gas at that premise
|  | There is a risk that… | Some energy being consumed at a premise is not being recorded due to theft leading to a higher level of unidentified gas in settlements
Effective From | 2017-09-25 | Category | THEFT OF GAS | RAG STATUS | Estimated AQ at risk (kwh) | 2066044 | Estimated value of risk (GBP)000's | 21422
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
No specific PARR reporting for theft at the moment
Industry activity
Workgroup/meeting/code change |  | comments
TRAS (under SPAA)
AUGE
UIG task force
UNC677R |  | raised by First Utility to review discrepancies in Shipper and Supplier reporting arrangements
PAC activity / mitigating actions
date | action | comment
2019-08-19 | PROPOSAL | monitoring of shipper detection and investigation, Xoserve presentation suggests work needed on shipper communication around process and timelines https://www.xoserve.com/media/7026/customer-expert-day-cms-tog-must-reads-24-07-19.pdf
2019-08-29 | PROPOSAL | consideration of the post nexus regime and implications for theft detection (loss of RbD smear)

## PACR002
Risk Number | PACR002 | Risk Title: | Use of the AQ Correction Process
|  | Risk Description: | The process to correct AQ's is not used correctly or appropriately thereby applying a bias to the AQ corrections which his not reflective of the AQ corrections needed in any shipper's portfolio
|  | There is a risk that… | Shippers do not apply AQ corrections in a fair and consistent way thereby introducing a bias, ultimately leading to inaccurate levels of unidentified gas in settlements
Effective From | 2017-09-25 | Category | DATA CORRECTIONS | RAG STATUS | Estimated AQ at risk (kwh) | 6829517 | Estimated value of risk (GBP)000's | 69237
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
PARR 2A.8 AQ correction by reason code
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment
ongoing | Monitoring | AQ corrections reviewed on a monthly basis by the PAC
2018-12-12 | Action | Performance improvement letters sent to four shippers in relation to PARR2A.8: AQ correction by reason code
ongoing | Monitoring | Work with CAMS on Shipper education around use of AQ corrections

## PACR003
Risk Number | PACR003 | Risk Title: | Use of Estimated daily meter reads
|  | Risk Description: | Use of estimated daily meter for daily metered sites in Product class 1 and 2 due to an actual daily reading not being loaded onto the UK Link
|  | There is a risk that… | The algorithm used to determine the estimated consumption for a DM site does not reflect the actual consumption at that site leading to inaccurate allocation and settlement
Effective From | 2017-09-25 | Category | DATA CORRECTIONS/ METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | 2123751 | Estimated value of risk (GBP)000's | 22700
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
PARR 2A.1 Estimated and check reads
Industry activity
Workgroup/meeting |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2018-11-28 | ACTION | Performance improvement Initial Letter sent Nov-18 - PAC further review 09/04/2019
2019-05-01 |  | PC1 - industry average achieving UNC requirement from MAY 2019
2019-07-01 | ACTION | Improvement to PC2 estimated read performance now PAC focus

## PACR004
Risk Number | PACR004 | Risk Title: | Identified LDZ offtake measurement errors
|  | Risk Description: | The gas measured into the network has been identified as being incorrect
|  | There is a risk that… | The gas being measured into the network is incorrect impacting allocation and shrinkage calculations
Effective From | 2017-09-25 | Category | THEFT OF GAS | RAG STATUS | Estimated AQ at risk (kwh) | 180017 | Estimated value of risk (GBP)000's | 12009
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Measurement error report available on the Joint Office website: https://www.gasgovernance.co.uk/MER
Industry activity
Workgroup/meeting |  | comments
Measurement errors report |  | LOW significance (1.77mcm) error report by WWU in May 2019
PAC activity / mitigating actions
DATE | ACTIVITY | comment
Monthly | Monitoring | LDZ measurement errors are available at monthly PAC meetings

## PACR005
Risk Number | PACR005 | Risk Title: | Incorrect or absent meter asset data
|  | Risk Description: | Consumptions are inaccurately derived from the meter billing attributes provided
|  | There is a risk that… | The billing attributes of a meter are incorrectly recorded or missing leading to incorrect or no consumption being derived from meter readings, impacting reconciliations and therefore settlement accuracy
Effective From | 2017-09-25 | Category | METER ASSET DATA / DATA CORRECTIONS | RAG STATUS | Estimated AQ at risk (kwh) | 3596924 | Estimated value of risk (GBP)000's | 36793
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
2A.3
2A.9
Industry activity
Workgroup/meeting/code change |  | comments
code change |  | 654s : Mandating the provision of NDM sample data - implemented
code change |  | 651: Changes to the retrospective data update provisions - implemented
PAC activity / mitigating actions
DATE | ACTIVITY | comment
ongoing | monitoring | 2A.2 No meter recorded, 2A.3 No meter recorded and data flows received - monitored on a monthly basis by PAFA and PAC

## PACR006
Risk Number | PACR006 | Risk Title: | Site specific winter annual ratio
|  | Risk Description: | Site specific WAR bands are not available for End User Category (EUC) 03-08 sites
|  | There is a risk that… | For daily settlement sites, a site specific WAR band is not available from which more accurate profiles can be derived, leading to more accurate allocation and settlement
Effective From | 2017-09-25 | Category | VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | 169480 | Estimated value of risk (GBP)000's | 1822
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
code change |  | 0652: Introductions of winter read/consumption reports and associated obligations
PAC activity / mitigating actions
DATE | ACTIVITY | comment
0652 should introduce additional reports to the PARR - implementation August 2019

## PACR007
Risk Number | PACR007 | Risk Title: | Undetected LDZ offtake measurement errors
|  | Risk Description: | The gas measured into the network is incorrect and remains undetected
|  | There is a risk that… | The gas being measured into the network is incorrect due to a measurement error impacting settlement, the levels of unidentified gas and shrinkage, which whilst the error is undetected
Effective From | 2017-09-25 | Category | THEFT OF GAS | RAG STATUS | Estimated AQ at risk (kwh) | 90009 | Estimated value of risk (GBP)000's | 6005
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
Measurement error report available on the Joint Office website: https://www.gasgovernance.co.uk/MER
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR008
Risk Number | PACR008 | Risk Title: | Unregistered supply points
|  | Risk Description: | The supply point is not registered, but is consuming gas
|  | There is a risk that… | No Shipper is putting gas into the network or paying for gas off-taken thereby directly impacting unidentified gas
Effective From | 2017-09-25 | Category | Meter asset data/theft of gas | RAG STATUS | Estimated AQ at risk (kwh) | 372544 | Estimated value of risk (GBP)000's | 3922
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | MONITORING
Related reporting
2A.2 No meter recorded
2A.3 No meter recorded but data flows received
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR009
Risk Number | PACR009 | Risk Title: | Shipperless supply points
|  | Risk Description: | The supply point exists on the supply point register with no registered Shipper whilst consuming gas
|  | There is a risk that… | No Shipper is putting gas into the network or paying for gas off-taken thereby directly impacting unidentified gas
Effective From | 2017-09-25 | Category | Meter asset data/theft of gas | RAG STATUS | Estimated AQ at risk (kwh) | 52389 | Estimated value of risk (GBP)000's | 553
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
2A.2 No meter recorded
2A.3 No meter recorded and data flows received
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR010
Risk Number | PACR010 | Risk Title: | Meter readings fail validation (PC3 and 4)
|  | Risk Description: | Insufficient meter reads are loaded into UKLink eroding the accuracy of the AQ
|  | There is a risk that… | Actual reads are either sent and fail validation or are not sent so that insufficient reads are provided to maintain the AQ accuracy leading to inaccurate allocation and settlement
Effective From | 2017-09-25 | Category | METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | 1565154 | Estimated value of risk (GBP)000's | 16615
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
24.6 Meter read validity monitoring
Industry activity
Workgroup/meeting/code change |  | comments
current risk model only considers PC4
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR011
Risk Number | PACR011 | Risk Title: | Derived meter read drift
|  | Risk Description: | The consumption derived from automatic reads is not reflective of the actual consumption recorded on the meter and this is not identified.
|  | There is a risk that… | Consumption drift is not identified because are not obtained to identify the issues, leading to incorrect consumptions being used in settlement
Effective From | 2017-09-25 | Category | METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP)000's | TBC
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
2A.1: Estimated and check reads
Industry activity
Workgroup/meeting/code change |  | comments
Current risk model does not consider meter drift
PAC activity / mitigating actions
DATE | ACTIVITY | comment
ongoing | monitoring | No action taken on check reads report to date - query reporting

## PACR012
Risk Number | PACR0012 | Risk Title: | Required meter read frequency for product class 4 meters
|  | Risk Description: | The differing required frequency in meter read provision between product class 3 and 4 sites
|  | There is a risk that… | The frequency of submission of meter readings for Product class 4 meter points could adversely impact the accuracy of the derived AQ consumption along with the frequency of reconciliation
Effective From | 2017-09-25 | Category | METER READ PREFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | 1057761 | Estimated value of risk (GBP)000's | 11280
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
2A.5 Meter reads.
Industry activity
Workgroup/meeting/code change |  | comments
Code change |  | 0700: Enabling large scale utilisation of class 3
PAC activity / mitigating actions
DATE | ACTIVITY | comment
ongoing | monitoring | 2.A5 meter reads
2019-10-01 | monitoring | Implementation of 0700 could lead to a reduction of value of this risk as large number of sites moving into PC3.

## PACR013
Risk Number | PACR0013 | Risk Title: | Change of Shipper Reads
|  | Risk Description: | Estimated change of shipper reads are used and rather than actual reads, creating inaccurate reconciliation to the shippers involved
|  | There is a risk that… | The opening and closing periods of reconciliation are not accurately reflected for the two shippers when an actual read is not used impacting reconciliation accuracy
Effective From | 2017-09-25 | Category | METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | 259831 | Estimated value of risk (GBP)000's | 2804
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
2A.10 Replaced meter reads
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2019-08-29 | monitoring | discussions with SPAA around transfer read/Shipper agreed read process - issues logged and being considered

## PACR014
Risk Number | PACR0014 | Risk Title: | Meter readings not provided within the settlement window
|  | Risk Description: | Sites do not have any reads loaded in the settlement window
|  | There is a risk that… | Reconciliations will be crystallised based on estimated readings due to the failure to provide a meter reading within the settlement window, impacting settlement accuracy unidentified gas
Effective From | 2017-09-25 | Category | METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | 16628 | Estimated value of risk (GBP)000's | 179
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
2A.1 Estimated and check reads
2A.7 No meter reads received for 1, 2, 3 or 4 years
2A.5 Meter reads
Industry activity
Workgroup/meeting/code change |  | comments
Risk model only considers those sites which have not obtained a read for a period longer than 42 months.
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR015
Risk Number | PACR0015 | Risk Title: | Retrospective updates
|  | Risk Description: | Application of an inconsistent approach by Shippers and the industry to retrospective updates
|  | There is a risk that… | The application of an inconsistent approach to retrospective updates introduces a bias and therefore impacts settlement accuracy
Effective From | 2017-09-25 | Category | DATA CORRECTIONS | RAG STATUS | Estimated AQ at risk (kwh) | 353 | Estimated value of risk (GBP) | 4
Last Review | 2019-08-01 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
code change |  | 0651: Changes to the retrospective update provisions
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR016
Risk Number | PACR0016 | Risk Title: | Correction Factors (CF) - incorrect use of standard CF above 732,000kwh
|  | Risk Description: | Correction factors (CF) - incorrect use of standard CF above 732,000 kwh
|  | There is a risk that… | The standard correction factor is used when a site-specific correction factor should be applied, leading to incorrect consumptions and ultimately inaccurate settlement
Effective From | 2018-09-11 | Category | VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | 854,791 (for risks 16/17 and 18) | Estimated value of risk (GBP) | 9,212 (for risks 16, 17 & 18)
Last Review | 2019-08-11 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
Current risk model only considers incorrect correction factors as a whole and does not break down further
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2018-11-01 | monitoring | 2A.9 Standard correction factor: Data cleanliness observation to x3 shippers November 2018
2019-03-01 | monitoring | following improvements from initial communications data cleanliness observation to further x4 shippers in March 2019
2019-07-01 | monitoring | Single Performance improvement letter sent to performance being significantly out of line with industry in July 2019

## PACR017
Risk Number | PACR0017 | Risk Title: | Correction factors (CF) - incorrect use of standard CF for sites consuming on or below 73,200 kwh
Risk Description:
|  | There is a risk that… | The standard correction factor is incorrectly used when a site-specific correction factor should be applied, leading to incorrect consumptions and ultimately inaccurate settlement
Effective From | 2018-09-11 | Category | VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | 854,791 (for risks 16/17 and 18) | Estimated value of risk (GBP) | 9,212 (for risks 16, 17 & 18)
Last Review | 2019-08-11 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
Current risk model only considers incorrect correction factors as a whole and does not break down further
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR018
Risk Number | PACR0018 | Risk Title: | Correction factors (CF) - incorrect use of non-standard CF below 732,000 kwh
Risk Description:
|  | There is a risk that… | The site-specific correction factor is incorrectly used when a standard correction factor should be applied, leading to incorrect consumptions and ultimately inaccurate settlement
Effective From | 2018-09-11 | Category | VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | 854,791 (for risks 16/17 and 18) | Estimated value of risk (GBP) | 9,212 (for risks 16, 17 & 18)
Last Review | 2019-08-11 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
Current risk model only considers incorrect correction factors as a whole and does not break down further
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR019
Risk Number | PACR0019 | Risk Title: | Smart meter exchanges - Late meter exchanges involving smart meters
Risk Description:
There is a risk that…
Effective From | 2018-11-20 | Category | METER TECHNOLOGY | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review | 2019-08-12 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR020
Risk Number | PACR0020 | Risk Title: | Issues with UK link post New UK Link implementation
Risk Description:
There is a risk that…
Effective From | 2018-11-20 | Category | CENTRAL SYSTEMS | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review | 2019-08-12 | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
Xoserve communications |  | https://www.xoserve.com/communications/?topic=UK Link;&search=
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR021
Risk Number | PACR0021 | Risk Title: | AMR data provision
|  | Risk Description: | Problems with AMR data provision could be and is distorting settlement accuracy
|  | There is a risk that… | Poor read submission in class 2 and 3, in addition to low rates of check read submission, suggests that there could be underlying inaccuracy of equipment, software and processes related to AMR. Incorrect settlement energy being potentially recorded at D+5 and corrected for some time, if at all.
Effective From | 2019-03-18 | Category | METER TECHNOLOGY | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR022
Risk Number | PACR022 | Risk Title: | Use of meter bi-pass
|  | Risk Description: | Inappropriate use of meter bi-pass and/or inaccurate records kept
|  | There is a risk that… | gas consumption is not accurately measured at sites where meter bi-pass is possible
Effective From | 2019-03-18 | Category | THEFT OF GAS | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
25/10/19 - PARR workshop |  | PAC met to design PARR report to capture use of meter bi-pass
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR023
Risk Number | PACR0023 | Risk Title: | Post New UK Link implementation reconciliations: delay in finalising 'pot 2' reconciliations
|  | Risk Description: | Following the roll out of project nexus, a number of sites a number of sites have remained unreconciled following a period of no actual meter read provision.
There is a risk that…
Effective From | 2019-03-18 | Category | CENTRAL SYSTEMS / DATA CORRECTIONS | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Updates given to PAC: most recent update here: https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-05/Outstanding%20Action%200103%20Update%20UIG%20Class%201%20-%20Consumption%20Adjustment%20Resolution.pdf
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment

## PACR024
Risk Number | PACR0024 | Risk Title: | understated Aqs on 177,000 PC3 meters
|  | Risk Description: | Following 2019 AQ review 177,000 PC3 meters have received an understated AQ
There is a risk that…
Effective From | 2019-06-09 | Category | CENTRAL SYSTEMS | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
AQ issues report published on Xoserve ewb: https://www.xoserve.com/communications/xce1726-annual-quantity-issues-update-friday-22nd-february-2019/
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2019-09-10 | Monitoring | Xoserve are to present on the impact of the AQ calculations at 08/10/19 meeting

## PACR025
Risk Number | PACR0025 | Risk Title: | Impact on performance assurance reporting of change to PC3 settlement process for EUC01
|  | Risk Description: | UNC700 to be implemented 28 September 2019 and will create a new process for EUC01 sites that wish to move into PC3
|  | There is a risk that… | ..a change in the meter read validation and submission process for EUC01 sites that are moving into PC3 will lead to a distortion in settlement
Effective From | 2019-08-01 | Category | CENTRAL SYSTEMS / METER READ PERFORMANCE | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | monitoring
Related reporting
Industry activity
Workgroup/meeting/code change |  | comments
code change |  | UNC700: Enabling large scale utilisation of Class 3, will be implemented with effect from 28 September 2019
code change |  | XRN4991: systems change proposal to facilitate UNC0700
PAC activity / mitigating actions
DATE | ACTIVITY | comment
04/092019 | meeting | PAFA meet with CDSP to discuss impact of XRN4991 on the existing PARR reports
2019-09-09 | Consultation response | PAFA respond to consultation on XRN4991 suggesting that they continue to work with the CDSP to limit the impact of the changes on the PARR reports

## PACR026
Risk Number | PACR0026 | Risk Title: | Removal and/or non-replacement of correction equiptment
|  | Risk Description: | There is a risk that Suppliers (at customer request) remove onsite correction equiptment, relying on standard/non-standard correction factors
|  | There is a risk that… | ..if correction equiptment (correctors) are removed from a customers premises, volume measurements will be less accurate, leading to a reduction in settlemetn accruracy
Effective From | 2019-02-14 | Category | METER ASSET DATA/DATA CORRECTION / VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review |  | Risk Status (Active/ Monitoring/Closed) | DRAFT
Related reporting
None to date
Industry activity
Workgroup/meeting/code change |  | comments
Issue raised at PAC 14/02/19 |  | Questions raised around where the obligation to have a corrector installed at a site v the appropriate correction factor being recorded in central systems sits.
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2018-02-14 | PAFA | PAFA To monitor progress on developments in this area and attempt to assist in researching the appropriate answer.

## PACR027
Risk Number | PACR0027 | Risk Title: | COVID-19 - impact on the operation of the PAC
|  | Risk Description: | During the COVID-19 pandemic there is the possibility that the PAC will not be able to effectively function if PAC members, PAFA and CDSP were negatively impacted.
|  | There is a risk that… | There is a risk that PAC will not be able to reach quoracy should a number of members or alternates are impacted by the virus. There is also a risk that the deliverables in to the PAC from PAFA or CDSP could be impacted.
Effective From | 2020-03-23 | Category | ALL | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
None to date
Industry activity
Workgroup/meeting/code change |  | comments
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2020-03-30 | industry comms | PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP

## PACR028
Risk Number | PACR0028 | Risk Title: | COVID-19 - related UNC modifications
|  | Risk Description: | A number of Urgent UNC modifications have been raised by industry to an attempt to mitigate the impact of COVID-19 on Shippers
|  | There is a risk that… | the urgent modifications lead to a negative impact on the settlement regime, particularly when the UK lockdown is lifted and operations begin to return to 'normal'. The modifications have been raised as urgent and it is acknowledged that there are limitations to the effectivness and the ability to monitor the temproary changes proposed.
Effective From | 2020-03-23 | Category | METER READ PERFORMANCE/VOLUME CONVERSION | RAG STATUS | Estimated AQ at risk (kwh) | TBC | Estimated value of risk (GBP) | TBC
Last Review | 2020-06-01 | Risk Status (Active/ Monitoring/Closed) | ACTIVE
Related reporting
None to date
Industry activity
Workgroup/meeting/code change |  | comments
2020-04-21 |  | Urgent UNC modifications raised (0721, 0722, 0723, 0724)
2020-04-30 |  | Final mod reports published following industry consultation
2020-04-30 |  | Urgent UNC mod panel meeting held - PAFA invited to attend to provide input on available monitoring
2020-05-07 |  | UNC 0725 raised
2020-05-11 |  | UNC 722, 723 and 724 are implemented by Ofgem (0721 still outstanding)
2020-05-12 |  | PAC discuss the ability to monitor the reports - Xoserve take actions to determine what reporting is available
2020-05-21 |  | 0725 Final mod report published following industry consultation
2020-05-29 |  | 0725 rejected by Ofgem
PAC activity / mitigating actions
DATE | ACTIVITY | comment
2020-03-30 | industry comms | PAC write to industry to advise that during the COVID-19 period, they will continue to monitor Shipper performance and would advise that Shippers notify PAC of any performance issues ASAP