## Slide 1: Change Assurance XEC Report - Health Check - 1
UK Link Release – November 20
May 2020

## Slide 2
Topic | RAYG | Summary
Business Case |  | The delayed detailed project planning and insufficient RAID management has significant risk for successful delivery of the outcomes for the November 20 Release. This is the first health check after the pulse check that was conducted in March 2020. Some of the observations raised as part of the pulse check are still to be addressed and this is reflected in the outcome of the assurance activity. It was highlighted by various Stakeholders that November 20 have implemented the following lessons from previous releases: Better engagement with Stakeholders (Service Transition/Business and People Change) Applied better workshop management but still need to build on consistency Positive ownership of change pack delivery Good control of the requirements catalogue Currently the design phase is still in progress and has been extended by 3+ weeks due to further requirements clarification and new requirements. However, the reasons and impact of the delay have not been communicated and escalated effectively. The extension of the design phase may have a slight increase on the EQR cost which is to be discussed with ChMC. Funding for the full delivery is yet to be secured and it is planned to be presented to IRC on 4th June while the Build phase is to commence at risk on 1st June. Due to incomplete detailed planning, the start-up and initiation phases were not delivered in time following project commencement in February 2020, the initiation and design stage gates are to be re-planned and baselined. The initial project planning focussed on just the design deliverables and lacked some detail of the overall picture of project management. This has resulted in lack of adequate project management governance for example: documentation, baselining milestones, financial tracking, RAID management, inclusion of requirements traceability in project plan and effective change management. It has been challenging to engage with Stakeholders on time due to the ways of working during Covid-19 situation. There should more support provided by SPM to the developing PM with close monitoring of the project and validation of messages being sent out to Customers to ensure good quality of outputs, and appropriate communication. There is a risk that the build environment may be delayed due to the configuration of Charm and a dependency on CSSC releasing the track 1 environment in time to perform the refresh (data and code) for the November 20 release. The lessons learnt from previous releases is to be reviewed and implemented on this release to ensure a successful outcome. It is recommended that the next change assurance health check should be conducted before entry into UAT.
Sponsorship |  | 
Governance |  | 
Scope & Solution |  | 
Team & Skills |  | 
Plan |  | 
Customer |  | 
Other - Information Security |  | 
Other – Suppliers |  | 
Other - Testing |  | 
Other – Environments |  | 
Project | Date | Change Assurance Type | Overall RAYG
UK Link Release – November 20 | 22/05/2020 | General Health Check - 1 | 
CA1 | Open 1 | Closed 0 | CA2 | Open 16 | Closed 0 | CA3 | Open 8 | Closed 0 | CA4 | Open 3 | Closed 0

## Slide 3: Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme

## Slide 4: Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects