## Slide 1: 7.5 XRN5110 - Nov 20 Release - Status Update
08/07//20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design Design activities completed 19/06/20. On track to complete Design milestone and Stage Gate Track 1 Build activities completed for 2 change there was a delay for XRN4899 due to complete - 03/07/20 SIT preparation complete and activities due to start – 29/06/20. The current plan takes us into contingency but looking to complete within plan Track 2 Build activities started to plan – 22/06/20 SIT preparation activities ongoing SIT activities due to start – 20/07/20 UAT UAT preparation, including Knowledge Transfer sessions, for both tracks on target to start to plan – 29/06/20 Security Working with Information Security to complete change impact assessments Return to Green Approval of the full delivery plan 01/07/20 Change Assurance approval – 03/07/20 |  |  | 
Risks and Issues | Low Risk: Missed requirements and test scenarios due to parallelism of resources between Nov 20 and all other projects. Low Risk: COVID-19 may impact availability of key resources Low Risk: Knowledge Transfer between Build and UAT partners may not be detailed enough and items may be missed |  |  | 
Cost | BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 Forecast to complete within budget |  |  | 
Resources | SME resources have been allocated for UAT and Tech Ops resource requirements have been requested Return to Green is approval of full delivery plan by 01/07/20 |  |  | 

## Slide 2: XRN5110 - Nov 20 Delivery Timeline

## Slide 3: XRN5110 Nov 20 - Scope
Track 1
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
2. Track 2
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 6 changes. Implementation is planned for November 2020

## Slide 4: XRN5110 - Nov 20 Change Assurance Health Check 1
Health Check 2 planned for before UAT 06/07/20 – 17/07/20
Health Check 3 planned for before Implementation 12/10/20 – 23/10/20