## Slide 1: Must Read Industry Journey review
Victoria Mustard
19/08/2020

## Slide 2: Project Phases
Following the initial workshops held with representatives of all customer segments we intend to split the Must Read process review into 3 phases
Phase 1 – Existing Must Read cleanse
Phase 2 – Outstanding Read requirements analysis
Phase 3 – Process Improvement phase

## Slide 3: Phase 1 Must Read Cleanse
Current Outstanding Must Read Pot | 173758​
​ | ​
MUR Created in Apr'20, May'20 & Jun'20​ | 19628​
DE/EX​ | 300​
Shipperless​ | 1367​
READ​ | 103085​
NO READ​ | 54616​
Xoserve engaging with all IGT/GT customers to review and close down (where appropriate) the DE/EX, Shipperless and Read pots (aim to complete by end of September)
All Shippers will be informed individually of the confirmed closed must reads by September 31st.

## Slide 4: Phase 3 Process Improvement Phase
Project Kick Off
Requirements & Change Plan
Opportunity Spotting
Future Process Design
Customer Evaluation
DESIGN
Generate a spread of ideas - explore widely to reduce the chance of missing something valuable, before focusing in and designing solutions
Design the target experience with customers in mind and review this with users. This may be an iterative process to establish the finalised journey and concepts.
DELIVER
Determine change plan and business case.
Handover to business with appropriate monitoring/measures agreed
Phases
Draft To Be journey (target experience)
Draft Concepts
Finalised To Be Journey
Concepts (for customers and colleagues)
Requirement
Value case
Implementation Approach
Draft KPIs
Journey Dashboard
Comms plan
Key Outputs
Supporting Info
Data to support research (CSATs, queries, volumes etc)
Delivery
Change plan
Governance to monitor
Clarity on enduring ownership
Journey Dashboard
Customer engagement re. potential concepts
Data ownership/ gathering
Define (Project team)
Segment Personas
Inspiration Report
DEFINE
Use the research to define areas to focus on
Process mapping
Process map
Further opportunities to improve process …and in turn experience
Compile into To Be
STAGE COMPLETE
Current position
DISCOVER
Orient and Engage, understand the service today
!
Sense check
July / August
September
October
Key
Green = completed
Black = still to do

## Slide 5: Phase 2 Outstanding Read requirements analysis
Current Outstanding Must Read Pot | 173758​
​ | ​
MUR Created in Apr'20, May'20 & Jun'20​ | 19628​
DE/EX​ | 300​
Shipperless​ | 1367​
READ​ | 103085​
NO READ​ | 54616​
Xoserve running more detailed analysis on these pots to understand read history and address details more clearly.
All Customers to be informed of progress following analysis (analysis completion aim end of August)
Xoserve to work with GT/IGT community following analysis to enable them to collect reads /update address data/close MUR contacts if no longer relevant