## Slide 1: UK Link Future Releases Update
October 2020 ChMC

## Slide 2: UK Link Future Releases Update
Agenda:
Future Releases Governance Timeline 2020 – 2021
Allocated Changes - in delivery
Minor Release Drop 9 – potential scope
November 2021 – potential scope
Glossary

## Slide 3: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Please note that this slide includes potential activity within UK Link over the next 24 months
Assumes 3x Minor Releases required prior to May 2021
BER Approval
10/04/18
Potential Activity
On track
At risk
Key:
Complete
BER Approved Jun-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
Scope Approved – April ChMC
Potential Activity
MiR 9
MiR 8
Retro
Nov 20
June 20
MiR 7
Potential Activity
Scope Approval – November ChMC
Scope Approval – Jan ChMC
MiR 10
Potential Activity
BER Approval – May ChMC
Scope Approved – August ChMC
June 21
Nov 21
Potential Activity
Scope Approved – Aug 2020 ChMC
Scope Approval – November 2020 ChMC
Full EQR Approval – Oct ChMC
BER Approval - Nov ChMC

## Slide 4: UK Link Allocated Changes – In Delivery
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4780c | MAP ID Part C | In Capture | Tbc – June 2021 | Large | Shippers
 | 4627 | Consequential Central Switching Services | In Delivery | Tbd | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO
MiR Drop 8 | 5181 | Acceptance of consumption adjustments where meter point moved after meter set to dead | In Delivery | Nov 2020 | Small | MiR Delivery
 | 5118 / 5174 | Service sustaining activity – Change how actual MR data is populated in UK Link / Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | In Delivery | Nov 2020 | Small | MiR Delivery

## Slide 5: UK Link Allocated Change - Continued
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
Jun-21 | 4941 | MOD0692 - Auto updates to meter read frequency | Descoped from Nov 20. Dependent on appeal decision | June 2021 | Large | Shippers
 | 4992 | MOD0687 – Creation of new charge to recover last resort supply payments | Descoped from Nov 20. Dependent on Ofgem decision | June 2021 | Large | Shippers
 | 5093 | MOD0711 – Update of AUG Table to reflect new EUC bands | Solution Option approved | June 2021 | X-Large | Shippers
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | HLSOs in review. Scope inclusion dependent on SEC/Ofgem decision | June 2021 | Large | DNO
 | N/A | Placeholder for Service Sustaining Activity | Tbd | June 2021 | Tbd | Xoserve
XRN5142 was descoped at September ChMC
XRNs 4941 and 4992 will be descoped from the release, at the Extraordinary ChMC arranged for 26th October , if not approved by Ofgem.

## Slide 6: UK Link Nov 2021 Release - Candidates
Potential Release | XRN | Change Title | Comments | Status | Complexity | Points | Finance
Nov 21 | 5038 | MOD0691 – Class 2,3 or 4 meter points to Class 1 when G1.6.15 criteria are met | Depending on solution option chosen this change could be delivered via a Minor Release | In Capture | Tbd | Tbd | Shipper
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Related to a SEC change. Descoped from June 21 Major Release | HLSOs | Tbd | Tbd | DN
 | 4990 | MOD0664 – Transfer of sites with low read submission performance |  | In Capture | Tbd | Tbd | Shipper
 | 5186 | MOD0696 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | If approved MOD will be progressed | In Capture | Tbd | Tbd | DN
 | 5187 | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Related to MOD0696 | In Capture | Tbd | Tbd | DN
 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes |  | HLSOs | Tbd | Tbd | Shipper
 | 5091 | Deferral of creation of Class change reads at transfer of ownership |  | HLSOs | Tbd | Tbd | Shipper
 | 5197 | QMP File validation in CMS – Current Address Field |  | HLSOs | Tbd | Tbd | IGT
Service sustaining activity will be considered for inclusion in future releases.

## Slide 7: Minor Release Drop 9 - Candidates
Potential Release | XRN | Change Title | Comments | Status | Complexity | Points | Finance
MiR Drop 9 | 5080 | Failure to Supply Gas (FSG_GSOP1) – System Changes | RIIO-2 – Required for start of April 2021 | HLSOs | Tbd | Tbd | ?
 | 5210 | Daily CV Determination Service DN Invoicing Options | Minor Release candidate | HLSOs | Tbd | Tbd | NG
 | 5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | Minor Release candidate. Potential impacts to Gemini | HLSOs | Tbd | Tbd | ?
Minor Release Drop 9 implementation date will be in Feb 2021. Exact date to be confirmed

## Slide 8: November ChMC
UK Link Future Releases Updates:
Minor Release Drop 9
  Scope for approval
  Potential implementation dates for discussion
November 21 Major Release
  Update on progress through Capture
  Scope for approval.

## Slide 9: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal – an external request for a change to UK Link
CR | Change Request – an internal request for a change to UK Link
HLSO(s) | High Level Solution Option(s)