## Slide 1: Xoserve IX Refresh
Customer Update
November 2020

## Slide 2: IX Refresh Customer Update
The project has not seen any impact so far following recent changes to government guidance regarding COVID-19
The project end date is February 2021. Our current run rate is tracking a January 2021 completion
The project is targeting to complete all physical installations by 30th November. Currently there are 8 sites (5%) that are at risk of missing this date
There are four key milestones for customer migrations:-
  Installation of Network lines (At Risk)
  Installation of Routers (At Risk)
  Installation of Servers (At Risk)
  Customer Migration (On Track)
The project would like to request customer support in ensuring that we migrate you as quickly and smoothly as possible onto your new IX Gamma network
  The migration onto the new IX Network will allow a reduction in IX pricing
  Your IX equipment will be fully refreshed onto new hardware
  There is a risk that we will not be able to extend the legacy support past February 2021
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com