## Slide 1: Xoserve IX Refresh
Customer Update
December 2020

## Slide 2: IX Refresh Customer Update
The project is not currently being impacted by COVID-19 restrictions
The project end date is February 2021. Our current run rate is tracking a February completion
The project targeted to complete all physical installations by 30th November.
  6 sites (3%) missed the milestone date
    3 sites have dates scheduled in December
    3 sites yet to be scheduled
86% of all migrations have been completed
Project team have engaged with our legacy service provider to secure extension terms, if needed.
  Agreement in place to extend support past February 2021
  Minimum 3 month extension
  A decision will be made mid-December
  Project needs customer support to ensure all remaining sites are migrated by February
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com