## Slide 1: Xoserve IX Refresh
Customer Update
January 2021

## Slide 2: IX Refresh Customer Update
The project is currently experiencing limited impact regarding the current COVID-19 lockdown
The project end date is February 2021. Our current run rate is tracking a February completion
91% of all migrations have been completed
  16 IX sites remaining
Legacy support has been extended on the minimum term (3 months) to mitigate any impact to COVID-19 restrictions on the final migrations
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com