## Slide 1: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: To date we had had 1 network use the service for both extract and SMS service for a limited number of meter points due to the limited data availability in UK Link which is currently circa 5-million-meter points with a further 2 million planned by end of December 2020, discussions ongoing with Supply Point Administration Agreement (SPAA) group to encourage greater population of data, please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Project Closedown: Following completion of PIS project closedown is in progress. The Change Completion Report has been submitted for approval. Scope Variations: XRN4850 design for scope variation for report automation in progress. Report delivery mechanism decision expected during Change Management meeting. Manual reporting will be available in the interim should the service be used. XRN4850 UK Link Portal changes – to allow special characters, increase character limits in text and email and display character number count is in progress XRN4780(B) MAP ID – MAP ID data migration in to UK Link was successfully completed as per plan on 14th December 2020 |  |  | 
Risks and Issues | Risk – DN's/IGT's do not use the new SMS/Email broadcast functionality during Post Implementation Support, because of the limited number of customer contact details uploaded to UK Link or networks do not need to send broadcasts during this period. To mitigate, Networks to confirm requirements for the report details to provide % saturation of sites in each LDZ which has BRO data populated. |  |  | 
Cost | Costs have been finalised in the CCR which has been submitted for approval |  |  | 
Resources | No resource issues identified for the remainder of the project |  |  | 
Updates as of the 16th December 2020

## Slide 2
Decision Required: Deliver Mechanism for the Network Reporting
Background
Networks have requested to automate the generation and delivery of the Network Delivery Report following delivery of broadcast notifications to end consumers. Three options are being considered: via existing IX channels to deliver the reports Option no longer viable using new Twilio service to email Network users a link to access the reports via Data Discovery Platform (DDP) portal access the reports – option A and option B (Please see next slide) Following a split vote in December, it was agreed to defer the final decision to January Since then, an addition option for DDP has been included as a result of a change in resource circumstances within the DDP team A piece of reporting work that was due to be delivered in early 2021 for the Shippers has been postponed until later in the year therefore freeing up existing DDP resource meaning there is capacity to deliver the reporting as part of DDP BAU delivery without the need for additional resource. This means that the automated reporting can be delivered at zero cost if scheduled for Q1 2021 Xoserve is recommending using the Data Discovery Platform to deliver this reporting requirement. This approach has been ratified by our platform architects as the optimal delivery mechanism in order to provide a consistent customer experience. DDP is our enduring solution, has the necessary security protocols in place and therefore avoids introducing a further delivery mechanism which generates technical debt / avoidable future operational overheads.
Decision Required
A decision is required as to which report delivery option is preferred so that Xoserve can proceed with build, test and deliver. n Required
Updates as of the 22nd December 2020

## Slide 3
Decisions Options
Options: Deliver Mechanism for the Network Reporting | Outcome
Azure/Twilio Service Solution: Strategic Delivery timescale: late January/early February 2021 Delivery cost: £0 included within SMS/Email notification allowance Considerations: switch may need to be made to enduring solution at some point in the future, at this point additional costs may be incurred. If alternative service provider is sourced, additional integration costs may be incurred. Data is only available for 7 business days, following that a service desk ticket would be required to obtain the report | 
Data Discovery Platform (DDP) A Solution: Enduring Delivery timescale: late February/early March Delivery cost: £0 delivered by DDP as part of BAU activities Delivery benefits: when a report is available, an notification email can be delivered so that you only need to access DDP when prompted. Data will be held within DDP for 12 months so supplementary process not required to retrieve reports after 7 business days | 
Data Discovery Platform (DDP) B Solution: Enduring Delivery timescale: to be agreed with Networks for a future DDP/Minor release implementation Delivery cost: circa £35,000 (DDP integration and project costs) Considerations: existing delivery mechanism for data delivered by Xoserve. Will have to be delivered outside of June 20 release | 
In this meeting the decision is required on one of the above options
Updates as of the 22nd December 2020

## Slide 4: XRN4850 – SMS/Email Broadcast Notification Timeline
Project closedown is in progress.
Daily/Monthly Network Usage report delivery in progress, delivery mechanism decision to be made during the meeting
Updates as of the 16th December 2020
TODAY

## Slide 5: XRN4996 June 20 Release Summary
June 20 Release consists of 7 changes, Implementation was completed for June 20:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 - Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters (UKLink file formats, new service to follow)
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining change requests. Descoped at ChMC on 8th January 2020
** Descoped at eChMC on 22nd November 2019
*** Added to scope (revised scope from original)
Updates as of the 16th December 2020