## Slide 1: December KPM Failure Updates 2020 (Version 2 @ 12th Jan 2021)

## Slide 2
Key Performance Measures December 2020 – Right First Time Failures (Version 2)
Journey / Process | Frequency | Measure Detail | Target Description | Oct-20 | Nov-20 | Dec-20 | Comments
Customer Contacts | Monthly | % of Escalations raised against total query responses | Less than 5% | 2.36% | 5.49% | 6.99% | 27 out of 386 query resolutions issued in Dec'20 were 'reopened' back to Xoserve. Process improvements underway to enhance current system functionality to enable the distinction between a rejected query response versus a further question being posed as currently both scenarios count towards a failure in this KPM scenario.
Customer Relationship Management | Quarterly | KVI relationship survey | 95% starting to trust/ trust | Next Survey-Dec Next Report-Jan | Next Survey-Dec Next Report-Jan | 91.67% | Highest scores since we started measuring Trust, with all 3 categories performing above 90% for the first time. There have been improvements to the customer contact and query management experience, more frequent customer engagement and Xoserve's Customer Centric approach has resulted in customer trust rising from 70.5% in Dec 2019 to 91.67% in Dec 2020. Improvements to RFT and access to self-serve process guidance are the things that customers have said we need to improve on.
Monthly AQ processes | Monthly | % of AQs processed successfully | 100% | 99.98% | 99.96% | 99.84% | Performance is below 100% as a small number of exceptions were created during this process. Those exceptions either pause the process or require manual rework, but as further intervention is required to complete the transaction, that transaction is not 'Right First Time'.
Monthly AQ processes | Monthly | % of AQs at risk/ have defects | 0.75% | 1.34% | 2.04% | 1.69% | 1.69% of LDZ AQ is currently known to be at risk due to defects. 0.23% of MPRNs are known to be currently impacted by an AQ related defect. Data based on AQs Calculated up to the end of December 2020, Effective from 01/01/2021.

## Slide 3
Journey / Process | Frequency | Measure Detail | Target Description | Oct-20 | Nov-20 | Dec-20 | Comments
Energy Balancing (Credit Risk Management) | Monthly | % of revenue collected by due date | 98% | 99.72% | 99.92% | 96.64% | 11 customers were issued with Failure to Pay Notices this reporting month with one of them being for a high value invoice which was not paid on the payment due date. This had a significant impact on the performance this month making it unusually lower. This customer explained they used a new payment system to pay all of their invoices and this particular invoice to Xoserve was missed. All payments were settled in full the next business day.
Invoicing customers | Monthly | % of exceptions resolved within 2 invoice cycles of creation date | 100% | 97.41% | 94.37% | 98.50% | 112,425 exceptions created - 110,739 exceptions closed
Key Performance Measures December 2020 – Cycle Time Failures (Version 2)

## Slide 4: December Overall KPM Update 2020 (Version 2 @ 12th Jan 2021)

## Slide 5
Key Performance Measures December 2020 – Right First Time / Quality (Version 2)
Journey / Process | Frequency | Measure Detail | Target Description | Oct-20 | Nov-20 | Dec-20 | Comments
Customer Contacts | Monthly | % of Escalations raised against total query responses | Less than 5% | 2.36% | 5.49% | 6.99% | 27 out of 386 query resolutions issued in Dec'20 were 'reopened' back to Xoserve. Process improvements underway to enhance current system functionality to enable the distinction between a rejected query response versus a further question being posed as currently both scenarios count towards a failure in this KPM scenario.
Customer Contacts (technical) | Monthly | % of tickets not re-opened within period | 95% | 98.80% | 98.30% | 99% | December 2020 saw our highest performance on Right First Time during 2020 at 99% against our target of 95%. This continued increased performance is driven through new operational quality processes, supported by Service Now tooling implemented during October.
Customer Joiners/Leavers (UK Gas Market) | Monthly | % of readiness criteria approved by customer (join) Shippers | 100% | 100% | No Joiners | 100% | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % of readiness criteria approved by customer (join) Non Shippers | 100% | No Joiners | 100% | No Joiners | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % of exit criteria approved and account deactivated within D+1 of cessation notice being issued (leave) Shippers | 100% | 100% | No Leavers | 100% | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % of exit criteria approved and account deactivated within D+1 of cessation notice being issued. (leave) Non-Shippers | 100% | 100% | 100% | 100% | 
Customer Relationship Management | Quarterly | KVI relationship survey | 95% starting to trust/ trust | Next Survey-Dec Next Report-Jan | Next Survey-Dec Next Report-Jan | 91.67% | Highest scores since we started measuring Trust, with all 3 categories performing above 90% for the first time. There have been improvements to the customer contact and query management experience, more frequent customer engagement and Xoserve's Customer Centric approach has resulted in customer trust rising from 70.5% in Dec 2019 to 91.67% in Dec 2020. Improvements to RFT and access to self-serve process guidance are the things that customers have said we need to improve on.
Customer Reporting (all forms) | Monthly | % of RFT against all reports dispatched | 99% | 100% | 100% | 99% | A customer identified that one of the Mno. Data Extract Files was issued with extra characters. This prevented the internal upload. The CDS team undertake QC's but due to the size of this data-set the error was not flagged. We are still working with Tech Ops to understand why this occurred.
Demand Estimation obligations | Bi Annually | Confidence in DE Team to deliver DESC obligations (via Survey of DESC Members) | 75% Met or Exceeded | Next Survey-Dec Next Report-Jan | Next Survey-Dec Next Report-Jan | 100% | 
Energy Balancing (Credit Risk Management) | Monthly | Energy Balancing Credit Rules adhered to, to ensure adequate security in place | 100% | 100% | 100% | 100% | 
Invoicing customers | Monthly | % of invoices not requiring adjustment post original invoice dispatch | 98% | 100% | 100% | 100% | 
Invoicing customers | Monthly | % of customers that have been invoiced without issues/ exceptions (exc. AMS) | 100% | 100% | 100% | 100% | 
Invoicing customers | Monthly | % customers with less than 1% of MPRNs which have an AMS Invoice exception | 97% | In Development | 100% | 100% | 
Manage Shipper Transfers | Monthly | % of successful shipper transfers processed | 100% | 100% | 100% | 100% | 
Manage updates to customer portfolio | Monthly | % of valid CMS challenges received (PSCs) | Less than 1% | 0.14% | 0.07% | 0.07% | A record equalling performance.
Management of Customer Issues | Monthly | Provision of relevant issue updates to customers accepted at CoMC and no negativity on how the issue is managed. | 100% | 100% | 100% | 100% | Issue updates provided at December CoMC. Communications issued to customers as per the agreed Issue Management Framework. No negative comments received regarding the management of issues.
Managing Change | Monthly | No of valid defects raised within PIS period relating to relevant change (excluding programmes) | Zero P1 or P2 valid defects | 0 | 0 | 0 | 0 defects raised on Gemini changes during December
Managing Change | Monthly | No of valid defects raised within PIS period relating to relevant change (excluding programmes) | <=four valid P3 defects | 0 | 1 | 0 | 0 defects raised on Gemini changes during December
Managing Change | Monthly | No of valid defects raised within PIS period relating to relevant change (excluding programmes) | <=five valid P4 defects | 0 | 5 | 2 | 0 defects raised on Gemini changes during December 1 defect raised against UK Link Nov-20 on 3rd Dec, Difference in ratchet changes calculated for class 2 sites, code fixed on 4th Dec 1 defect raised against UK Link Minor Release 8 on 15th Dec, Monthly AQ Roll Process, code fix planned for 5th Feb 2021
Meter Read / Asset processing | Monthly | % of meter reads successfully processed | 99.5% | 99.97% | 99.98% | 99.98% | 
Meter Read / Asset processing | Monthly | % of asset updates successfully processed | 99.5% | 99.68% | 99.79% | 99.99% | 
Monthly AQ processes | Monthly | % of AQs processed successfully | 100% | 99.98% | 99.96% | 99.84% | Performance is below 100% as a small number of exceptions were created during this process. Those exceptions either pause the process or require manual rework, but as further intervention is required to complete the transaction, that transaction is not 'Right First Time'.
Monthly AQ processes | Monthly | % of AQs at risk/ have defects | 0.75% | 1.34% | 2.04% | 1.69% | 1.69% of LDZ AQ is currently known to be at risk due to defects. 0.23% of MPRNs are known to be currently impacted by an AQ related defect. Data based on AQs Calculated up to the end of December 2020, Effective from 01/01/2021.

## Slide 6
Key Performance Measures December 2020 – Cycle Time / Delivery (Version 2)
Journey / Process | Frequency | Measure Detail | Target Description | Oct-20 | Nov-20 | Dec-20 | Comments
Customer Contacts | Monthly | % P5 queries responded to within SLA/ OLA | 90% | 88.80% | 91.85% | 90.76% | 
Customer Contacts | Monthly | % responded to within SLA | 90% | 94.45% | 96.00% | 96.18% | Continued strong performance within response SLAs, there is further opportunity to improve this during 2021 through use of automation and tooling which will be explored later in the year.
Customer Joiners/Leavers (UK Gas Market) | Monthly | % key milestones met on readiness plan (join) Shipper | 100% | 100% | No Joiners | 100% | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % key milestones met on readiness plan (join) Non Shipper | 100% | No Joiners | 100% | No Joiners | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % closure/termination notices issued in line with Service Lines (leave) Shipper | 100% | 100% | No Leavers | 100% | 
Customer Joiners/Leavers (UK Gas Market) | Monthly | % of closure notices issued within 1 business day following last exit obligation being met (leave) Non Shipper | 100% | 100% | 100% | 100% | 
Customer Relationship Management | Quarterly | Survey results delivered to CoMC in Month +1 | 100% | 100% | Next Report-Jan | Next Report-Jan | 
Customer Reporting (all forms) | Monthly | % of reports dispatched on due date against total reports expected | 100% | 100% | 100% | 100% | 
Demand Estimation obligations | Monthly | DESC / CDSP DE obligations delivered on time | 100% | On Track | On Track | On Track | 
Energy Balancing (Credit Risk Management) | Monthly | % of revenue collected by due date | 98% | 99.72% | 99.92% | 96.64% | 11 customers were issued with Failure to Pay Notices this reporting month with one of them being for a high value invoice which was not paid on the payment due date. This had a significant impact on the performance this month making it unusually lower. This customer explained they used a new payment system to pay all of their invoices and this particular invoice to Xoserve was missed. All payments were settled in full the next business day.
Energy Balancing (Credit Risk Management) | Monthly | % of revenue collected by due date (+2 days) | 100% | 100% | 100% | 100% | 
Invoicing customers | Monthly | % of invoices sent on due date | 100% | 100% | 100% | 100% | 
Invoicing customers | Monthly | % of exceptions resolved within 2 invoice cycles of creation date | 100% | 97.41% | 94.37% | 98.50% | 112,425 exceptions created - 110,739 exceptions closed
Manage Shipper Transfers | Monthly | % processed within SLA | 100% | 100% | 100% | 100% | 
Manage updates to customer portfolio | Monthly | % CMS Contacts processed within SLA | 80% in D+4 | 95.87% | 94.71% | 93.43% | While performance dipped very slightly across each measure, each target was surpassed again. The slight drop can be attributed to the fewer short cycle time Contacts submitted during the month due to the holidays. For the longer cycle time Contacts, there will have been a longer turnaround time where there is a referral to the DNs and IGTs as it will have been more difficult to attain appointments for visits during the holiday period.
Manage updates to customer portfolio | Monthly | % CMS Contacts processed within SLA | 95% in D+10 | 96.68% | 96.64% | 95.63% | 
Manage updates to customer portfolio | Monthly | % CMS Contacts processed within SLA | 98% in D+20 | 98.88% | 99.14% | 98.53% | 
Management of Customer Issues | Monthly | Plan accepted by customers & upheld (Key Milestones Met as agreed by customers) | 90% | 100% | 100% | 100% | AQ Taskforce: progress updates including outcome of the analysis published & discussed at December CoMC including update on financial adjustments. Financial Adjustments for historical defects on target to meet plan. AQ defects continue to be prioritised and managed until resolution. Low volume of MPRNs impacted by unresolved defects. Issue Management summary slide published providing updates for all 'Gold' issues.
Managing Change | Monthly | % level 1 milestones met | 95% | 100% | 100% | 100% | 
Meter Read/Asset processing | Monthly | % requests processed within SLA | 100% | 99.99% | 99.99% | 100% | 
Monthly AQ processes | Monthly | % Notifications sent by due date | 100% | 99.99% | 99.99% | 100% | System defect contributing to Oct'20 and Nov'20 failures has now been successfully resolved resulting in 100% achieved for this measure in Dec'20.