## Slide 1: Amendment Invoice Update
13th January 2021

## Slide 2
Amendment Invoice Taskforce Update
Health – RAG |  |  | Return to Green Plan | 
Overall Status | Previous | Current | A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid January 2021. This will enable the Plan to return to green and the defect SLAs will be met. Dedicated team to progress defects Number of exceptions have increased this month to 65,716 A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid January 2021. Delays experienced due to a separate Project code freeze and additional assurance scenarios have been identified. | 
Plan | Previous | Current |  | 
Exceptions | Previous | Current |  | 
Defects | Previous | Current |  | 
Executive Summary |  |  |  | Key Progress & Milestones (Last Month: September)
Key Updates: ASP file merge activities ensured the 61 MPRNS with mismatch were included in the relevant customer ASP files. All AML file delivered ahead of payment due date. Exception figure = 65,716 Risks/Issues: Defects impacting the Amendment invoice continue to miss SLA. A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid January 2021. This will enable the Plan to return to green and the defect SLAs will be met. The backlog of exceptions (although significantly reduced in recent months) means the exceptions SLA is not being met, meaning customers have reconciliations that are being excluded for their invoices. |  |  |  | ASP Mismatch file merge activities continue to ensure customers receive full supporting information for their LSP sites on invoice issue date. All AML files delivered to customers ahead of SLA.
 |  |  |  | Upcoming Activities & Milestones (Next Month: October)
 |  |  |  | Automation of exception resolution steps for specific MN09 scenarios. Work on resolving the backlog of defects continue – plan to clear backlog by mid Jan-20.

## Slide 3: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
GREEN
RAG Justification
61 MPRNs out of the 179,513 LSPs (0.3%) that were billed incurred an ASP mismatch.
61 unique MPRNs with ASP mismatch. File merge activities ensured mismatch data was included in ASP file issue on the invoice issue date.
All AML files were delivered ahead of the SLA.
 |  |  | ASP Mismatches |  | AML Mismatches |  | 
Billing Month | Billed Contracts | LSP Invoiced | Unique LSP MPRNs causing ASP mismatch | % of invoiced LSPs causing ASP mismatches | SSP Invoiced | Unique SSP MPRNs causing AML mismatch | % of invoiced SSP causing AML mismatches
Nov-19 | 10,746,544 | 235,402 | 110 | 0.05% | 10,511,142 | 585 | 0.01%
Dec-19 | 9,907,903 | 227,508 | 133 | 0.06% | 9,680,395 | 2,019 | 0.02%
Jan-20 | 11,143,336 | 190,009 | 189 | 0.10% | 10,953,327 | 1,521 | 0.01%
Feb-20 | 10,672,939 | 206,203 | 151 | 0.07% | 10,466,736 | 247 | 0.002%
Mar-20 | 11,210,849 | 257,092 | 172 | 0.07% | 10,953,757 | 1,113 | 0.010%
Apr-20 | 10,308,100 | 249,620 | 120 | 0.05% | 10,058,480 | 4,582 | 0.046%
May-20 | 10,227,416 | 240,451 | 54 | 0.02% | 9,986,965 | 419 | 0.004%
Jun-20 | 9,897,048 | 183,092 | 48 | 0.03% | 9,713,956 | 191 | 0.002%
Jul-20 | 10,584,643 | 183,410 | 44 | 0.02% | 10,401,233 | 222 | 0.002%
Aug-20 | 10,334,318 | 180,969 | 40 | 0.02% | 10,153,349 | 146 | 0.001%
Sep-20 | 10,800,486 | 175,523 | 47 | 0.03% | 10,624,963 | 109 | 0.001%
Oct-20 | 10,995,039 | 185,324 | 63 | 0.03% | 10,809,715 | 58 | 0.001%
Nov-20 | 11,081,470 | 179,513 | 61 | 0.03% | 10,901,957 | 189 | 0.002%

## Slide 4: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
AMBER
RAG Justification
Automation of exception resolution steps continuing to be worked upon – a number of codes have now been automated
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
65,716 distinct MPRNs currently have unresolved exceptions within our systems (as of 5th January 2021).
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 5: AMS Invoice – Billed MPRNs vs MPRNs with exception
Chart: 
| 43952 | 43983 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166
Total MPRNS Billed | 11210849 | 10308100 | 10227416 | 9897048 | 10584643 | 10334318 | 10800486 | 10995039
MPRNS with Exception | 320023 | 130441 | 186437 | 74660 | 33561 | 29813 | 35198 | 45066
% MPRNs with exception vs MPRN Billed | 0.028546 | 0.012654 | 0.018229 | 0.0075437 | 0.0031707 | 0.0028849 | 0.0032589 | 0.0040988

## Slide 6: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
GREEN
RAG Justification
Cataloguing of all scenario resolution steps to ensure accuracy now completed.
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
133 distinct MPRNs for the November 2020 billing period currently have bill blocks placed upon them (as at 5th January 2021). Bill blocks are placed on MPRNs where there are known issues that will result in incorrect charges being calculated.
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 7: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
4 Defects did not meet the December's SLA 63566 – Defect was placed on hold 14/09 as object locked with defect 62634. On hold status was removed 25/09 and defect is currently in UAT Assurance status which is due for completion by 12/01/21 for deployment 15/01/21 63690 – Defect has been placed on hold 30/09 as object locked with defect 63485 and defect 61093. This defect will be progressed once the other 2 defects have been deployed. -63691 – Defect was placed on hold 30/09 as object locked with defect 62060. On hold status was removed 09/11 and defect is in UAT Execution status. - 63726 – Defect is a complex issue which required 2 defect review sessions to clarify on the test scenarios. Defect has now been progressed and is in UAT Execution status.
10 open Amendment related defects as of 7th January 2021
(8 defects open at last month’s update)
Defect ID | Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
63346 | (WB) High priority - Volume and Energy is being calculated incorrectly for read inserted between Cyclic (CYCL) Read and subsequent Estimated Read (LDEX) for a Class 3 Meter Point (UBR File) | 10/08/2020 | 15/01/2021 | 06/11/2020
63392 | Linked with defect 63142 & defect 63494 (WB) High priority -Transfer estimated read (OPNT) is getting derived incorrectly if transfer read loaded through RGMA process and previous read of shipper transfer is an estimated read | 14/08/2020 | 15/01/2021 | 06/11/2020
63393 | (WB) High Priority - For an NDM Prime Site, the Sub site volume and energy is not getting calculated if there is an Meter Reading Unit (MRU) frequency change for the same class | 14/08/2020 | 08/01/2021 | 06/11/2020
63566 | (WB) Medium priority - Inconsistent RGMA behavior of class 2 sites with or without DRE/AMR | 10/09/2020 | 15/01/2021 | 04/12/2020
63690 | (On Hold - objects locked under Defect#61093) Medium priority - Issue with the Class change re-estimation; whenever the previous Class is either Class 3 or 4, and the Read is received in the Class 2 period, the Class change estimated Read on the Class 2 start date does not get updated | 28/09/2020 | TBC | 04/12/2020
63691 | (Linked with defect#63498, defect#61966 )Medium priority - A read is not getting loaded in the Prime/Sub table after processing the read through the MOD 700 UBR process for Class 3 prime/sub sites under the EUC band - (Identified during UAT of Defect 62178) | 28/09/2020 | TBC | 04/12/2020
63726 | Medium priority - Issue with the Class 3 Prime Process; where the subsequent Actual Read has not considered the Shipper Transfer as the last Read Date | 05/10/2020 | TBC | 04/12/2020
64169 | For a Class 4 Prime site, after performing an NDM Class 4 Prime Reconciliation, the recalculated REC net off Volume and Energy is not getting updated in the EL31 screen | 11/12/2020 | 05/03/2021 | 05/03/2021
64250 | Issue with the DM bill order creation job, where bill orders are being created when the PCA Values are not loaded for DM Sites; however, should not create billing documents for the meters where we can't find any PCA process raised for these sites | 22/12/2020 | 05/03/2021 | 05/03/2021
64251 | When the ZB_REC_Val_exclu report is run it is bringing back multiple duplicates for the Class 4 sites; however the report is used for validation purposes and shouldn't bring back duplicate values | 22/12/2020 | 05/03/2021 | 05/03/2021

## Slide 8: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Reports shared with all customers and general and individual WebEx’s are ongoing.
MI reports continue to be shared with our customers 2 business days after Amendment invoice issue date.
Ongoing individual customer meetings to discuss what the MI means specifically to them.
If any customer would like an explanation of the MI reports they receive just let us know and we will arrange a session (contact Dan Donovan, Xoserve Invoicing Business Process Manager - dan.l.Donovan@xoserve.com).