## Slide 1: Section 3: DSC Change Budget & Horizon Planning

## Slide 2: 3.1 – DSC Change Budget 20/21 (Financial Year To Date) & 21/22

## Slide 3: Budget v Spend BP20/21 Financial Year To Date
Total available funds have decreased by £7k as a result of 2 changes moving through the lifecycle (see 2nd tab in embedded s/s for details)
Position as of Feb-21
Chart: Total Budget v Spend BP20/21 FYTD
| Total £
Change Budget 20/21 Pipeline | 1719892.8568
20/21 Budget | 3000000
Chart: Constituency Budget v Spend BP20/21 FYTD
| NTS £ | GDN£ | IGT £ | Shipper £
Change Budget 20/21 Pipeline | 15140 | 490972.6567 | 75484.9336 | 1138295.2665
20/21 Budget | 48000 | 600000 | 9000 | 2343000
Chart: Variance in available funds
| NTS £ | GDN£ | IGT £ | Shipper £
Varience in avilable funds since last report | -13940 | 6940 | 0 | 0

## Slide 4: Budget v Forecasted Spend BP21/22 (as of Mar-21)
Chart: Total Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 2589600 | 500000 | 100000 | 200000 | 200000
Spend | 1113485 | 0 | 0 | 0 | 0

## Slide 5: Budget v Forecasted Spend BP21/22 Per Constituency
Chart: Shipper Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 1495000 | 288654.6185 | 57730.9237 | 115461.8474 | 115461.8474
Spend | 836385 | 0 | 0 | 0 | 0
Chart: DN Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 900000 | 173772.0111 | 34754.4022 | 69508.8044 | 69508.8044
Spend | 258100 | 0 | 0 | 0 | 0
Chart: NTS Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 54600 | 10542.1687 | 2108.4337 | 4216.8675 | 4216.8675
Spend | 0 | 0 | 0 | 0 | 0
Chart: IGT Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 140000 | 27031.2017 | 5406.2403 | 10812.4807 | 10812.4807
Spend | 19000 | 0 | 0 | 0 | 0

## Slide 6: 3.2 – Change Pipeline

## Slide 7: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: XRNs Per Category
| Pre-capture | Capture | Ready for delivery | Standalone | Nov-20 | Jun-21 | Nov-21 | MiR8 | MiR9 | MiR10 | MiR11 | PAC 21/22 | Xo Change Fund
XRNs | 17 | 23 | 2 | 5 | 4 | 1 | 6 | 3 | 2 | 0 | 0 | 0 | 0

## Slide 8: 2020-2022 DSC Change / MiR Pipeline
Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
2020 | 2021 | 2022
Approval on track
Approval at risk
Governance Approvals Key
Approved
Nov 21
Jun 21
MiR 10
MiR 9
Nov 20
Xo CF
Scope Approved – August ChMC
MiR
11
Scope / EQR
Scope
Scope
EQR
CP / BER
BER
CCR
CCR
PAC
CP / BER
Scope
CCR
CCR
Stand Alone
XRNs
4645
5164
BER
CCR
CCR
CCR
CCR
MiR 8
CCR
XRNs
5167
XRNs
5120
XRNs
5183
XRNs
5146
XRNs
5206
5237
Project RAG Key
Not Started
On Track
Potential risk to plan
Plan At Risk
Complete
CSSC
Non-DSC / MiR
Retro
Activity
Potential Activity
XRNs
4876
XRNs
5038
4876CCR

## Slide 9: Section 4: Capture

## Slide 10: 4.1 New Change Proposals – Initial Review
XRN / Title | Voting |  |  |  | DSC Service Area
 | Shipper | DNO | IGT | NTS | 
XRN5327 Xoserve Change Fund 2021/22 | X | X | X | X | 
XRN5321 PAC Ring-Fenced DSC Change Budget 21/22 | X | X | X | X | 
XRN5329 Amendments to V16 of the Service Description Table | Information Only |  |  |  | N/A

## Slide 11: XRN5327 Xoserve Change Fund 2021/22
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Problem Statement
As part of the 2021/22 Xoserve Business Plan a budget to fund DSC Change was approved. This budget (£3.6m) contains a ring-fenced £200,000 that is available for use by Xoserve to deliver change that is appropriate for delivery outside of a major or minor release.
Sponsor Representative | Xoserve
Change Description
This Change Proposal will act as the parent XRN for the financial year 2021/22. The Xoserve Change Fund will allow Xoserve greater flexibility to deliver appropriate changes with more agility, which will further lead to process and system improvements to increase efficiency and boost customer experience.
Change Type | Non Regulatory
Priority Score | Low
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X
This is a parent XRN that may deliver changes that impact all parties | 

## Slide 12: XRN5321 PAC Ring-Fenced DSC Change Budget 21/22
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Each year the Performance Assurance Committee (PAC) requests a budget to amend existing / create new performance assurance reports. These reports and dashboards are used to monitor industry performance in settlement related risk areas (e.g. meter reads, assets). The ChMC has approved a ring-fence proportion of the wider DSC Change Budget for the development of such change. A parent XRN is required in each financial year to enable the tracking of these annual funds - the Change Proposal (CP) acts as that 'parent' XRN. Draw down on the £100k that has been approved will be done via a forthcoming Business Evaluation Report (BER). The CP will eventually be closed down via a Change Completion Report (CCR) at the end of the financial year.
Sponsor Representative | Xoserve
Change Description
PAC has identified a list of 'user stories' it wants the CDSP to develop - these user stories include those that were raised in the last financial year (listed in XRN4876 - the parent XRN for the last financial year's PAC budget). Those user stories have been carried forward as 'requirements' for the current financial year. As new user stories are identified, these will be included in the PAC backlog.
Change Type | Non regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X
Each DSC Constituency funds the annual DSC Change Budget based on approved % splits introduced in the annual business plan | 

## Slide 13: XRN5329 Amendments to V16 of the Service Description Table
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Sponsor Representative | Xoserve
Change Description
This change is to seek approval for the inclusion of two new service lines to the DSC Service Description Table and to propose an amendment to an existing service line. Proposed New Service Lines Proposed Service Line amendment Existing Line :-
Change Type | Documentation
Priority Score | N/A
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 
Information Only – CoMC will vote to be implemented in March meeting | 
Service line ref | Description
SS SA22 87 | To grant Customers access to the Data Discovery Platform that will enable access to real time data and key metrics to provide insight pertaining to their portfolio
DS-CS SA6 - 22 | Maintenance of a Shipper Affiliate relationship table for the purpose of validating AQ corrections using reason code 3 Associated XRN 5237 in support of Mod 736
Service line ref | Proposed amendment
DS-CS SA18 – 03 | Publication of a report identifying those users of the Data Permissions Matrix suppliers which have a Third Party Services agreement in place with the CDSP for the disclosure of Supply Point Premises Data as contemplated by V 5.18.3 5.5.2(k)

## Slide 14: 4.2 Change Proposals – Post Solution Review for Approval
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement SoLR Directions
XRN5200 Shipper Pack Transition to Data Discovery Platform
XRN5218 – Modification 0710 - CDSP provision of Class 1 read service

## Slide 15: XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement SoLR Directions
Proposed Release Link to Change Proposal Change Pak Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Not yet scheduled Link to CP Link to Change Pack ref: 2768.1 – RT - PO Voting: Shipper, DNO, IGT, NTS | N/A User views requested | NGN |  |  | X | NGN Opposes this change and we defer comment on this proposed solution until we receive clarity from Ofgem. We would also like to highlight the post meeting notes from the Feb Switching Programme design forum state: SoLR - Kishan Nundloll (Ofgem) provided an update on SoLR. It was noted that CR-D025 Changes to support enhanced SoLR arrangements has been withdrawn and any future SoLR developments/updates will be brought through the Design Forum.
 |  | EDF | X Analysis only |  |  | To be able to successfully migrate customers to our systems, we would still need to undertake a mass change of shipper/supply event post Supplier ID reassignment. Therefore we would prefer to retain the existing SoLR process or be able to suggest that is the process that we would prefer to use as part of any SoLR bid and not to be reassigned the supplier ID, otherwise on the gas side this could be seen to give an advantage to those Suppliers on SoLR event who use same Shipper or use the same software as the failing company. With the implementation of a more innovative and flexible CSS, it is our expectation that as an industry we should be able to do much higher volume of SoLR CoS events in much shorter 2 timelines and therefore believe that the proposal for reassignment is not necessary. As an industry, we need to ensure that any SoLR events can be managed by flexing DCC/CSS central systems accordingly. See Change Pack for full response
 |  | W&W |  |  | X | An alternative would be to create a legal entity id and present data with the legal entity id and the legal entity industry role in place of Transporter Mpid, Shipper MPid, Supplier Mpid. We expect that this solution would be expensive and far reaching. See Change Pack for full response
 |  | SGN |  |  | X | SGN have previously indicated that we believe the proposal to re-use the Supplier Short Code in the event of a SoLR as a material risk to our business. We are mindful that CR-D025 has been withdrawn and Ofgem have indicated future developments will be brought through the Design Forum. This would indicate that the current solution options should await further direction before being progressed.
 |  | SSE |  |  | X | The Faster Switching arrangements will allow sites to be taken on quickly by the new supplier using normal industry processes. Therefore, it seems unreasonable to request that shippers build this potentially very difficult functionality into their systems and processes at significant cost when it is intended only to be used for SOLRs, i.e., infrequently or not at all. See Change Pack for full response
 |  |  | X With comment |  |  | Private Response - Support assuming comments are reflected.
 |  | Centrica |  | X |  | It is our opinion that the option to reassign the MPID should be available for any supplier that wishes to use it, but the solution should not disallow a ‘bulk CoS’ for the impacted MPRNs if that is what the supplier wishes to do. The solution should focus on the customer and meeting our needs. We also still need to address the issue of MPIDs that are shared between Supplier and Shippers, the fact that they are 2 different parties should mean 2 different parties can have the same MPID as is the case for electricity.

## Slide 16: XRN5200 Shipper Pack Transition to Data Discovery Platform
Proposed Release Link to Change Proposal Change Pak Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Adhoc Link to CP Link to Change Pack ref: 2768.2 - RT - PO Voting: Shippers High level Solution cost: 4 options at £0 cost Service Area: Service Area 18: Provision of User Reports and Information Funding: 100% Shipper (reapportioned) Service Area 18 is normally split Shipper 34%, NTS 7%, DNO/IGT 59% | DSG preferred Option 3 or 4 | OVO | X |  |  | We are happy to go with the majority decision, but believe that a crossover period between DDP and Shipper Packs could prove useful for comparison
 |  | EDF | X |  |  | We prefer option 3 or 4
 |  | Scottish Power | X |  |  | Solution Options 3 or 4 would be our preferred, however, would be fine with 2 as well if this was majority. I think as long as there is some form of parallel running for these reports, as do think this is needed.
 |  | EON | X |  |  | We support option 1 and prefer to have a single clean cut over to decommission the current Shipper Packs. As the proposers of this change we are happy to go with the majority choice.
 |  | Orsted | X |  |  | Option 4 is our preferred solution as it facilitates utilising DDP for exiting topics & data and moving other data items and topics in the future with sufficient notice to Shippers.
 |  | SSE | X |  |  | Our preference is for option 2, to allow the parallel running of the shipper pack and Data Discovery Platform for a period of time in order to allow parties to get used to the DDP and transition at their own pace from one to the other.
 |  | Centrica | X |  |  | No Preference

## Slide 17: XRN5218 – Modification 0710 - CDSP provision of Class 1 read service
Proposed Release Link to Change Proposal Change Pak Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Adhoc – aiming for 01/06/2021 Link to CP Link to Change Pack ref: 2768.3 - RT - PO Voting: Shipper, DNO, IGT, NTS High level Solution cost: Implementation cost - £30K - £45K Ongoing cost - DMSP charge + £67,000 GBP per annum Service Area: Service Area 1 Manage Supply Point Registration Funding: Implementation cost is proposed 98% DNO, 1% IGT and 1% NTS funded Ongoing cost is 100% Shipper funded | Option 1 | W&W | X |  |  | WWU supports this change, the development should be funded by Transporters and the ongoing costs by Shippers.
 |  | NGN | X |  |  | NGN supports Solution Option 1 and agrees with the implementation date Xoserve are aiming for
 |  | SSE | X |  |  | We agree with the solution proposed. We assume that Xoserve will list the Class 1 read service charges as a distinct separate line item on the invoice, so that this is clearly identifiable for shippers and suppliers.
 |  | Centrica | X |  |  | Do Xoserve have an idea on the amount the “uplift” will be? And will it be the same across all sites? When the contract is novated can we have a view of service standards for our sites? Will we be able to see MPRN and site specifics for example, if a site is lost mid-month are we still charged for the full month? It would be good to understand how the costs can be associated to individual sites. Partially related to Mod 0710, has OFGEM or the industry not set any timescale for ensuring all DMR sites are telemetered? My other concern would be that as/when sites move to telemetered the costs per MPRN that is non-telemetered could increase to the point that they are disproportional.

## Slide 18
Please Note: The implementation dates for each of the Capabilities are subject to change following completion of the respective Capability design activities

## Slide 19: section 5. Design & Delivery

## Slide 20: Design Change Pack
XRN5038 - CDSP to convert Class 2, 3 or 4 Supply Meter Points to Class 1 when G1.6.15 criteria are met (Modification 0691) – Implementation date for approval only
XRN5285 (Mod 730V) - COVID-19 Capacity Retention Process
XRN4922 CSSC Shipper BRD

## Slide 21: XRN5038 - CDSP to convert Class 2, 3 or 4 Supply Meter Points to Class 1 when G1.6.15 criteria are met (Modification 0691) Proposed Implementation Date – For approval March ChMC

## Slide 22: Background
XRN5038 was raised to deliver the changes introduced under UNC Modification 0691S – CDSP to convert Class 2, 3 or 4 Supply Meter Points to Class 1 when G1.6.15 criteria are met.
It proposed to give authority to the CDSP to update Supply Meter Points (SMP) within Class 2, 3 & 4 to Class 1 where the AQ exceeds 58,600,000kWh for the duration set out in UNC G2.3.15 and the Shipper does not take the required action in moving to Class 1 by 20 Supply Point System Business Days (SPSBD) after the existing deadline (2 months after the Class 1 Read Requirements have been met).
As well as the CDSP converting sites to Class 1 in the above scenarios, this change also proposes new Performance Assurance Committee (PAC) report will be provided:
    • SMPs that have been reclassified to Class 1 by the CDSP and the Shipper over the previous 12 months

## Slide 23: Current situation
Modification 0691 was approved by UNC Panel in October and is awaiting an implementation date.
Change Proposal: XRN5038 has followed the DSC change process.
The Solution Change Pack was approved by the January ChMC and the Detailed Design Change Pack was approved by February ChMC.
At the February ChMC, it was requested that the proposed implementation for this change should be agreed at the March ChMC.

## Slide 24: Proposed Implementation Date
The proposed implementation date for XRN5038 is 01 April 2021.
We have liaised with the proposer and legal text provider for Modification 0691 who agreed that the implementation date of the XRN should align with the Modification.
ChMC are asked to approve this implementation date.
  To reconfirm this change is:
  Voting: Shipper, DNO, IGT
  Funding: 100% Shipper
  Service Area 1: Manage Supply Point Registration

## Slide 25
XRN5285 (Mod 730V) - COVID-19 Capacity Retention Process
Functional Changes |  |  |  |  | 
Change Pack ref: 2768.4 – RT - PO Release: Adhoc Voting: Shippers, DNO, NTS Funding: Service Area 7 is split 17% NTS & 83% DNO – Reapportioning for discussion Service Area 7 NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 | NGN |  |  | X | We have several concerns regarding this change. Firstly, when all legal restrictions are lifted, there doesn’t appear to be a hard stop for the rebate applying, Xoserve having the ability to automatically remove the flag. As this change is looking to be implemented potentially 3 months after the modification proposal is approved, life span of this change could be around 6 weeks. This seems a lot of work and therefore cost to industry, for something so limited in time. The charge is using an existing charge type, and there is a risk that other charges can be included on the same invoice. Under UNC should a site be isolated and Xoserve or Transporters become aware it is consuming gas, then they have the right to remove the isolation flag. Please can you advise whether this will include reversing any rebate given when the site was consuming above de minimis quantity. Please can we have clarity that UNC0723 sites are still being chased with the Users for continued confirmation that they are still valid ‘Covid Isolations’. And should UNC0730 be implemented, that sites not part of 0730 will continue to be chased accordingly. See Change Pack for full response
 | W&W |  |  |  | DNs will need notification of any discounts awarded to shippers that will have an affect on LDZ capacity charges, in advance of the invoices being raised. The information provided must be on a shipper level and must include calculation of amounts and periods to which the discount applies. This could be in the form of a monthly report.
 |  |  |  |  | Private Response – Abstained

## Slide 26
XRN4922 CSSC Shipper BRD
Functional Changes |  |  |  |  | 
Change Pack ref: 2769 – RT – PO Release: CSS Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 |  |  |  |  | No responses received as of 25/02/2021
The Change pack closes out on 01/03/2021 and any reps will be added by 03/03/2021

## Slide 27: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 28: Standalone Change Documents for Approval (BER, CCR, EQR)
CCR for XRN5206 TPI/PCW Access
CCR for XRN5225 Minor Release Drop 8

## Slide 29: June 2021 Major Release

## Slide 30
BER for XRN5253 June 21 Release

## Slide 31: XRN5253 - June 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build execution completed to plan in January System Testing execution completed in February User Acceptance Testing (UAT) execution to commence in March 2021 Regression Test & Performance Test prep in progress Implementation Approach Approved. Go Live date pending final confirmation with ChMC Proposed Go Live date currently under review as there is a risk of no contingency date due to Gemini code freeze commencing on 28th June. Project team are in discussions to agree a feasible contingency date. Post Implementation Support (PIS) period still under discussion with Operation teams to ensure it is sufficient and covers what is required |  |  | 
Risks and Issues | Risk: There is a risk that there is no contingency date for June 21 implementation (26th June 2021) because of no availability of a contingency date as Gemini code freeze begins on 28th June 2021 leading to a delay in Cutover Mitigation: Currently under discussion |  |  | 
Cost | Cost RAG status will return to green on approval of updated BER inclusive of AUGE costs (to be presented in March ChMC) BER Approved at ChMC in December, revised BER to be issued to include AUGE set up costs incorrectly omitted from previous BER. |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level for future stages. Resources in place to support agreed test timescales. |  |  | 
Update as 24th February 2021

## Slide 32: June 2020 Major Release

## Slide 33: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: The new service is being utilised by Networks however usage is limited due to the limited amount of data held in UK Link. Currently there is circa 8.99 million meter points in UK Link and the team are monitoring usage. Please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Scope Variations: XRN4850 - Report automation integration into DDP Go Live completed on 24th February 2021 XRN4850 UK Link Portal changes – Change implemented in Portal on 13th February 2021 to allow special characters, increase character limits in text and email and display character number count. Project Closedown: Following completion of Post Implementation Support project closedown is in progress on track for end of March 2021 |  |  | 
Risks and Issues | N/A |  |  | 
Cost | Costs have been finalised in the CCR which has been approved by Change Management |  |  | 
Resources | No resource issues identified for the remainder of the project |  |  | 
Updates as of the 24th February 2021

## Slide 34: November 2020 Major Release

## Slide 35: XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS PIS is complete for XRN4871b, XRN5014 and XRN4897/99 Daily Cleanse Update regarding the approved change requests: XRN4801 Additional Information in DES - Issue identified with active read indicator displaying incorrectly for a small volume of OPNX reads. Fix to be implemented 06/03/21 due to an extra requirement of additional PIS and a code and data environment re-fresh. Plan has been approved and re-baselined. The remaining functionality of XRN4801 is working as expected. XRN4897/99 Historical Cleanse job. Build is currently in progress and the change is on track to be implemented on 27/03/21. The historical cleanse job will then run for a period of 10 weeks PIS. Return to Green N/A |  |  | 
Risks and Issues | Issue: XRN4897/99 Historical Cleanse Change Request needs to be completed to exit PIS Issue: XRN4801 Active Read Indicator – Additional Performance Testing and re-arranged code and data refresh have delayed the implementation by 3 weeks Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – risk probability being understood. Return to Green: Deliver the two approved change requests for XRN4801 and XRN4897/99 |  |  | 
Cost | Additional funds of £34k approved on 29/01/21 to cover the XRN4897/99 Historical Cleanse change request Original BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 |  |  | 
Resources | SME & Tech Ops resources approved ft deliver remaining change requests Return to Green N/A |  |  | 
Updates as of the 24th February2020

## Slide 36: November 2021 Major Release

## Slide 37: XRN5289 - November 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design workshop plan has commenced XRN4941, XRN5142 and XRN5007 have completed its design awaiting final document approvals CSSC/CSS impact assessment timeline and requirements is approved Plans to bring 3 changes change packs for approval 1 month earlier than originally planned High Level Design has been approved by Design Review Board (DRB) |  |  | 
Risks and Issues | RISK – Not a full 6 months before implementation date for design change pack approval Requesting E-ChMC on the 5th May for the remaining changes RISK - XRN5142 - Unknown plans from DCC on their plan of delivery and design Regular touch points with DCC to understand their plan and design have been set up RISK - XRN4941 – CR raised to change the definition of the Operational Smart Meter to only consider a DCC Service Flag of active. Current design considers meter mechanism code and installing Supplier – this has been shared with DSG – please find presentation that was submitted to DSG for further information in the appendix slide. – delay to the timeline for design for this change only Xoserve to follow the internal change control process |  |  | 
Cost | EQR approved by ChMC on the 13th January 2021 |  |  | 
Resources | Resource Forecasts and Plans until the end of design have been defined and approved SME resource has been provided for design, approach for technical SME resource to support design has been agreed |  |  | 
Updated as of 24th February 2021

## Slide 38: XRN5294 - Minor Release Drop 9 Update

## Slide 39: XRN5294 - Minor Release Drop 9 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 2 changes for Minor Release Drop 9 to be implemented. The implementation date is planned for 20th March 21: XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​ XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance Acceptance Testing has been completed. Regression Testing in progress on track Preparation has started for Implementation on 20th March 2021 |  |  | 
Risks and Issues | No risks or issues to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 24th February 2021

## Slide 40: Gemini Horizon Plan

## Slide 41: Section 6: Non-DSC Change Budget Impacting Programmes

## Slide 42: 6.1 CSSC Programme Dashboard
March 2021

## Slide 43
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme is now at Amber-Green status. SIT Functional testing has completed with milestone approval being requested at this month’s Delivery Group. There are very few defects remaining but all within the allowable tolerance to exit this phase. All other test phases continue to track to plan The Switching Programme has introduced a Change Freeze which commenced on 19th February. Only Go-live critical changes will be considered for implementation from this point onwards. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: External activities have progressed with the Transition Test Plan v0.1 and Transition Plan/Runbook iteration 3 and Live Rehearsal Scenarios and Data requirements are all out for industry review. Internal planning activities continue alongside engagement with the SI. Extraordinary DSG sessions have introduced Transition as a dedicated topic and will remain of the key focus areas in the months to come. SoLR; An Ofgem policy decision has been made to implement their favoured SoLR solution. This solution will see supplier short codes transferring to the recipients portfolios in the event of a supplier of last resort process instigation. Change Packs are currently out for industry representation. This process did not form part of the Switching Programme requirements, however Ofgem did include as part of the DB4 consultation. Internal Testing: UAT Assurance is currently tracking to plan. SIT integration continues for Programme CR deliveries. Defect rate continues to be low. Data Migration: DM NF Cycle 2 commenced on time, however defects have been encountered for this phase and the SI are monitoring closely to ensure that milestone completion date is met. Market Trials: Xoserve CR to remove Market Trials from the Switching Programme MAD Log is currently out for industry impact analysis. This is expected to be tabled the Ofgem Change Advisory Group within the next week or so. |  |  |  | DMT NFR: Continue test execution Internal Test: Continue SIT & UAT assurance DES:& Secondary APIs Continue development and system test activities. Transition: Continue Live Rehearsal & Transition planning SoLR: Detailed Design to commence MAP C: Detailed Design in progress Market Trials: Closure following Switching Programme approval REC: Continue REC schedule review as per Ofgem timelines
Programme Update

## Slide 44: 6.2 UK Link Cloud Programme
March 2021

## Slide 45: UK Link Cloud Programme
The primary objective of the UK Link Roadmap is to ensure this critical data processing platform is optimized and sustain to ensure continued service to the UK Gas Sector.
The near term drivers for this roadmap are to:
Reduce operational risk – Ensure that all components are within mainstream vendor support, improve UK Link Infosec footing
Reliability at scale – Maintain & improve the stability of service that we deliver and its ability to scale
Pace of change delivery & adoption - Organise to allow multiple paces of change and reduce impact on customer systems
The longer terms drivers for the roadmap span a delivery from now through to 2023/24.
To deliver the near term drivers immediate action was required to commence this programme of work. Following approval of our BP21 submission for the UKL Roadmap an internal delivery Programme has commenced and the first delivery incorporates a core UK Link Platform Migration. This migration includes:
Move to Microsoft Azure
Move to SQL Server
New UK Link Portal

## Slide 46: UK Link Cloud Programme
This programme has been split into a number workstreams to deliver individual components
Each workstream is currently in high level design and we will continue to talk to you and keep you informed as we work through this design phase and understand our delivery route and Go Live date
We know there are no functional impacts, therefore no build requirements for your systems. We have a good understanding of the browser versions you are using as we have asked you to provide this information through conversations for the CSSC Programme but will appreciate you providing this detail if you haven’t already
A password reset for the new UK Link Portal will be required at Go Live but we will keep you informed and explain what this will look like as we move towards this date
Security is a very key consideration and we will be accessing as we work through design
We also know that an outage will be required at implementation. As we move towards this date I will be keeping you informed and will ensure UK Link manual governance is followed to ensure the appropriate outage notifications are provided within the governance timescales

## Slide 47: 6.3 CMS Rebuild Update
March Updates
Jo Williams

## Slide 48: CMS Rebuild - Progress to date
Summary of progress to date
CMS is a dated system which is coming to end of life support, rather than a lift and shift of current processes the project team wanted to understand the following from the actual users of CMS perspective: What are their current processes and activities What are their current pain points What would their ideal version of the process be All initial requirement workshops have now been completed and the ideal “To Be” Workshops are now underway, following feedback received from the first session the structure has been altered to continue to get the best value out of the sessions. The Project Team are seeing a big increase in the number of attendees for each workshop, which is a great sign and this has led to additional requirements being identified All Workshop outputs have been published here: https://www.xoserve.com/systems/contact-management-service/contact-management-service-cms-rebuild-project/ Potential Suppliers are being engaged to understand high level requirements to obtain figures and timescales for High Level Solution Options
Key Milestones | Due
Initial Workshops Completed | 22/01/2021
To Be Workshops Commence | 08/02/2021
HLSO – Target Date | April
Next Steps
Continue to refine the requirements as we develop the Ideal “To Be” Models Continue the Governance process to seek approval of design and solution at CoMC ChMC DSG Consider potential delivery methods along with any dependencies on other systems, it maybe that we have a two step delivery consisting of; front end for customers and then the UKLink integration post CSSC Approval of processes to remain in scope of CMS

## Slide 49: CMS Governance Process
CMS Rebuild Project
Capture
Design
Build
Test
Implement
Dedicated Workshops for “As Is” and the “To be”- Customers registered for events and ratify the requirements in the ideal state
Updates to DSG, ChMC and CoMC
HLSO and Delivery Methodology Agreed at:
DSG
ChMC
CoMC
Dedicated CMS DSG Meetings to agree detailed design
Approvals at ChMC, CoMC as required
Change Governance will be followed e.g. Change Packs
Dedicated CMS DSG Meetings to ensure customers have visibility of Project progress and testing
Slots at ChMC for Updates and Change Packs
Slots at CoMC for Updates and Financial tracking

## Slide 50: Section 7: Any Other Business

## Slide 51: 7.1 Post Mercury Change Process
Verbal update to be presented by Emma Smith

## Slide 52: APPENDIX

## Slide 53
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
CHG0031092 | Gemini | 15/05/2021 | 03:15 | 15/05/2021 | 08:30 | Gemini Disaster Recovery Test 2021 This is an annual activity to confirm Gemini services can be migrated to a secondary data centre location should there be a catastrophic failure within the primary data centre. During this phase of the test Gemini services will failover from the primary site to the secondary site. The activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 10/02/2021
CHG0031092 | Gemini | 16/05/2021 | 03:00 | 16/05/2021 | 08:30 | Gemini Disaster Recovery Test 2021 During this phase of the test Gemini services will failback from the secondary site to the primary site. Again the activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. NOTE: Contingency dates for these activities are 29th / 30th May | 10/02/2021

## Slide 54: XRN5253 - June 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build execution completed to plan in January System Testing execution completed in February User Acceptance Testing (UAT) execution to commence in March 2021 Regression Test & Performance Test prep in progress Implementation Approach Approved. Go Live date pending final confirmation with ChMC Proposed Go Live date currently under review as there is a risk of no contingency date due to Gemini code freeze commencing on 28th June. Project team are in discussions to agree a feasible contingency date. Post Implementation Support (PIS) period still under discussion with Operation teams to ensure it is sufficient and covers what is required |  |  | 
Risks and Issues | Risk: There is a risk that there is no contingency date for June 21 implementation (26th June 2021) because of no availability of a contingency date as Gemini code freeze begins on 28th June 2021 leading to a delay in Cutover Mitigation: Currently under discussion |  |  | 
Cost | Cost RAG status will return to green on approval of updated BER inclusive of AUGE costs (to be presented in March ChMC) BER Approved at ChMC in December, revised BER to be issued to include AUGE set up costs incorrectly omitted from previous BER. |  |  | 
Resources | Resource Forecasts and Plans have been defined at a high level for future stages. Resources in place to support agreed test timescales. |  |  | 
Update as 24th February 2021

## Slide 55: XRN5253 – Proposed June 21 Proposed High Level Plan
Update as 24th February 2021
TODAY

## Slide 56: XRN5253 - June 21 Release Summary
In Scope
XRN5093 - MOD0711 – Update of AUG Table to reflect new EUC bands
De-Scoped at Extraordinary Change Management Committee on 26th October 2020
XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments
De-Scoped at Change Management Committee on 11th November 2020
XRN4941 - MOD0692 - Auto updates to meter read frequency
June 21 Release now consists of 1 change.

## Slide 57: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: The new service is being utilised by Networks however usage is limited due to the limited amount of data held in UK Link. Currently there is circa 8.99 million meter points in UK Link and the team are monitoring usage. Please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Scope Variations: XRN4850 - Report automation integration into DDP Go Live completed on 24th February 2021 XRN4850 UK Link Portal changes – Change implemented in Portal on 13th February 2021 to allow special characters, increase character limits in text and email and display character number count. Project Closedown: Following completion of Post Implementation Support project closedown is in progress on track for end of March 2021 |  |  | 
Risks and Issues | N/A |  |  | 
Cost | Costs have been finalised in the CCR which has been approved by Change Management |  |  | 
Resources | No resource issues identified for the remainder of the project |  |  | 
Updates as of the 24th February 2021

## Slide 58: XRN4996 June 20 Release Summary
June 20 Release consists of 7 changes, Implementation was completed for June 20:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 - Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters (UKLink file formats, new service to follow)
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining change requests. Descoped at ChMC on 8th January 2020
** Descoped at eChMC on 22nd November 2019
*** Added to scope (revised scope from original)
Updates as of the 24th February 2021

## Slide 59: XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS PIS is complete for XRN4871b, XRN5014 and XRN4897/99 Daily Cleanse Update regarding the approved change requests: XRN4801 Additional Information in DES - Issue identified with active read indicator displaying incorrectly for a small volume of OPNX reads. Fix to be implemented 06/03/21 due to an extra requirement of additional PIS and a code and data environment re-fresh. Plan has been approved and re-baselined. The remaining functionality of XRN4801 is working as expected. XRN4897/99 Historical Cleanse job. Build is currently in progress and the change is on track to be implemented on 27/03/21. The historical cleanse job will then run for a period of 10 weeks PIS. Return to Green N/A |  |  | 
Risks and Issues | Issue: XRN4897/99 Historical Cleanse Change Request needs to be completed to exit PIS Issue: XRN4801 Active Read Indicator – Additional Performance Testing and re-arranged code and data refresh have delayed the implementation by 3 weeks Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – risk probability being understood. Return to Green: Deliver the two approved change requests for XRN4801 and XRN4897/99 |  |  | 
Cost | Additional funds of £34k approved on 29/01/21 to cover the XRN4897/99 Historical Cleanse change request Original BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 |  |  | 
Resources | SME & Tech Ops resources approved ft deliver remaining change requests Return to Green N/A |  |  | 
Updates as of the 24th February2020

## Slide 60: XRN4897/99 Historical Cleanse Change Request Timeline and Progress
Updates as of the 24th February 2020
Note: Implementation will be on 27/03/21 and PIS will run for 10 weeks to complete the historical cleanse exercise
XRN4801 Active Read Indicator Change Request Timeline and Progress
Note: Implementation will be on 06/03/21 and PIS will run until 12/03/21

## Slide 61
In Scope
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 5 changes. Implementation was in November 2020
XRN5110 - Nov 20 Scope
Updates as of the 24th February 2020

## Slide 62: XRN5289 - November 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design workshop plan has commenced XRN4941, XRN5142 and XRN5007 have completed its design awaiting final document approvals CSSC/CSS impact assessment timeline and requirements is approved Plans to bring 3 changes change packs for approval 1 month earlier than originally planned High Level Design has been approved by Design Review Board (DRB) |  |  | 
Risks and Issues | RISK – Not a full 6 months before implementation date for design change pack approval Requesting E-ChMC on the 5th May for the remaining changes RISK - XRN5142 - Unknown plans from DCC on their plan of delivery and design Regular touch points with DCC to understand their plan and design have been set up RISK - XRN4941 – CR raised to change the definition of the Operational Smart Meter to only consider a DCC Service Flag of active. Current design considers meter mechanism code and installing Supplier – this has been shared with DSG – please find presentation that was submitted to DSG for further information in the appendix slide. – delay to the timeline for design for this change only Xoserve to follow the internal change control process |  |  | 
Cost | EQR approved by ChMC on the 13th January 2021 |  |  | 
Resources | Resource Forecasts and Plans until the end of design have been defined and approved SME resource has been provided for design, approach for technical SME resource to support design has been agreed |  |  | 
Updated as of 24th February 2021

## Slide 63: XRN5289 – November 21 High-Level Plan
Updated as of 24th February 2021

## Slide 64
For Information Only
Presentation to DSG on XRN4941 Operational Smart Meter Criteria on the 22nd February 2021
Updated as of 24th February 2021

## Slide 65: XRN5289 - November 21 Release Summary
In Scope
XRN4941 - MOD0692 - Auto updates to meter read frequency
XRN5007 - Enhancement to reconciliation process where prevailing volume is zero
XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes
XRN5091 - Deferral of creation of Class change reads at transfer of ownership
XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC
XRN5180 - Inner tolerance validation for replacement reads and read insertions
Out of Scope
Approved to removed from 13th January 21 ChMC
XRN5186* MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs
XRN5187* MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs
The initial scope of the November 2021 Major Release consists of 8 changes
Updated as of 24th February 2021

## Slide 66: XRN5294 - Minor Release Drop 9 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 2 changes for Minor Release Drop 9 to be implemented. The implementation date is planned for 20th March 21: XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​ XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance Acceptance Testing has been completed. Regression Testing in progress on track Preparation has started for Implementation on 20th March 2021 |  |  | 
Risks and Issues | No risks or issues to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 24th February 2021

## Slide 67: XRN5294 - Minor Release Drop 9 Timelines
Updated as of 24th February 2021
TODAY

## Slide 68: XRN5294 - Minor Release 9 Summary
There are 2 changes for Minor Release 9 to be implemented. The proposed implementation date is 20th March 21:
  XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​
  XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance
Updated as of 24th February 2021

## Slide 69: CSSC Programme Dashboard
March 2021

## Slide 70
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme is now at Amber-Green status. SIT Functional testing has completed with milestone approval being requested at this month’s Delivery Group. There are very few defects remaining but all within the allowable tolerance to exit this phase. All other test phases continue to track to plan The Switching Programme has introduced a Change Freeze which commenced on 19th February. Only Go-live critical changes will be considered for implementation from this point onwards. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: External activities have progressed with the Transition Test Plan v0.1 and Transition Plan/Runbook iteration 3 and Live Rehearsal Scenarios and Data requirements are all out for industry review. Internal planning activities continue alongside engagement with the SI. Extraordinary DSG sessions have introduced Transition as a dedicated topic and will remain of the key focus areas in the months to come. SoLR; An Ofgem policy decision has been made to implement their favoured SoLR solution. This solution will see supplier short codes transferring to the recipients portfolios in the event of a supplier of last resort process instigation. Change Packs are currently out for industry representation. This process did not form part of the Switching Programme requirements, however Ofgem did include as part of the DB4 consultation. Internal Testing: UAT Assurance is currently tracking to plan. SIT integration continues for Programme CR deliveries. Defect rate continues to be low. Data Migration: DM NF Cycle 2 commenced on time, however defects have been encountered for this phase and the SI are monitoring closely to ensure that milestone completion date is met. Market Trials: Xoserve CR to remove Market Trials from the Switching Programme MAD Log is currently out for industry impact analysis. This is expected to be tabled the Ofgem Change Advisory Group within the next week or so. |  |  |  | DMT NFR: Continue test execution Internal Test: Continue SIT & UAT assurance DES:& Secondary APIs Continue development and system test activities. Transition: Continue Live Rehearsal & Transition planning SoLR: Detailed Design to commence MAP C: Detailed Design in progress Market Trials: Closure following Switching Programme approval REC: Continue REC schedule review as per Ofgem timelines
Programme Update

## Slide 71: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall green. We have seen resource constraints which has now been resolved. Internal & External SIT support in progress. On track to delivery to internal testing ahead of external programme testing phases.
 |  | Testing | The overall status remains Green. Planning underway for all upcoming test phases such as UEPT, E2E, OT Internal testing is tracking to plan
 |  | Service Management | Xoserve have submitted our requirements traceability matrix ahead of the Service Design assurance activity undertaken by the SI. A CR is anticipated to be raised to align Switching Programm SLAs to match Xoserve’s existing response times. Our existing resolution times are more stringent than the Programme’s hence needs no change.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green. Planning underway to undertake a connected Gas Day testing with UK Link.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess and deliver Switching Programme changes raised through the last few months whilst supporting test phases.

## Slide 72: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC consultation continues with Xoserve actively engaged in relevant RDUG meetings as well as reviewing REC schedules
 |  | Data Migration & Provision | DM NF Cycle 2 commenced on time, however defects have been encountered for this phase and the SI are monitoring closely to ensure that milestone completion date is met.
 |  | Market Trials | The CR to remove Market Trials milestones from the Switching Programme Plan has been raised and is currently undergoing industry-wide impact assessments. Amber in the PoaP reflects the fact that Market Trials is imminently being de-scoped
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan.
 |  | MAP C | Detailed Design has commenced and is progressing to plan.
 |  | SoLR | Following Ofgem policy decision, workstream to commence this month

## Slide 73: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
64569 |  | Data | There is a risk that the environment for DM live rehearsal will not be ready in time because of late running DM NF, and insufficient time allowed on the CSSIP for a full refresh to a new data copy (4 weeks) leading to late start to smoke test and test prep (TE700) | Clarity required from SI on what is or isn't needed for the various sub phases of live rehearsal | DM NF due to complete 02/04. CSSIP shows environment to be made available for smoke testing 1/4, with smoke testing for Xoserve starting on 12/04. The Xoserve UK Link environment will not be available until 3/5 at the earliest. Confirmation required form SI that early smoke tests are for the API layer only, and no further smoke tests will be schedule before May | 02/04/21
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | Continues to be monitored until Tranche 1 of E2E is complete | 01/03/21
64158 |  | Programme | There is a risk that that the Operational Choreography CR that is in progress may be approved because it might be deemed necessary by the central programme leading to further plan considerations (at both the central and individual PUI's plans) and cost implications to Xoserve | This has been raised with SI/DCC & Ofgem. This is being tracked collectively via the MAD log actions. Should this CR be approved, this action will be addressed with central bodies | CR has now been issued and is undergoing PIA | 01/03/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Lankmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Current understanding is that SoLR events are unlikely to occur during the Go-live range. This is on the Ofgem risk register as well. Will be monitored and await formal confirmation of whether or not this is an accepted risk | 30/04/21

## Slide 74: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
64695 |  | Data | There is a risk that Live rehearsal and transition test artefacts may not be reviewed in the detail required because of late delivery by the SI leading to review of live rehearsal artefacts crashing into transition artefact reviews, and rushed review missing important issues | Check and review with the teams, report any issues | We currently have 5 test artefacts for review this week for live rehearsal and transition - this is too many to guarantee a thorough review. | 26/02/21
64642 |  | Service Management | There is a risk that the CSS implementation plan does not capture all Service Management activities because of DCC and SI requesting information or completion of documents at the last minute or not currently within scope, I.e recent Service Design Assurance exercise leading to additional time, and therefore impact and cost on CSS staff, and potentially also changing of scope and requirements. | Any concerns to be raised with SI and DCC and CSSC Management team | New Risk - Any concerns to be raised with SI and DCC and CSSC Management team | 31/12/21
64572 |  | Data | There is a risk that Xoserve will be expected to complete Live rehearsal preparation in a very reduced timeframe because of delays in completion / approval of the LR Test Plan document, with knock on impacts to scenarios, data and scripting leading to poor quality / incomplete preparation, or delays to start of live rehearsal testing | Check and review with the teams, report any issues | LR Test plan was due for approval 01/12/20 and has not yet been completed. | 26/03/21
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until Tranche 1 of E2E is complete | 01/03/21
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | This was tabled at the Design Forum on 25/01 and discussed. Xoserve will be sending through our feedback (previously shared with DCC) to Ofgem. | 26/02/21

## Slide 75
High Level Plan

## Slide 76: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
MAD Log Changes for UIT Environment Verification | CR-D057 | £0.00 | 25/01/2021 | Pending PIA
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | £0.00 | 25/01/2021 | Pending PIA
Changes to Support Energy Company Data | CR-D059 | £25,500.00 | 25/01/2021 | Pending SI Response
Operational Choreography Detection 0.5 | CR-D060 | £538,625.00 | 25/01/2021 | Pending PIA
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Pending PIA

## Slide 77: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Not Received
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | £0.00 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | £0.00 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 | £0.00 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | £0.00 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | £0.00 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Removal of Transition Stage 1 Delta files from the Data Migration Solution | CR-D062 | £108,990.00 | 27/01/2021 | On Hold
Uplift to SMS CoCo | CR-D063 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact