## Slide 1: XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS PIS is complete for XRN4871b, XRN5014 and XRN4897/99 Daily Cleanse Update regarding the approved change requests: XRN4801 Additional Information in DES - Issue identified with active read indicator displaying incorrectly for a small volume of OPNX reads. Fix to be implemented 06/03/21 due to an extra requirement of additional PIS and a code and data environment re-fresh. Plan has been approved and re-baselined. The remaining functionality of XRN4801 is working as expected. XRN4897/99 Historical Cleanse job. Build is currently in progress and the change is on track to be implemented on 27/03/21. The historical cleanse job will then run for a period of 10 weeks PIS. Return to Green N/A |  |  | 
Risks and Issues | Issue: XRN4897/99 Historical Cleanse Change Request needs to be completed to exit PIS Issue: XRN4801 Active Read Indicator – Additional Performance Testing and re-arranged code and data refresh have delayed the implementation by 3 weeks Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – risk probability being understood. Return to Green: Deliver the two approved change requests for XRN4801 and XRN4897/99 |  |  | 
Cost | Additional funds of £34k approved on 29/01/21 to cover the XRN4897/99 Historical Cleanse change request Original BER approved - 10/06/20 Full Business Case approved XEC – 23/06/20 |  |  | 
Resources | SME & Tech Ops resources approved ft deliver remaining change requests Return to Green N/A |  |  | 
Updates as of the 24th February2020

## Slide 2: XRN4897/99 Historical Cleanse Change Request Timeline and Progress
Updates as of the 24th February2020
Note: Implementation will be on 27/03/21 and PIS will run for 10 weeks to complete the historical cleanse exercise
XRN4801 Active Read Indicator Change Request Timeline and Progress
Note: Implementation will be on 06/03/21 and PIS will run until 12/03/21

## Slide 3
In Scope
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 5 changes. Implementation was in November 2020
XRN5110 - Nov 20 Scope