## Slide 1: 2.2 – Change Pipeline

## Slide 2: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Change Development
| Capture | Initial Review | Pre-capture | Solution Consultation
Total | 26 | 3 | 18 | 2
Chart: Delivery Pipeline
| Ready for delivery | Standalone | CSSC | Jun 21 | Nov 21 | Standalone | Awaiting Delivery | In Delivery
Total | 3 | 1 | 4 | 1 | 7 | 7
Chart: Changes From Last Period
| New | Rejected by Ofgem | MOD to be implemented | Change Implemented
Total | 3 | 1 | 2 | 3

## Slide 3
2020-2022 DSC Change / MiR Pipeline
 | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Minor Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Major Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standalone Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 2021 (DBTI + PIS/Closedown)
Nov 2021 Analysis / Design
November 2021 Build/Test Implement/PIS
MiR 9
MiR 10
MiR 11
MiR 12
Regression
EXTERNAL(MT/UEPT/E2E/Defect Mgmt)
Planning
Transition
Go Live Range
PIS
Retro
Key:
On Track
Potential Activity
Nov 21 IA
November 2022 Build/Test/Implement/PIS
Nov 2022 Analysis / Design
XRN
5206
5237
XRN
5146
XRN
5038
XRN
5120
XOS CF
PAC
XRN
4780C
BER
CCR
Scope
CCR
CCR
Scope
Scope
CCR
CCR
PAC XRN4876
BER
CCR
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
XRN
52185143
Nov 20 PIS
CCR
XRN
4780C