## Slide 1: CSSC Programme Dashboard
May 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status however we are actively monitoring the COVID-19 situation in India to mitigate any potential impacts on to our suppliers. This risk is also actively being monitored at the Switching Programme level Smoke Testing is complete for DM Live Rehearsal. All preparatory activities are now complete for entry into UEPT . Preparations continue for Operational Testing. However, at the point of writing this, 2 multi-party defects are being progressed. Should testing of these fail, there is a risk to the commencement of UEPT. An ad-hoc implementation group has been planned to discuss if necessary. Xoserve also encountered this defect, which has been fixed and tested internally, awaiting joint-up testing. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: Internal and external preparatory activities continue towards DM Live Rehearsal and Transition test phases.CR-D071 which proposes to de-scope In-Flights from the transitional period is now due for approval on 11th May 2021. Internal detailed workshops have commenced with all key stakeholders. Preparations are underway to create an external facing cutover calling out all key activities for shippers to undertake during the various phases. Governance planning will commence following CR-D071 approval. An open question exists with the Switching Programme to understand the catch-up processing approach. This will need to be planned in both the cutover plan and potentially within UNC governance. SoLR; Discussions continue with Ofgem. Internal Testing: Programme change requests continue to be progressed through internal testing in line with the Switching Programme release cycles and/or milestones. Data Migration: REL cycle 4 data work has completed and has been delivered 1 week early. A request has been received for Cycle 5 (non-rel) Analysis reports due for delivery on July. Market Trials: The CR to remove Market Trials has been approved by the Switching Programme. A support group has been set up provide support, information and set up in readiness for E2E Business Change: Internal knowledge transfer sessions continue. Target Operating Model activitiies are on track |  |  |  | Live Rehearsal: Smoke testing complete Internal Test: Progress CR testing and any relevant regression tests DES:& Secondary APIs Continue development and system test activities. Transition: Continue Live Rehearsal & Transition planning SoLR: Discussions continue MAP C: Shipper Change Pack out for reps. MAMCOP change pack due for release REC: Continue REC schedule review as per Ofgem timelines Business Change: Continue awareness and knowledge transfer session
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall Green: Delivery on track for UEPT. Work continues with the SI to load DES User for UEPT/E2E. Logon details will be provided via the SI.
 |  | Testing | The overall status remains Green. Planning complete for all upcoming test phases such as UEPT, E2E, OT. Smoke testing complete for UIT and OT 2 multi-party defects are being progressed at the progarmme level. Should testing of these fail, there is a risk to the commencement of UEPT.
 |  | Service Management | Internal Service Management activities continue to feed into OT and internal OAT A CR has been raised (CR-072) and discussed at Change Advisory Workgroup (CAT) to align Switching Programme SLAs to match Xoserve’s existing response times. Awaiting direction from Ofgem on the next steps.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess, deliver and test Switching Programme changes raised through the last few months

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC consultation continues with Xoserve actively engaged in relevant RDUG meetings as well as reviewing REC schedules
 |  | Data Migration | REL cycle 4 data work has completed and has been delivered 1 week early. A request has been received for Cycle 5 (non-rel) Analysis reports due for delivery on July.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan for all upcoming activities. Awaiting confirmation from DCC and REC around the need for enduring environments post Go-live
 |  | MAP C (XRN-4780C) | Shipper Change Pack is out for reps. MAMCOP Change Pack is due for release.
 |  | SoLR (XRN-5144) | Industry discussion continue with Ofgem

## Slide 5: Key Programme Risks (1/3)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
65114 |  | Transition and Cutover | There is a risk that Live Rehearsal may not reflect the Transition Runbook because of the number of CRs in flight which will impact on the Transition plan leading to Previously untested process change at formal Transition testing | Track progress at SITDG | escalated by parties at SITDG on 20/04. Risk remains | 26/07/21
64158 |  | Programme | There is a risk that that the Operational Choreography CR that is in progress may be approved because it might be deemed necessary by the central programme leading to further plan considerations (at both the central and individual PUI's plans) and cost implications to Xoserve | This has been raised with SI/DCC & Ofgem. This is being tracked collectively via the MAD log actions. Should this CR be approved, this action will be addressed with central bodies | Still awaiting clarity. Ofgem/SI/DCC meeting next week to discuss further | 25/05/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | SI to draft scenarios and walk through / role play to identify impacts | 28/05/21
65122 |  | Transition and Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Xoserve actively monitoring this. | 26/07/21
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | Xoserve will continue to advise customers of cleansing requirements, but can't guarantee compliance | 30/12/22

## Slide 6: Key Programme Risks (2/3)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until Tranche 1 of E2E is complete | 01/08/21
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | Continues to be monitored until Tranche 1 of E2E is complete | 01/08/21
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | CR was presented at Switching Programme CAB on 26/3. | 31/05/21
65127 |  | Transition & Cutover | There is risk that the reconciliation change could impact transition timelines because the reconciliation approach is yet to be finalized leading to leading to downstream impacts. | Work with the SI to agree an approach with minimal impacts | Discussions in progress to agree on an approach with SI. | 26/07/21

## Slide 7
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64642 |  | Service Management | There is a risk that the CSS implementation plan does not capture all Service Management activities because of DCC and SI requesting information or completion of documents at the last minute or not currently within scope, I.e recent Service Design Assurance exercise leading to additional time, and therefore impact and cost on CSS staff, and potentially also changing of scope and requirements. | Any concerns to be raised with SI and DCC and CSSC Management team | Any concerns to be raised with SI and DCC and CSSC Management team. Continued to be monitored | 31/12/21
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | Some reporting is being tested during SM OT testing. We will review this and continue to discuss wider reporting requirements with DCC | 31/08/21
65155 |  | Transition & Cutover | There is risk that reconciliation change may not be deployed in time for DM LR because the reconciliation approach is yet to be finalized leading to an impact during Transitional testing. | Work with the SI to agree an approach with minimal impacts | New risk raised on 27/04 | 26/07/21

## Slide 8
High Level Plan

## Slide 9: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created

## Slide 10: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £25,500.00 | 25/01/2021 | Pending SI Response
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Pending SI Response
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Pending SI Response
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 |  | 19/03/2021 | Pending PIA
Uplift to the CSS Interface Specification | CR-D068 |  | 15/03/2021 | Pending PIA
REL Dissemination to iDNO and DNO | CR-D069 |  | 15/03/2021 | Pending PIA
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Pending SI Response

## Slide 11: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact

## Slide 12: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 |  | On Hold
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact