## Slide 1: CSSC Programme Dashboard
August 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status. Ofgem has shared some Go-live date principles by which they are looking at non-Mondays as potential Go-live dates. This analysis is currently a high focus area whilst we continue to work with Ofgem to provide them with the detail required to baseline their Go-live principles. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: Live Rehearsal Cycle 1 has completed successfully. LR Cycle 2 commences on 30/07, with Transition Testing starting on 06/11. Internal & External Testing: All testing activities are on track. UEPT continues with no major impacts or defects. E2E Testing has commenced successfully. No defects to date. Business Change: Internal activities continue to plan including Target Operating Model. Service Management: Xoserve’s CR-D072 which was aiming to change the Response SLAs have now been through Industry consultation following a position being agreed across all PUIs. This is expected to be approved in August. Data Migration: Planning to begin to support Rel cycle 4b - due Oct. |  |  |  | Live Rehearsal: Commence Cycle 2 Internal Test: Progress CR testing and any relevant regression tests DES:& Secondary APIs Continue Test support Transition: Continue Transition planning MAP C: Delivery continues to plan, build updates will be provided via Nov 21 updates. REC: Continue REC version 3 review complete. Business Change: Continue awareness and knowledge transfer sessions
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall Green: UEPT/E2E support continues specifically around setting up users. No defects raised to date for the external testing phases.
 |  | Testing | The overall status remains Green. UEPT and E2E continues well. At the point of writing this, no significant defects have been seen. Operational Testing with DCC is also progressing well, with no defects raised against Xoserve. This is due to complete in September
 |  | Service Management | Service Management requirements have been clarified with DCC. CR-D072 has been through industry consultation and is expected to be tabled up for approval in August.
 |  | Batch | The overall status is green, with testing support underway for UEPT/E2E activities
 |  | Gemini | The overall status is green
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess, deliver and test Switching Programme changes raised through the last few months

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data Migration | Planning to begin to support Rel cycle 4b - due Oct.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan for all upcoming activities.
 |  | MAP C (XRN-4780C) | Delivery continues to plan, detailed delivery updates will be provided via Nov 21 updates.
 |  | SoLR (XRN-5144) | Engagement continues with Ofgem

## Slide 5: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
65426 |  | Transition & Cutover | There is a risk that the Go Live assumption day of Monday may get changed because various variables (factors) are being looked at by OFGEM leading to rework on Transition plan and related activities. | Internal assessment planned to assess impact of this ask by Ofgem to provide an assessment that covers everything that could impact Xoserve | Internal assessment planned to assess impact of this ask by Ofgem to provide an assessment that covers everything that could impact Xoserve | 31/08/21
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until E2E is complete | 30/11//21
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | CRD072 PIA responses have been favourable and is expected to be tabled for approval in August | 30/08/21
65156 |  | Transition & Cutover | There is risk that the change freeze scope could impact Transition because the scope of Programme Change Freeze from 03/01/22 is not clearly defined leading to impacts during actual Transition | Work with the SI to collectively define the scope of Change Freeze | Internal discussions are ongoing within Ofgem to define the scope of this Change Freeze | 30/08/21

## Slide 6: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Still awaiting confirmation from the SI that Ofgem have accepted this risk. This risk will be accepted once this is formally confirmed | 30/07/21
65122 |  | Transition and Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | The probability of this risk has been reduced. Recon CR is being IA'ed, the CR itself is not impacting Transition activites, however testing considerations need to be understood and assessed | 26/07/21
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | No update on the data cleansing. However have this week challenged CR-D083 - new assumption NCA476 that data providers will be responsible for cleansing any data issues found during transition - as this responsibility is with data owners not data providers | 30/12/22
65176 |  | Transition and Cutover | There is a risk that the Runbook may not be properly tested because schedules to be used across test phases (DM LR / Transition testing) are being developed seperately leading to potential for discrepancies and for insights from one activity being missed by the other | Liaise with the SI to ensure that all plans are aligned. Request early sight of plans to ensure adequate review in advance | Awaiting DM LR plans to compare against the latest issued Transition Test schedule | 01/03/22
65157 |  | Transition & Cutover | There is risk that the catch up processing could impact transition timelines because the catch up processing is not being exercised/rehearsed during Central Programme Transition Testing leading to impacts during actual Transition. | Work with the SI to assess if this activity can be tested in advance of Transition | This was discussed at the SI Transition Group on 16/06. The current expectation is that the approach will be landed in August, which still carries the risk that the held switch processing will not be tested during Transition and was raised by Xoserve at the call | 26/07/21

## Slide 7
High Level Plan

## Slide 8: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | £0.00 | 14/05/2021 | Awaiting Decision
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Awaiting Decision
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Awaiting Decision
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | £76,000.00 | 01/06/2021 | Rejected
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £34,000.00 | 28/06/2021 | Awaiting Decision

## Slide 9: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 10: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Changes to Support Energy Company Data | CR-D059 | 25/01/2021 | On Hold
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 28/06/2021 | On Hold