## Slide 1: UK Link November 21 – Deep Dive on 4780C Change Assurance Report & Return to Green Plan
September 2021

## Slide 2
Project | Date | Change Assurance Type | Overall RAYG
N21 | 10/09/2021 | Deep Dive – 4780C | 
CA1 |  |  | CA2 |  |  | CA3 |  |  | CA4 |  | 
Total 0 | Closed 0 | Open 0 | Total 4 | Closed 2 | Open 2 | Total 5 | Closed 3 | Open 2 | Total 3 | Closed 3 | Open 0
Topic | RAYG | Summary
Business Case |  | This slide calls out key findings from the independent Change Assurance deep dive on XRN4870C. The activity already underway to return this change to a Green RAG status is captured on subsequent slides. At time of slide submission, 8 from the total 12 findings have been closed, with the remaining 4 findings expected to be closed by 15th October This change 4780C is a CSSC change that is being delivered in November 21 release as this needs to be live before CSSC goes live and that there is an obligation on MAMs and CDSP to adhere to in the REC code from 7th November. There are various risks highlighted in this report due to the short timelines and complexity of bringing in this new service by 5th November.. Key Findings After being approved into scope at a relatively late point in the project lifecycle, the project needed to complete several activities in preparation for this change, such as: Scope and solution - Aligning the requirements to the agreed solution, configuration of the new service, completion of elements of design Planning and Customer - testing of the configuration with MAM/MAPs, performing the end to end testing, defining the support model and Customer training activities, Governance - risks/issues could have been highlighted earlier to the governance group to manage the direction of this delivery
Sponsorship |  | 
Governance |  | 
Scope & Solution |  | 
Team & Skills |  | 
Planning |  | 
Customer |  | 
Other - Information Security |  | 
Other – Suppliers |  | 
Other - Testing |  | 
Other – Environments |  | 
Other – People Change & Service Transition |  | 

## Slide 3
4780c Deep Dive - Return to Green Plan
Deep dive requested when 4780c was included in scope of Nov 21 release
12 findings reported as a result of the deep dive produced 10th Sept; with an overall status of Amber
Target resolution dates are to be agreed between project and Change Assurance (CA) team
Progress being monitored by the CA team
All findings are on track to be resolved by the project by 1st October; with the exception of 1 CA3 finding by 15th October
Next steps: A Stage Gate check is planned against Nov-21 at pre implementation w/c 25th October
CA Category | # Reported | Closed by 27th Sept | Remaining | Pending CA Assurance | Latest Closure Date
CA1 | 0 | - | - | - | -
CA2 | 4 | 2 | 2 | - | 1st Oct 21
CA3 | 5 | 3 | 2 | - | 15th Oct 21
CA4 | 3 | 3 | - | - | 1st Oct 21

## Slide 4
Lessons Learned from Key Themes from Deep Dive
Key Theme | Action | Measure | Date
Planning / RAID Management | Greater focus on planning and associated RAID management | Further coaching to be made available to portfolio resources to ensure understanding of critical dependencies and impact to plan | 30th Oct 2021
Scope / Governance | Ensure all changes go through Capture and adhere to governance process | Understanding and articulating risk associated to late inclusion in a release | 30th Oct 2021
Customer Engagement | Customer engagement is appropriately planned | Early engagement with Customers to ensure they can meet their obligations | 30th Oct 2021
3rd Party Engagement | 3rd party supplier engagement is appropriately planned and follows internal procurement process | Early engagement with 3rd parties; to ensure project deliverables are achieved in line with plan | 30th Oct 2021
Dependencies / Solution | Ensure approval of functional / non functional requirements prior to commencing detailed design | Ensuring project plan is in place and dependencies are adhered to | 30th Oct 2021

## Slide 5
Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme
Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects