## Slide 1: Extraordinary Change Management Committee
1st November 2021

## Slide 2: Section 2: N/A

## Slide 3: Section 3: Capture

## Slide 4: New Change Proposals – Initial Review
XRN / Title | Voting |  |  |  | DSC Service Area
 | Shipper | DNO | IGT | NTS | 
XRN5443 – XRN to support Urgent Modification 0788 Minimising the market impacts of ‘Supplier Undertaking’ operation | Y |  |  | Y | TBC

## Slide 5: XRN5443 Urgent Modification 0788 - Minimising the market impacts of ‘Supplier Undertaking’ operation
Voting Parties
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Change Details
Sponsor Representative | National Grid NTS
Problem Statement
Extract from Modification 0788 ‘Why’: Where a Shipper User has been terminated from the UNC, there may be a period where its supply meter points have no Registered User and the supplier is required to pay transportation and energy balancing charges under a Deed of Undertaking pursuant to its supplier license. The Deed of Undertaking recognises that a Supplier will not have established commercial arrangements to secure delivery of gas to the Total System to balance the demand of its consumers. Hence the Energy Balancing Charges payable by the Supplier operate on the assumption of the relevant Supplier delivering no (zero) gas to the Total System on each of the relevant days. Consequently, the Supplier is effectively required to pay for all its consumers’ gas demand at the SMP buy price (‘cashout’).
Change Type | Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | Y
IGT’s | N/A
Change Description
Modification 0788 – Minimising the market impacts of ‘Supplier Undertaking’ operation has been raised and been granted Urgent status by Ofgem. The Modification seeks to provide the ability for Suppliers who are operating under a Deed of Undertaking following the Termination of the Shipper User, to make arrangements with another Shipper User to source additional supplies of gas and make trade nominations to the Terminated Shipper User account to balance that portfolio and mitigate increased costs, until a new ‘Registered User’ is appointed. This Change Proposal has been raised to implement the solution required to deliver what is set out within the Modification. Please note, Modification 0788 is progressing under the Ofgem directed Urgent Timetable. Ultimately the Modification will require an Ofgem decision on approval and implementation however we are proposing that this CP is progressed ahead of the final Ofgem decision to ensure immediate implementation is possible if the Modification is approved.

## Slide 6: 3.2 Change Proposals – Post Solution Review for Approval
XRN5431 - Temporary community access to pre-COVID AQ values for Shippers

## Slide 7: XRN5431 - Temporary community access to pre-COVID AQ values for Shippers
Proposed Release Link to Change Proposal Change Pak Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Ad hoc Link to Change Pack ref: 2918.5 - MT - PO Voting: Shippers Funding: 100% Shipper DSC Service Area: SSA22 29 | Option 1 & Option 2 - Xoserve No preferred option from DSG | Northern Gas |  |  | x | Our below response is a mirrored response to WWU As this is proposed to operate to October 2022 which will be after the proposed go -live for REC 3.0. Following REC 3.0 go-live community view data will be governed by REC not DSC. Therefore there will be a period when release of this data will fall under REC not DSC governance. Our view is that the DSC contract committee can only authorise release of this data up to the day before REC 3.0 go-live and therefore the period for the release of this data should be amended unless corresponding permission for the remaining period is obtained from REC. We approve the implementation date as we have no problem with the implementation date but reject the solution because we do not believe that the DSC contract committee has the authority to approve release of the data until the end of October 2022 but only until the day before REC 3.0 goes live. If the end date was set to the day before REC 3.0 go-live we would support the change.
 |  | Wales and West Utilities |  |  | x | Our understanding is that this change proposes to release data to Shippers relating to a period when they may not have been the Registered User. It is also proposed to operate to October 2022 which will be after the proposed go -live for REC 3.0. Our understanding is that following REC 3.0 go-live community view data will be governed by REC not DSC. Therefore there will be a period when release of this data will fall under REC not DSC governance. Our view is that the DSC contract committee can only authorise release of this data up to the day before REC 3.0 go-live and therefore the period for the release of this data should be amended unless corresponding permission for the remaining period is obtained from REC. We approve the implementation date as we have no problem with the implementation date but reject the solution because we do not believe that the DSC contract committee has the authority to approve release of the data until the end of October 2022 but only until the day before REC 3.0 goes live. If the end date was set to the day before REC 3.0 go-live we would support the change.

## Slide 8: section 4. Design & Delivery

## Slide 9
Impact Assessment to SoLR process of the November 2021 Release

## Slide 10: Overview
During the current crisis within the gas industry, we have been managing the Supplier of Last Resort (SoLR) process in UK Link. In what is a very challenging time for the industry, our primary obligation as CDSP is to ensure that we provide a robust and effective UK Link platform to manage core processes such as switching
Last week the market environment changed considerably with an organisation withdrawing from the shipping market - this is having a significant impact, with c100,000 switches per day being required to support SoLR activity
The November 2021 (N21) project includes changes that impact areas within UK Link that are critical to the SoLR process
As market issues escalated, we undertook an Impact assessment (IA) into the potential risk that the N21 release poses to the current UK Link production service that is supporting the industry SOLR process

## Slide 11: Recommendation
Our recommendation is that the N21 release should be wholly / partly delayed to 22nd & 23rd January 2022 to ensure that potential risks identified in the Impact Assessment do not materialise and lead to failure of the SoLR process at such a critical point in time
The key points from the IA are as follows:
    Some changes have ‘common code’ components with the SoLR process, which introduces potential risk of service interruption
    Some changes in the release have requirements for data cleansing activity which introduces a ‘system load’ risk that could affect SoLR processing volumes
    Changes are being deployed to the file flow (MarketFlow) that supports the SoLR process
    Any change to UK Link at this moment adds potential risk
We recognise that a delay would have impacts to our customers and to code bodies - the recommendation is driven by the need to protect the current switching platform
There are three options for ChMC consideration:
    Deliver full scope as planned
    Delay full release to 22/23 January 2022
    Deliver some change in November and the rest in January

## Slide 12
Risk Factors taken into consideration
 | Description | Risk | Prob | Impact
1 | UK Link is providing a stable processing platform to support the SOLR process and deploying any production changes that have a direct or indirect impact introduces risk. | Extended outage to resolve release issues and potential impact to daily confirmation volumes being processed | L | H
2 | Two of the changes proposed for the release have common code objects (Confirmation workflow and SPC/Contract workflow) that are impacted by the release that support the current SOLR process. | Code issues that require resolution post go-live and slow down or stop SOLR process | L | H
3 | Data cleansing of historical data may take longer than planned introducing additional load to the system | Potential performance impact to BAU processing and reduction in daily confirmation volumes being processed | L | M
4 | Technical and operational resource conflict between SoLR processing and November ’21 implementation | SoLR process may be impacted if post go-live issues encountered that divert resource or increase time to resolve to production issues | M | H
5 | Introducing AMT Marketflow Changes into Production | Issues encountered with AMT changes and any AMT impacts may affect file flows | M | H
6 | Number of BAU defects found in 5072 introduces risk of potential further issues | Testing may not have found all BAU defects and post go-live issues could be encountered | M | M

## Slide 13
Bundling Options Considered
Option | Option | Further Mitigations | Risk 1 | Risk 2 | Risk 3 | Risk 4 | Risk 5 | Risk 6 | Risk Total
1 | Full Release | N/A | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | 12
2 | 4780C | N/A | Remains 2 | Remains 2 | Removed 0 | Reduce 1 | Remains 2 | Removed 0 | 7
3 | 5142 | Deployed on 5/11 – first usage on 6/11 or 8/11 | Remains 2 | Removed 0 | Reduce 1 | Reduce 1 | Remains 2 | Removed 0 | 6
4 | 4780C, 5142 | Deployed on different dates | Remains 2 | Remains 2 | Reduce 1 | Reduce 1 | Remains 2 | Removed 0 | 8
5 | 5142, 4941, 5007, 5072, 5180 | Deployed on different dates | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | 12
6 | 4941, 5007, 5072, 5180 | N/A | Remains 2 | Remains 2 | Reduce 1 | Remains 2 | Removed 0 | Remains 2 | 9
7 | 4780C, 4941, 5007, 5072, 5180 | N/A | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | Remains 2 | 12
Risk Scoring mechanism for comparison reasons – the lower the score the lower risk
Note: XRN 4941 data cleanse is dependent upon completion of data cleanse for XRN 5142 so options 6 and 7 are not viable
The viability of any mitigation options needs to be considered by customers

## Slide 14
Rationale for suggested dates in January
N21 Release 22/1/22
Move to Cloud 12-13/3/22 March
6 week gap
6 week gap
CSSC Data Migration 1/5/22 (earliest)
Later delivery in 2021 (Nov/Dec) would not avoid risk to SoLR, with related switching expected to be ongoing until Christmas
Suggested dates in January pose least risk to dependent projects and future releases in UK Link
In order to protect production services, we plan for a 6 week period between major releases, for the following reasons:
Allows for planned contingency implementation date whilst ensuring an absolute minimum of 4 weeks before the next major release
Allows for monthly cycle of first usage to ensure code and production stability of the deployed release
New production code label is utilised by the next major release as the baseline for Implementation Dress Rehearsal, this ensures that we use the latest available production code label
Any production code defects found post go-live can be fixed, tested and deployed prior to the next major release
Allows other planned sustaining activities to be planned between in between major releases (e.g. For next year - EFT upgrade, FWACV service go live)
Dependent projects ‘moving to right’ would rely on CSS implementation also moving (which we cannot assume)

## Slide 15
Activity since eChMC 25th October
Since the last meeting we have:
Continued to work on the N21 release, according to the current delivery plan
Written to all organisations acceded to DSC (via their stated single point of contact ‘contract manager’) informing them of the options that were presented at eChMC 25th October and the decision to defer vote to 1st November
Issued 2 communications to 662 contacts across 155 different companies via our UK Link Distribution List informing of situation, welcoming feedback on options and highlighting code-body comms on the subject of a potential delay
Presented IA output / recommendation to DSG and assorted ‘constituency’ meetings
Updated xo.com with news story highlighting potential delay
Updated SEC, DCC, REC and UNC parties on current situation and highlighted next steps

## Slide 16
Available deployment options
 | Option | Pros | Cons
1 | Continue as planned to deploy the changes in November 21 | Meets customer expectations Minimises change congestion | Change to UKL at critical time for industry, introducing risk of service disruption
2 | Deliver XRN5142 – (New Allowable Values for DCC Service Flag in DXI File From DCC) as planned in November but defer all other changes to January 2022 | Reduced likelihood of production issues post go-live Enables delivery v SEC requirements | Still represents change to UKL during a critical period Unknown customer effort in potential de-coupling of code changes
3 | Delay the implementation of the full release to the next available window – 22nd January 2022 (contingency 29th January); This uses the assumption that the M2C implementation is moved to early March in order to accommodate the SAP data migration approach. | Gives time for industry situation to subside and any potential change related impacts/issues to be minimised Reduced code de-coupling issue for customers | Unknown industry landscape Increased costs for customer project extensions
RAG represents level of risk to SoLR
A /G
G
R

## Slide 17
Next Steps
In the event of a ‘delay’ decision, the following next steps will be required:
    Notification to relevant code bodies (UNC - XRN 4941, REC - XRN4870c and SEC - XRN5142) of decision taken
    Confirmation of implementation and contingency dates, including outage notification
    Revised Change Pack issued with effective dates of changes
    Revised detailed plan of connectivity testing for MAMs of XRN4780C

## Slide 18: UK Link Cloud Programme
November 2021

## Slide 19: UK Link Move To Cloud Data Migration
The programme of work to migrate the UK Link platform to the cloud is progressing well with build and test activities continuing to plan
As reported in October ChMC, one area of challenge has been migration of the data in an appropriate time frame, to limit customer impact
We have now analysed the migration options reported to ChMC in October, and have concluded that the SAP-lead solution is best approach
The dates targeted for migration to cloud are 12th & 13th March
This approach avoids the need for customer impacting ‘non-effective dates’, but the timeline brings the project very close to the currently proposed start of CSS transition activities which with current timelines are due to commence on 26th March
On that date Xoserve and other Parties Under Integration (PUIs) will need commence a number of key activities in support of the central programme including the provision of a Data Extract from UK Link and bringing an outbound API live

## Slide 20: Section 6: Any Other Business

## Slide 21: APPENDIX