## Slide 1: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN5142: Implementation and data cleanse completed successfully First usage is in progress; due to complete 03/12/21 Final usage to be completed 31/01/22 Deferred Changes: Re-plan is in progress Preparation for go-live is in progress for 22/01/22 Revised dates for implementation approach will be shared in January ChMC Revised data cleanse plan will be shared via email XRN4992a: Impact assessment taking place to ascertain if delivery can be aligned to 22/01/22 Decision in December ChMC: None |  |  | 
Risks and Issues | In re-plan |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope – XRN4941 - MOD0692 - Auto updates to meter read frequency Icope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope – XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 24th November 2021
Complete
On Track
At Risk
Overdue
Not Baselined