## Slide 1: CSSC Programme Dashboard
December 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates: Transition: A preliminary Go Live date of the 18th July has been released by Ofgem. The Programme has also confirmed a ‘firebreak’ period of six weeks which will be added to transition phase 2 timelines. This means that the current transition timelines remain ‘as is’ and do not ‘lift and shift’ with the change in Go Live date from the June date that has been used for transition/cutover planning. Industry has been consulted on both the Go Live date and the firebreak. Xoserve have supported both aspects in principle but have called out impacts, for which we have proposed mitigations and are pending Ofgem approval/discussion. Internal & External Testing: UEPT has completed, E2E is nearing it’s final stages of Programme testing. A CR has been approved at Programme delivery group to allow the continuation of testing on the UIT environment for new participants and low priority support. The SI confirmed that this continuation presently is contained to one participant and would require support from two DNO’s only. Data Migration: REL Cycle 5 was delivered on track to Landmark last week. Landmark have confirmed receipt. Landmark are now in the process of providing the REL analysis reports on the back of REL cycle 4. Portfolios will be prepared and issued to customers for investigation into sites where a REL is failing to be identified. SOLR: The CR is now out for Industry consultation and is due to be tabled for recommendation for approval at the Ofgem Design Forum on the 6th December. |  |  |  | Transition: Completion of transition testing stage 1 and commencement of stage 2. Testing: Completion of E2E testing until end of phase. Continue to review programme CR’s and defect fixes to Programme release plan DES: CR has been raised by Xoserve to clarify the NFR around how quickly CSS data will be displayed in DES. This CR is being tabled on the 6th December at Ofgem Forum with recommendation for approval.
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | UEPT/E2E support continues. Defects raised via external testing phases have been fixed and release within the Programme releases.
 |  | Testing | UEPT has completed. E2E is in the final stages of this testing phase. CR approved to continue low level support testing but at the moment this is related to one party only and requires only DNO support.
 |  | Service Management | Continued operational readiness support. Internal workshops being held with relevant business teams to continue to work through scenarios.
 |  | Batch | All internal activities are on track and being managed across workstreams as well as working with other Programmes where activities require monitoring and regression tests.
 |  | Gemini | There are currently no Shippers registered to test the new ACT file. Information has been provided to Shippers but as yet there is still no uptake for anybody to test this file. We have one Shipper who has been granted access to the testing but they are not testing the ACT file or Exit Zone change scenario.
 |  | Reporting | Internal CR is being progressed to incorporate known changes to current reporting suites in readiness for Programme Go Live. Continued review with business teams to identify any further reporting requirement change.
 |  | UK Link | We are working on a revised retrofit delivery plan for post Jan 2022. We continue to work on the approval and implementation of internal CR’s within the Programme release timelines

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data | REL Cycle 5 has been delivered to Landmark in advance of the delivery milestone. Landmark are working on providing the REL cycle 4 analysis reports. Once analysed we will issue to the wider industry for industry cleanse. Continue to work with transition workstream for planning for cutover and transition.
 |  | Environments | All activities continuing to track to plan for all upcoming activities. Environment readiness for Transition is in progress. Environment requirements will continue to be assessed in line with the Cloud Programme for combined activities.
 |  | MAP C (XRN-4780C) | Detailed delivery updates are being provided as part of November 21
 |  | SoLR (XRN-5144) | The CR is now out for Industry consultation and is due to be tabled for recommendation for approval at the Ofgem Design Forum on the 6th December.

## Slide 5: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | There is a potential that SoLR related implications during Transition may be considered for Transition Testing. Currently expected to be discussed in September. Dates have been aligned accordingly | 30/12/21
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 30/12/22

## Slide 6
High Level Plan

## Slide 7: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Awaiting Decision
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £34,000.00 | 23/08/2021 | Pending PIA
Continuation of support for UEPT | CR-D098 | £308,000.00 | 03/08/2021 | Awaiting Decision
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | £0.00 | 17/08/2021 | Pending PIA
Elaborations for Service Management Requirements DB4 | CR-D104 | £0.00 | 17/08/2021 | Pending SI Response

## Slide 8: Switching Programme CR Position – CRs not impacting Xoserve ((Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 9: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 10
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transtion stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact