## Slide 1: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN5142: First usage complete 03/12/21 Final usage (.IQL) to be completed 31/01/22 Deferred Changes: Re-plan is approved and re-baselined Additional regression testing cycle has commenced; expected completion 13/01/21 Preparation for go-live is in progress for 22/01/22 Revised data cleanse plan will be shared via email; expected issue 07/01/22 Implementation Approach updated and shared in the following slides XRN4992a: Historical report testing completed; reports are being run in production to validate before sending to the DN's by 10th January XRN5188b: Impact assessment currently being progressed to bring into scope of November 21 Decision in January ChMC: None |  |  | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope – XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope – XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope – XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 4th January 2022
Complete
On Track
At Risk
Overdue
Not Baselined
Deferred go-live date: 22/01/2022 Contingency date: 29/01/2022

## Slide 2: XRN5289 – November 21 Implementation Approach v2

## Slide 3: Contents
Title | Slides
Principles | 3
November 21 Scope | 4
High Level Implementation Timeline | 5
File Transition & Plans | 6-8
Deployment Timeline | 9

## Slide 4: Principles
Project plan for each activity for both Implementation Dress Rehearsal (IDR) and Implementation will be defined and agreed by all internal stakeholders involved
All customer and business training and awareness sessions will have been completed prior to implementation
IDR plan will be used and refined for implementation
Any unexpected system updates on 22/01/22 to be shared with project team
Maintenance window will be utilised for code deployments

## Slide 5: November 21 Scope
XRN | Title
XRN4941 | MOD0692 - Auto updates to meter read frequency - change to Operational Smart Criteria
XRN5007 | Correction in the reconciliation process when volume is zero
XRN5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes
XRN5180 | Inner tolerance validation for replacement reads and read insertions
XRN4780C | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) – Detailed Design Update

## Slide 6: High Level Implementation Timeline
The implementation for the 5 changes consists of code transports for BW, and ISU, Control M, AMT systems, UK Link Oracle web centre (DN Portal)
Go Live 22/01/22
Deferred Changes

## Slide 7: File Transition
To incorporate the changes to files and associated processing the EFT channels will need to be closed
We will follow the standard processing times and ensure that there are none of the files listed in the next slide waiting for processing before we close the channels
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59 prior to any transports taking place
Channels will be re-opened for 09:00:00 for the next standard job processing time

## Slide 8: File Format Transition Plan - Inbound
File Type | Last inbound (Time = File Processing) | First Inbound (Time = File Processing) | Related Change
UMR | 23:00:00 | From 09:00 the next calendar day | XRN5007 XRN5072 XRN5180
UBR | 23:00:00 | From 09:00 the next calendar day | 
UDR | 23:00:00 | From 09:00 the next calendar day | 
SFN | 23:00:00 | From 09:00 the next calendar day | 
DLC | 23:00:00 | From 09:00 the next calendar day | 
SPC | 23:00:00 | From 09:00 the next working day | XRN4941
JOB | 23:00:00 | From 09:00 the next calendar day | XRN4941 XRN5072
UPD | 23:00:00 | From 09:00 the next calendar day | 
AQI | 23:00:00 | From 09:00 the next working day | XRN5072

## Slide 9: File Format Transition Plan - Outbound
File Type | Last outbound | First outbound | Related Change
IDL | 23:59:59 | From 09:00 the calendar day | XRN4941
AQR | 23:59:59 | From 09:00 the next working day | XRN5072
CFR | 23:59:59 | From 09:00 the next working day | XRN4941
URS | 23:59:59 | From 09:00 the next calendar day | XRN5007 XRN5072 XRN5180
SFR | 23:59:59 | From 09:00 the next calendar day | 
SCR | 23:59:59 | From 09:00 the next working day | XRN4941
JRS | 23:59:59 | From 09:00 the next calendar day | XRN4941 XRN5072
URS | 23:59:59 | From 09:00 the next calendar day | 
21/01/22 - 22/01/22

## Slide 10: Deployment Timeline
Deployment window to be followed according to the below table
System | Available window | Code deployment Date / time | Changes
Control-M (configuration only) | 12pm - 2pm | 21-Jan-2022 / 12pm – 2pm | XRN4941 XRN4780C
IS-U | 5am - 7am | 22-Jan-2022 / 5am - 7am | All changes
AMT | 5am - 7am | 22-Jan-2021 / 5am - 7am | XRN4780C
UK Link Oracle Web Centre (DN Portal) | 5am - 7am | 22-Jan-2022 / 5am - 7am | XRN5180
MOVEIT SFTP | 5am – 7am | 22-Jan-2022 / 5am - 7am | XRN4780C