## Slide 1: Change Management Committee
12th January 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget 21/22 YTD

## Slide 4: Budget v Committed Spend BP21/22
Chart: Total Committed Spend v Approved Budget
| Budget | Spend
 | 3589600 | 2616839.1166
Chart: Movement since last month
| Shipper | DN | IGT | NTS
 | -106058.48 | 3000 | 0 | 0
A reduction to the total Approved DSC Change Budget (BP21) of £103k occurred as a result of a change / introduction of costs across 6 changes (see linked s/s for details)
Chart: Shipper Budget v Spend
| Budget | Spend
 | 2073012.3133 | 1329719.0123
Chart: DN Budget v Spend
| Budget | Spend
 | 1248246.62 | 1253245.8415
Chart: IGT Budget v Spend
| Budget | Spend
 | 194765.1631 | 33874.2628
Chart: NT Budget v Spend
| Budget | Spend
 | 73575.9036 | 0
At this stage, Shippers have committed 64% of approved BP21 Budget
DNs have committed 100%
IGTs have committed 17% and NTS 0%

## Slide 5: Change Pipeline

## Slide 6: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Change Development
| Capture | Initial Review | Pre-capture | Solution Review
Total | 19 | 6 | 30 | 1
Chart: Delivery Pipeline
| CSSC | Nov 21 | Standalone | Unallocated | Proposed Nov 22
Total | 4 | 5 | 9 | 5 | 1
Chart: Changes From Last Period
| New Mod | New CP | CP Implemented | Mod to be closed
Total | 5 | 4 | 4 | 1

## Slide 7
2021-2022 DSC Change / MiR Pipeline
Key:
On Track
Potential Activity
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals – Initial Review
For Approval
XRN5454 Supplier of Last Resort (SoLR) Reporting Suite
XRN5463 Technical Debt reduction- Prime and Sub process enhancement
XRN5464 Technical Debt reduction – Enhancement to asset exchange process for Class 1 and 2 Meter Points

## Slide 10: XRN5454 Supplier of Last Resort (SoLR) Reporting Suite
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | EDF
Change Description
This change seeks to define [a suite] of reports that a prospective/appointed SoLR may expect to obtain to support their bidding process and, subsequently, during the period immediately following the notice of their appointment, having been issued to the CDSP by Ofgem and until every registration has transferred from the failed Supplier (either to the SoLR or to another Supplier). It is expected that this service will be an enduring service and will form part of the Gas Enquiry Service following implementation of CSS. [These reports may be subject to Third Party Service charges under the DSC.] The change will initially scope but will not be limited to the following reports: - Review of, with potential to revise, data items within the Pre-SoLR appointment report. Initial review will be with Ofgem and Suppliers (this report is currently issued to Ofgem, upon their request, and issued to Suppliers in support of the SoLR bidding process) - Post-SoLR appointment Daily Progress Report (incl switching, withdrawal status, Incoming Supplier ID) Weekly Portfolio Report - Historical Data (Failing Supplier) The final scope of reporting will be proposed to Change Managers and covered in a Solution Change Pack. Any required data permissions will be identified during the Capture process. Some of the reporting due to be scoped as part of this change, will significantly support the nomination process and therefore Modification 0788 – Minimising the market impacts of ‘Supplier Undertaking’ operation
Change Type | Non-Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 11: XRN5463 Technical Debt reduction- Prime and Sub process enhancement
DSC Service Area: | SA4: Meter Read/Asset processing ASGT-CS SA4-10
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
In the Prime & Subs portfolio, the below scenarios have been identified where the reconciliation process is not working as expected: 1. When a sub site is Isolated, consumption of the isolated sub site is not taken into account for the net-off calculation which then feeds into downstream processes such as Reconciliation and AQ calculation 2. Read replacement on sub sites does not trigger re-reconciliation. Net-off consumption should be re-calculated for the prime sites based on the read replacement on sub sites. Above scenarios are currently manually monitored and corrective actions are taken accordingly. However, delays in manual resolution could impact timely reconciliation of Prime & Sub meter points. This change seeks to enhance the reconciliation process for Prime & Sub sites within the CDSP central systems to remove the need for manual monitoring and data correction. Delivery of this change proposal will address the problem scenarios as defined within the problem statement. As the required changes will be internal to the CDSP and the analysis and corrective action is being undertaken in a support and maintenance capacity the proposed release will be ad hoc, in line with other maintenance work, to deliver benefits immediately.
Change Type | Non Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 12: XRN5464 Technical Debt reduction – Enhancement to asset exchange process for Class 1 and 2 Meter Points
DSC Service Area: | SA3: Manage updates to customer portfolio DS-CS SA3 – 06
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
When an RGMA exchange request is received for a Class 1 or Class 2 SMP, existing reads associated with the previous asset are cleared from new device installation date +1 up to RGMA processing date but not re-populated. This change seeks to ensure that the read history of a Class 1 or 2 SMP, following meter exchange, is populated with accurate estimated reads in a timely manner and these are issued to the Shipper and DMSPs via existing file interfaces (MDR/DDR). This will ensure that all parties have an accurate view of the read history, future estimated reads are accurate and any associated risk on submission of future actual reads is reduced. The required changes will be internal to the CDSP and utilisation of existing file formats and process will be sought in order to pass updates to Shippers and the DMSP. The analysis and corrective action will be undertaken in a support and maintenance capacity and, therefore, the proposed release will be ad hoc, in line with other maintenance work, to deliver benefits immediately.
Change Type | Non Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 13: section 4. Design & Delivery

## Slide 14: XRN4992a – Update ChMC 12th January 2022

## Slide 15: XRN4992a – Latest Position
At the December ChMC meeting, Change Managers approved XRN4992a (interim solution) moving into detailed design.
Modification 0687V - Creation of new charge to recover Last Resort Supply Payments is currently out for consultation due to be discussed at an Extraordinary Panel on 12th January.
Since the last ChMC, Modification 0797 - Last Resort Supply Payments Volumetric Charges has been raised and granted Urgent Status by Ofgem.
We have assessed Urgent Modification 0797 and provided that the monthly Last Resort Charge calculation is based upon a single monthly snapshot of each User’s portfolio, we will be able to utilise the proposed interim solution for XRN4992a.
Ultimately, the interim solution for 0687V and 0797 are the same but utilises different data to apply the SoLR Customer Charge. To confirm, the interim solution proposes that new Charge Types will be created for the SoLR Customer Charge and these will be invoiced via the Request to Bill (RTB) process.

## Slide 16: Proposed next steps – for awareness
Xoserve will continue progressing through detailed design for XRN4992a (interim solution). This solution should be suitable for either Modification (0687V or 0797).
Panel will make a recommendation on Modification 0687V and Urgent Modification 0797 at the Extraordinary Panel on 12th January.
Following this, a decision is expected from Ofgem regarding which Modification will be implemented (expected 20th January), the CDSP will still look to deliver the XRN4992a solution by 1st April 2022 in line with the Authority decision, modification implementation date and industry expectations.
A Change Pack will be issued in January providing users with further details on the XRN4992a interim solution and specify the differences between the two Modifications (however it’s expected that CDSP process impacts for Shippers will not differ between Modifications).
Once an Ofgem decision is made, a further Change Pack will be issued, confirming the solution and process in line with the Modification which has instructed to be implemented by the Authority.

## Slide 17: Detailed Design Change Packs
XRN5368.2 Gemini Single Sign-On
UK Link Manual

## Slide 18: XRN5368.2 Gemini Single Sign-On
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2944.2 - RT - PO | National Grid | Shipper, DNO, NTS | Adhoc – 24th April 2022 | XRN5368 |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 19: UK Link Manual
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2945.1 - RT - PO | N/A Documentation Change | Shipper | CSS Implementation July 22 | N/A |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 20: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Overall Status set to Amber due to multiple phases progressing in parallel and the need to baseline the Dual Run, Cutover & transition phases and Go Live date Build completion now 05/01/22 to incorporate several CRs (inclusive of Gemini Consequential Changes) System Testing due to complete by 07/01/22 (1 week extension to plan but no overall impact) System Integration Testing due to commence on 04/01/22 (1 week behind plan but no overall impact) Gemini Consequential changes tracking to plan, and System Testing completed on 27/12/12 Focus Groups for project continued through December 21 with National Grid and DN reps Dual Run and Market Trials approach discussed at Focus Groups with approach published on 24/12/21. Planned start of testing is 10/01/22 Cutover and Transition Approach to be shared for review & approval by 31/01/22 Notional Implementation date set for 26/03/22, contingency options defined and shared to Focus Group. To be discussed further with DNs & NG |  | 
Risks and Issues | There is a risk that change congestion with UK Link move to Cloud, Gemini Regulation and Sustaining change during Q1 & 2 2022 where cutover & implementation dates may need to be prioritised There is a risk that until the transition & cutover approach is agreed between Xoserve, National Grid & DNs to confirm the length of Post Implementation Support and what support dependencies are required from National Grid as the existing service provider There is a risk that National Grid have served notice to terminate the current FWACV service on the 31st March 2022 and the project plan does not meet an implementation date of the new service from the 01st April 2022, resulting in the need to negotiate an extension of the service by National Grid |  | 
Cost | Forecast costs tracking to approved BER costs |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  | 
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 21: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN5142: First usage complete 03/12/21 Final usage (.IQL) to be completed 31/01/22 Deferred Changes: Re-plan is approved and re-baselined Additional regression testing cycle has commenced; expected completion 13/01/21 Preparation for go-live is in progress for 22/01/22 Revised data cleanse plan will be shared via email; expected issue 07/01/22 Implementation Approach updated and shared in the following slides XRN4992a: Historical report testing completed; reports are being run in production to validate before sending to the DN's by 10th January XRN5188b: Impact assessment currently being progressed to bring into scope of November 21 Decision in January ChMC: None |  |  | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope – XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope – XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope – XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 4th January 2022
Complete
On Track
At Risk
Overdue
Not Baselined
Deferred go-live date: 22/01/2022 Contingency date: 29/01/2022

## Slide 22: XRN5289 – November 21 Implementation Approach v2

## Slide 23: Contents
Title | Slides
Principles | 3
November 21 Scope | 4
High Level Implementation Timeline | 5
File Transition & Plans | 6-8
Deployment Timeline | 9

## Slide 24: Principles
Project plan for each activity for both Implementation Dress Rehearsal (IDR) and Implementation will be defined and agreed by all internal stakeholders involved
All customer and business training and awareness sessions will have been completed prior to implementation
IDR plan will be used and refined for implementation
Any unexpected system updates on 22/01/22 to be shared with project team
Maintenance window will be utilised for code deployments

## Slide 25: November 21 Scope
XRN | Title
XRN4941 | MOD0692 - Auto updates to meter read frequency - change to Operational Smart Criteria
XRN5007 | Correction in the reconciliation process when volume is zero
XRN5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes
XRN5180 | Inner tolerance validation for replacement reads and read insertions
XRN4780C | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) – Detailed Design Update

## Slide 26: High Level Implementation Timeline
The implementation for the 5 changes consists of code transports for BW, and ISU, Control M, AMT systems, UK Link Oracle web centre (DN Portal)
Go Live 22/01/22
Deferred Changes

## Slide 27: File Transition
To incorporate the changes to files and associated processing the EFT channels will need to be closed
We will follow the standard processing times and ensure that there are none of the files listed in the next slide waiting for processing before we close the channels
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59 prior to any transports taking place
Channels will be re-opened for 09:00:00 for the next standard job processing time

## Slide 28: File Format Transition Plan - Inbound
File Type | Last inbound (Time = File Processing) | First Inbound (Time = File Processing) | Related Change
UMR | 23:00:00 | From 09:00 the next calendar day | XRN5007 XRN5072 XRN5180
UBR | 23:00:00 | From 09:00 the next calendar day | 
UDR | 23:00:00 | From 09:00 the next calendar day | 
SFN | 23:00:00 | From 09:00 the next calendar day | 
DLC | 23:00:00 | From 09:00 the next calendar day | 
SPC | 23:00:00 | From 09:00 the next working day | XRN4941
JOB | 23:00:00 | From 09:00 the next calendar day | XRN4941 XRN5072
UPD | 23:00:00 | From 09:00 the next calendar day | 
AQI | 23:00:00 | From 09:00 the next working day | XRN5072

## Slide 29: File Format Transition Plan - Outbound
File Type | Last outbound | First outbound | Related Change
IDL | 23:59:59 | From 09:00 the calendar day | XRN4941
AQR | 23:59:59 | From 09:00 the next working day | XRN5072
CFR | 23:59:59 | From 09:00 the next working day | XRN4941
URS | 23:59:59 | From 09:00 the next calendar day | XRN5007 XRN5072 XRN5180
SFR | 23:59:59 | From 09:00 the next calendar day | 
SCR | 23:59:59 | From 09:00 the next working day | XRN4941
JRS | 23:59:59 | From 09:00 the next calendar day | XRN4941 XRN5072
URS | 23:59:59 | From 09:00 the next calendar day | 
21/01/22 - 22/01/22

## Slide 30: Deployment Timeline
Deployment window to be followed according to the below table
System | Available window | Code deployment Date / time | Changes
Control-M (configuration only) | 12pm - 2pm | 21-Jan-2022 / 12pm – 2pm | XRN4941 XRN4780C
IS-U | 5am - 7am | 22-Jan-2022 / 5am - 7am | All changes
AMT | 5am - 7am | 22-Jan-2021 / 5am - 7am | XRN4780C
UK Link Oracle Web Centre (DN Portal) | 5am - 7am | 22-Jan-2022 / 5am - 7am | XRN5180
MOVEIT SFTP | 5am – 7am | 22-Jan-2022 / 5am - 7am | XRN4780C

## Slide 31: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Project On Track Post Implementation Support (PIS) period 3 successfully concluded on 10/12/21 Project closedown activities have commenced Planned submission of Change Completion Report to ChMC in February for approval Decision In January ChMC None |  | 
Risks and Issues | None Applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | In Scope (XRN5093) - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped (XRN4992) - MOD0687 – Creation of new charge to recover last resort supply payments – Descoped at Extraordinary ChMC on 26th October 2020 Descoped (XRN4941) - MOD0692 - Auto updates to meter read frequency – Descoped at ChMC on 11th November 2020 |  | 
Slide updated on 4th January 2022
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 32: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS DEC 2021 - DEC 2023
December 2021

## Slide 33
Programmes & Projects 2021-2023 |  |  |  | 2021 | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 – Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | MOD0728B – UK Link & Gemini Delivered as part of CP5341 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Manisha Bhardwaj | Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | API Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS DEC 2021 – DEC 2023
Design to PIS -Dec 21 to Feb 22 – Indicative timeline
Design to PIS – Sept 21 to May 22 – Indicative timeline
PIS Gemini - Sept to Dec 21
Design to PIS – Jan 22 to Apr 22 – Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Analysis & Design
Oct 21 – Dec 21
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Mar 22 – Indicative timeline

## Slide 34: CSSC Programme Dashboard
Verbal Update presented by Emma Lyndon

## Slide 35: Move to Cloud
Verbal Update presented by Emma Lyndon

## Slide 36: Section 6: Any Other Business

## Slide 37: APPENDIX

## Slide 38: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5339 | EFT | 27/02/2022 | TBC | 27/02/2022 | TBC | This change will be to cutover from the existing EFT PROD to the newly built and upgraded EFT PROD, to keep the application in support. This extended outage will be on a Sunday and utilise the maintenance window for EFT to cause less impact to the industry. During the extended outage any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 6th March. | 13/10/2021
XRN 5339 | EFT | 13/03/2022 | TBC | 13/032022 | TBC | As part the Enhanced File Transfer (EFT) project we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgrade EFT. As EFT is a multiple site application we will fail over to one site then failback to service normal and test the other site the following week. Please be aware that the EFT DR Contingency Dates will be carried out on the following weekend. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. | 13/10/2021
XRN 5339 | EFT | 20/03/2022 | TBC | 20/03/2022 | TBC | As part the Enhanced File Transfer (EFT) project we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgrade EFT. As EFT is a multiple site application we will have failed over, then failed back one site on the previous week, to complete the DR testing this weekend we will DR test the remaining site. Please be aware that the EFT DR Contingency Dates will be carried out on the following weekend. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. | 13/10/2021

## Slide 39: Portfolio POAP