## Slide 1: CSSC Programme Dashboard
February 2022

## Slide 2
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met Xoserve raised a CR (CR-D129) to include an NFR to ensure all Secured Active Messages from CSS reach UK Link within a stipulated time following Gate Closure. Discussions have been held with Ofgem (details below) | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini: Based on the CSS design and the Programme testing carried out to date, normal operation should be satisfied from CSS with enough time to process secured active messages. However, there is a risk that some messages may be received late or in an extreme circumstance experience a system failure which could result in a disconnect. Following discussions with Ofgem, DCC/Landmark and ourselves have been instructed to look at exceptions processes and Service Management measures to mitigate the issue should it occur. An RTO of one hour was stipulated on CSS as part of design in DB4 requirements. This RTO will allow ensure CSS will be operational within an hour of any P1 failure, which in turn protects PUI processes as this will allow us to accept and process the secured active messages and keep systems in sync. It has recently come to our attention that the REC schedule pertinent to CSS is referring to an RTO of four hours rather than the one-hour RTO. This would mean that CSS has four hours to recover and if a failure was seen at gate closure Xoserve and other parties would not receive secured active messages within the expected NFR. We continue to work this through with the Central Programme and REC Transition: The Programme have approved 18th of July as the Go-live date. Transition Testing is being undertaken currently, with Transition Stage 2 being inflight. Xoserve have had 2 minor defects which have been addressed without any implications to timelines. Internal and external activities are now focussed on Business and Operational readiness. |  |  |  | Transition: Completion of transition testing stage 2 and commencement of stage 3. Operational Readiness: Planned activities are on track
e

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | UEPT/E2E support continues
 |  | Testing | UEPT low priority testing continues. This will conclude at the end of February
 |  | Service Management | Continued operational readiness support. Internal workshops being held with relevant business teams to continue to work through scenarios in readiness for early life support and Go Live
 |  | Batch | All internal activities are on track and being managed across workstreams as well as working with other Programmes where activities require monitoring and regression tests following Programme CR releases
 |  | Gemini | Readiness for Go Live activities are being undertaken
 |  | Reporting | Continued review and awareness sessions being held with the wider business as part of our business change activities
 |  | UK Link | We continue to work on the approval and implementation of internal CR’s within the Programme release timelines

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data | REL Cycle 5 has been delivered to Landmark in advance of the delivery milestone. Landmark are working on providing the REL cycle 4 analysis reports. Once analysed we will issue to the wider industry for industry cleanse. Continue to work with transition workstream for planning for cutover and transition.
 |  | Environments | All activities continuing to track to plan for all upcoming activities. Environment readiness for Transition is in progress. Environment requirements will continue to be assessed in line with the Cloud Programme for combined activities.
 |  | MAP C (XRN-4780C) | Successfully implemented as part of the November 21 release (Go-Live in January 22)
 |  | SoLR (XRN-5144) | Industry consultation concluded. Chosen SOLR option to be implemented
 |  | Transition | Transition Testing on track to schedule. All activities continue to be on track

## Slide 5: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Discussed at Delivery Group 25/01. Minutes pending. | 01/03/22
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 18/07/22
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | DCC engagement with DCC will ramp up in 2022 we will ensure reporting requirements are on the agenda | 25/02/22
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | SoLR impacts could manifest itself during the upcoming months - continues to be monitored | 31/03/22
65122 |  | Transition/ Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Continue to monitor, low exposure at this point | 28/02/22
66480 |  | Programme | There is a risk that the Go Live date could be pushed out further because of the current market situation in the Gas Industry with suppliers going out of business leading to additional cost to the programme, significant re-planning and impacts to other Correla initiatives | Regular communication with OFGEM to understand their strategy to address this issue | Continues to be monitored | 21/01/22

## Slide 6: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
66599 |  | Programme | There is a risk that the Transition phase of the Switching Programme may be adversely impacted as a result of SoLR activities consuming the focus and efforts of Business and Operational teams who had been planned to be focused on Switching Programme Transition activities leading to a potential impact to Transitional activities as planned currently (March 2022) | Liaise with Switching Programme stakeholders to agree mitigations | Continues to be monitored | 28/02/22
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | - Xoserve have raised CR-D129 to mitigate this risk. - Discussions ongoing with programme stakeholders | Session undertaken with Ofgem with actions in place. This will be tracked until mitigation actions are completed | 31/01/22
66907 |  | Programme | There is a risk that the SLAs stipulated with the CSS NFRs (1 Hr RTO) will not be met post CSS Go-live because REC is using the Switching BCDR document as the base for REC Service Definitions which has a 4 hour RTO defined with a maximum time of 8 hours for CSS to come back into operation leading to a massive impact on UK Link downstream processing, particularly with Gemini and settlement | This is being raised with REC and relevant Ofgem stakeholders | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 31/01/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 28/02/22

## Slide 7
High Level Plan

## Slide 8: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect newupdated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | £18,500.00 | 26/11/2021 | Approved - Internal CR Created

## Slide 9: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 10: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 11
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Withdrawn
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)

## Slide 12
CR Name | CR Ref | Date Raised | Status
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Complete - No Xoserve Impact
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)