## Slide 1: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 24/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baseline; revised to 03/03 due to additional requirements on reporting Detailed Design scheduled to be baselined 17/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | April 2022 – Consultation May 2022 - Approval | 67431: There is a risk that a MOD may be raised to include IGT sites into SoLR charging. This will cause a scope change and as different charge rates will be required for IGT sites, significant design work.​ Mitigation: Accept risk. Design will be completed prior to a Mod being approved. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
Slide updated on 25th February 2022
Notes: u

## Slide 2: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction | April 2022 – Consultation May 2022 - Approval | There is a risk that the physical works required on site will not be completed in line with a Nov 22 Release Date. Mitigation: Align to a future release post Nov22 release if works cannot be completed on time |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 24/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | April 2022 – Consultation May 2022 - Approval | There is a risk that the detailed design change pack will not be approved if MOD0799 is still outstanding​ Mitigation: Accept risk. Complete Design. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
Slide updated on 25th February 2022