## Slide 1: Change Management Committee
9th March 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget 21/22 YTD

## Slide 4: Budget v Committed Spend BP21/22
Full view of budget saved here, including details of movement from last month
Chart: DN Budget v Spend
| Budget | Spend
 | 1248246.62 | 1253245.8415
Chart: IGT Budget v Spend
| Budget | Spend
 | 194765.1631 | 33874.2628
At this stage, Shippers have committed 67% of approved BP21 Budget
DNs have committed 100%
IGTs have committed 17% and NTS 28%
Chart: Total budget v committed spend
| Budget | Spend
 | 3589600 | 2697236.1166
Chart: Shipper Budget v Spend
| Budget | Spend
 | 2073012.3133 | 1389719.0123
Chart: NTS Budget v Spend
| Budget | Spend
 | 73575.9036 | 20397
Chart: Movement since last month
| Shipper | DN | IGT | NTS
 | -60000 | 0 | 0 | -20397

## Slide 5: Change Pipeline

## Slide 6: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Delivery Pipeline
| CSSC | Standalone | Unallocated | Proposed Nov 22
Total | 4 | 12 | 6 | 1
Chart: Change Development
| Capture | Initial Review | Pre-capture | Solution Review
Total | 17 | 4 | 24 | 1
Chart: Changes From Last Period
| New Mod | New CP | CP Implemented | Withdrawn
Total | 5 | 2 | 1 | 4

## Slide 7
2021-2022 DSC Change / MiR Pipeline
Key:
On Track
Potential Activity
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
Planning

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals
For Approval
XRN5482 - Replacement of reads associated to a meter asset technical details change or update (RGMA)
XRN5485 - Resource to Support the Retail Energy Code (REC)
For Information
XRN5484 - New Service Line for SDT v22

## Slide 10: XRN5482- Replacement of reads associated to a meter asset technical details change or update (RGMA)
DSC Service Area: | Service Area 4 - Meter Read/Asset processing
Link to Change Proposal | Link to CP
Sponsor Representative | Scottish Power
Change Description
This change has been raised to investigate and develop the mechanism for Shipper Users to be able to replace an RGMA related read, actual or estimated, where that read is for a read date within their period of ownership. It is expected that any processes being proposed would align to the existing Updated Meter Read process which currently allows Shipper Users to update any read within their period of ownership, on or after the Code Cut Off Date (Line In the Sand (LIS)), not created as a result of an RGMA transaction. All Updated Meter Reads should continue to be subject to defined validations.
Change Type | Non regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 11: XRN5485 - Resource to support the Retail Energy Code (REC)
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
When developing the 2022/23 Business Plan (BP), it was agreed by DSC Customers that there would be ring-fenced part of the DSC Change Budget to fund additional resources to support the REC. With the BP for 2022/23 commencing in April, we have raised this Change Proposal to secure the resource to support the REC. The resource funded under this Change Proposal will support the REC, specifically the development, assessment and delivery of REC change impacting central systems and processes.
Change Type | N/A
Priority Score | N/A
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X

## Slide 12: XRN5484- New Service Line for SDT v22
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
A new service line has been created to support Mod 0788 – ASGT-NC-SA8-01 ‘Minimising the market impacts of ‘Supplier Undertaking’ operation. This is associated with XRN5450 which was raised to implement the solution required to be delivered as set out in the Mod.
Change Type | Documentation
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This will be presented for approval at CoMC on 16th March | 
Service Requirement Description | Service Requirement Trigger
To make available where required, a demand tool which in the event of a Shipper termination, the tool would allow the CDSP to calculate estimate demand at Supplier level enabling the Supplier to enter an arrangement with a new Shipper to offset the demand, via a trade, with the Terminated Shipper. | Supplier populates and submits the ‘Supplier – Failed Shipper replacement form’ which can be located on Xoserve.com. This is sent to the Shipper contact provided on the form. The Shipper requests the CDSP to provide the estimate demand

## Slide 13: XRN 5471 Services to release data to UNC Parties
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X
Link to Change Proposal | Link to CP
Link to Change Pack | 2973.4 - MT - PO
Description
DSC parties have indicated that they consider that they have specific use cases for access to data for them to fulfil activities necessary for them under UNC and Licence. They have indicated that they expect that they have specific data requirements based on particular use cases and would like to specify the necessary data that their users will wish to access rather than necessarily progressing through a series of screens to access a standard set of data. They anticipate that this service would be discrete from the Data Enquiry Service. It is expected that this will need to provide a User Interface – and based upon prescribed search criteria (that will need to be defined for each use case) will return a specified set of data items (which again will be specified per use case). This needs to be a low cost solution option that allows access to data for designated individuals within DSC parties organisations. This service would be available to core DSC customers. [This may be extended to Service Providers – such as the DMSP at some point in the future]. It is expected that users will need to access this data via a user interface (screen) and it is not expected that this will be a machine to machine API.
Approvals | Deferrals | Rejections
2 |  | 
Initial Review Consultation Summary
Change Proposals – Post Initial Review for Approval

## Slide 14
Organisation | Comments | Change Proposal in Principle : Approve Reject Defer
Northern Gas Networks | Northern Gas Networks support the principle of development of a new user interfacing enquiry service to replace DES (once this has moved to GES), to allow DSC parties to access data required for necessary activities. We are aware that a solution is still required, however as there are currently numerous data projects going on both within Correla and NGN, we are unable to add further comment until we can see the various solution options that will be proposed, including details of the data items, delivery (E.g. DDP, Email, CMS etc), frequency and whether these contain real time data, as well as various options for alternative methods of delivery. We are reluctant to rely solely on GES, as this is under the control of REC, and therefore we have no certainty that the data items will remain as currently built, or that the funding methodology will not change. We therefore wish for this proposal to remain open with options, and potential costs, being explored in more detail by Xoserve/Correla and DSC parties. | Approve with comments
SGN | SGN would support additional assessment by Xoserve specifically on those data items provided within the Data Enquiry Service (DES) that are not currently provisioned to DSC Parties via existing reporting or the Data Discovery Platform (DDP). We would be interested to understand the potential costs which could be associated with providing various Use Cases to DSC Parties and how this could be apportioned depending on the number utilised via an API Interface Service. As a Distribution Network our preference would be to gain access to the data we require to perform our obligations from Xoserve as the Gas Central Data Service Provider. If progressed SGN's preference would be for this to be implemented under a Minor Release which could provide flexibility in delivery. | Approve with comments

## Slide 15: XRN5236 Reporting Valid Confirmed Theft of Gas into Central Systems (Mod 0734)
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Funding | Preferred Option | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  | Approve | Defer | Reject
2934.1 - RT - PO | 135K – 175K | 100% Shipper | Option 1- Interim solution only | Shipper | By April 22 | CP Page |  |  | 1
Org | Status | Comments
EDF | Reject | We support MOD 0734S and the enduring solution which seeks to introduce a robust process whereby the volume of the confirmed theft is reported into central systems. We feel that the solution should allow the shippers to bulk accept Theft claims via CMS, and have a preview option of the bulk list so that the shipper is able to see any stand out volume and reject that one and then accept the rest. We feel this would allow efficiency in the solution. In terms of the interim solution, we cannot see a strong benefit case to implement something which will be subsequently replaced within months by the enduring solution. We would like to understand more details in terms of the benefits it would bring to industry. Our understanding is that MOD 0734S is yet to be approved in January 2022, which raises a question whether the solution should be discussed for approval. In addition, it is not clear what is driving the early implementation of the interim solution. Our understanding is that the proposed implementation date April 2022 was originally based on the new TRAS process being in place by this time. The new TRAS process will no longer be in place by this time as it has been delayed. Moreover, if the “as is” process is followed correctly then identified gas theft will be entered into settlements. MOD 0734S makes this simpler and to ensure compliance but there is nothing preventing compliance if current processes are followed. Therefore, we believe that this change should be delivered as part of the CMS rebuild programme as a more cost-efficient way to deliver the change.
Change Proposals – Post Solution Review for Approval

## Slide 16: section 4. Design & Delivery

## Slide 17: Design Change Pack
Supply Point Switching Data Items
UK Link Manual Documentation - CSSC Changes
XRN5245 - Move To Cloud
Notice of Delivery of MOD0785 – Aggregate Bacton (exit) Interconnector Points

## Slide 18: Supply Point Switching Data Items
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
2974.1 - MT - PO | CSSC Funded | Shipper | CSS Implementation 18/07/2022 |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 19: UK Link Manual Documentation
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
2974.2 - MT - PO | N/A Documentation Change | Shippers | Adhoc July 22 |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 20: XRN5245 Move To Cloud
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Outage Dates | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
2973.3 - MT - PO | Investment line | Shippers, IGTs, GTs, NTS | Please refer back to Change Pack |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 21: XRN5393 Notice of Delivery of MOD0785 – Aggregate Bacton (exit) Interconnector Points
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2973.1 - MT - PO | NTS | NGT, Shipper, DNO (from website) | Part A – 25/02/22 Part B – 03/04/22 dependant on OFGEM approval of UNC Modification 0785 | CP |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 22: Standalone Change Documents for Approval (BER, CCR, EQR)
EQR for XRN5485 Resource to support the Retail Energy Code (REC)
  - Voting: Shipper, IGT, DNOs

## Slide 23: November 2021 Major Release

## Slide 24: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN5142: Final usage (.IQL) has run; being validated Deferred Changes: First usage and data cleanses progressing against plan XRN4780C .MON files are currently on hold XRN4992a: Build is in progress Overall plan in final stages of approval prior to baselining XRN5188b: Design is in progress Overall plan in final stages of approval prior to baselining Decision in March ChMC: None |  | XRN5289 | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope - XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope - XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope - XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope - XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 24th February 2022
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 25: XRN5231 Flow Weighted Average CV

## Slide 26: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  | Replan in progress to confirm revised dates at the April ChMC | 
Risks and Issues | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 27: December 21 - April 22 Changes in Design Update

## Slide 28: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 24/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baseline; revised to 03/03 due to additional requirements on reporting Detailed Design scheduled to be baselined 17/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | April 2022 – Consultation May 2022 - Approval | 67431: There is a risk that a MOD may be raised to include IGT sites into SoLR charging. This will cause a scope change and as different charge rates will be required for IGT sites, significant design work.​ Mitigation: Accept risk. Design will be completed prior to a Mod being approved. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
Slide updated on 25th February 2022
Notes: u

## Slide 29: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction | April 2022 – Consultation May 2022 - Approval | There is a risk that the physical works required on site will not be completed in line with a Nov 22 Release Date. Mitigation: Align to a future release post Nov22 release if works cannot be completed on time |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 24/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | April 2022 – Consultation May 2022 - Approval |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | April 2022 – Consultation May 2022 - Approval | There is a risk that the detailed design change pack will not be approved if MOD0799 is still outstanding​ Mitigation: Accept risk. Complete Design. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 25/03/22 Change Packs to be issued to ChMC on 19/04/22
Slide updated on 25th February 2022

## Slide 30: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS FEB 2022 – FEB 2024
February 2022

## Slide 31
Programmes & Projects 2022-2024 |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Emma Catton | XRN5368.2 Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.3 API Enhancements |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.1 Control M and Batch Processing |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.5 Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS FEB 2022 – FEB 2024
Design to PIS -Dec 21 to June 22 – Indicative timeline
Design to PIS – Sept 21 to May 22 – Indicative timeline
API - Design to PIS – Jan 22 to May 22 – Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Jul 22 – Indicative timeline
Go Live
10th Apr
Go Live
30th Jun
Go Live
25th Feb – Part A
Go Live
29th May
Control M - Design to PIS – Jan 22 to Apr 22 – Indicative timeline
Go Live
8th May
Prod ChG 1
Go Live
15th Mar
ChG 2
Go Live
1st Mar
ChG 1
Contingency
27th Feb– Part A
Contingency
12th Jun
Go Live
18th May
Prod ChG 2
Go Live
3rd Apr – Part B
Contingency
10th Apr – Part B

## Slide 32: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 33: CSSC Programme Dashboard
March 2022

## Slide 34
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of an Amber status due to very close proximity and dependency on the M2C Programme. The two Programmes are working hand in hand with joint plans in place to ensure joint Programme dependencies are continuously tracked as we move to the implementation of M2C. Contingency scenario planning with mitigations are in place. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini: We are continuing to liaise with the Central Programme for CR-D130 and CR-D129. We have had an initial meeting with Ofgem to walkthrough our workaround process should the issue of ‘missing messages’. We are going to continue discussion with DCC to understand their actions and then we will joining meet with Ofgem and approve the way forward for these CR’s. We have over the last couple of weeks raised a number of design issues to understand CSSP functionality. Once we have an understanding of the system and downstream processes this will feed into our understand and workaround process. We will also either enhance CR-D129 or raise a new CR in order for us to request the ‘re-send’ of a secured active message Transition: Transition testing phase 2 has completed and we are on track for preparation activities to commence transition testing stage 3. We are rapidly moving towards the data cut for the Transition Stage 1, all of our prep activities are on track and we have received an internal Go decision to move to this Programme Phase. |  |  |  | Transition: Completion of transition testing stage 2 and commencement of stage 3. Continued preparation activities for Transition Stage 1 Defect management process and readiness for TS1 being put in place
e

## Slide 35: Move to Cloud Programme Dashboard
March 2022

## Slide 36
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of an Amber status due to the timescales in the plan and the lack of contingency to deliver prior to CSSC transition start. The programme is currently in the middle of the second dress rehearsal which is proceeding to plan and successfully using all of the lessons learned from dress rehearsal one. A successful outcome to this will provide the necessary confidence that the Easter cutover is achievable and therefore a return to green. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Dress Rehearsals Our first dress rehearsal was successful in proving the data quality of the migrated systems was 100% accurate. There were a number of lessons learned in the migration timings, assurance steps and critical batch file activity post cutover which have been incorporated into the plan for our second rehearsal. The second dress rehearsal is now underway and is progressing well with all data migrations and pre-requisite activities being carried out to plan in preparation for our cutover simulation starting on 5th March. Testing The final round of test cycles are close to being completed in our target production environment. Functional, UAT, performance and penetration testing are successfully finished. Gas day testing has also been carried out and we are now expanding this to test monthly, quarterly and annual jobs over the next couple of weeks. Go Live In order to complete the implementation and cutover activities for the move to the cloud as part of the UK Link roadmap, an extended outage is required from 09:00 on 15th April to 07:00 on 19th April 2022 BST. A timeline and dedicated page to share progress will be published on the Xoserve website w/c 7th March 2022 |  |  |  | Completion of second dress rehearsal Start of cutover cycle
e

## Slide 37: CMS Rebuild March Update
Update

## Slide 38: Progress to Date
The Product Team are continuing to mobilise and prepare for a first release in Q4 2022. Two processes have been shortlisted along with the new Theft of Gas (ToG) process that will deliver the UNC Modification 0734 requirements.
The Swapped Address (previously part of the Address amendments process) and the previously offline process for Meter Number Creation of found meters (MNC) have been selected as they address multiple current day pain points across the Customer Constituency Groups and will have minimal customer impact to implement.
The Team are currently going through a sizing exercise to determine what can be delivered in Q4 2022 alongside the ToG Modification. As delivery will follow an Agile Framework, there is an option to deliver a Minimum Viable Product (MVP) initially with future releases improving the end-to-end functionality of that process.
Continuing with the customer engagement the Customer Focus Group Sessions are currently being planned around the existing calendar entries and will be published in March 2022.
Further updates will be provided in April ChMC.

## Slide 39: Section 6: AnY Other Business

## Slide 40: Project 1Stop Update
Verbal Update Presented by Megan Troth

## Slide 41: Change Pack Update
As the Change Packs will now be uploaded individually as part of the CP page improvements, we have modified the documents.
This means that they are now papers in their own right and not an extension of the CP

## Slide 42: KVI Change Management Survey Feedback
January 2022

## Slide 43: KVI Change Management Survey – Jan 2022
Q3 score of 79%
There is an increase in average YTD from 71% to 73% (quarterly snapshot score of 79%)
Rolling 12 month average down from 87% to 79%
Increase in participants from 3 to 9
Chart: Change KVI Survey: Rolling Performance
| Jul-20 | Oct-20 | Feb-21 | Jul-21 | Oct-21 | Jan-22
% of positive answers per survey | 0.97 | 1 | 0.97 | 0.65 | 0.76 | 0.79
# of responding organisations | 10 | 8 | 5 | 5 | 3 | 9

## Slide 44: APPENDIX

## Slide 45: Portfolio POAP

## Slide 46: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5339 | EFT | 13/03/2022 | 05:45 | 13/032022 | 10:30 | EFT Upgrade File share operation system upgrade We will then upgrade the windows operating system (OS) of the EFT file share server, and an extended outage is expected to complete this upgrade activity. During the outage all files will be put on hold whilst upgrade activities are completed. Once the upgrade is complete all files and systems will continue to perform as usual. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 20th March. | 13/10/2021 Times and description updated 09/02/2022
XRN 5339 | EFT | 20/03/2022 | 04:45 | 20/03/2022 | 09:00 | Following successful implementation of the previous EFT upgrade implementations above, this change will see the EFT application version upgraded from 7.4.13 to 8.0.5, this will complete the final step in the EFT upgrade implementations. As part of this change, an extended outage is required to complete the production upgrade activities. This extended outage is being scheduled for Sunday 20th March and will be aligned to the UKLink maintenance window in order to cause minimum disruption to the services. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 27th March. | 13/10/2021 Times and description updated 09/02/2022
XRN 5339 | EFT | 26/03/2022 | TBC | 27/03/2022 | TBC | EFT Upgrade DR Testing As part the Enhanced File Transfer (EFT) upgrade project, we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgraded EFT. As EFT runs across two sites, we will fail over to one site then failback to service normal and test the other site the following week. During the outage all files will be put on hold whilst all upgrade activities are completed. Once complete all files and systems will continue to perform as usual. Timescales for the extended outage are currently under review and will be notified as soon as available. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 5th & 6th April. | 09/02/2022 New
XRN 5245 | UKLink | 15/04/2022 | 09:00 | 19/04/2022 | 07:00 | As part of UK Link Programme, an extended outage will be required to cutover UK Link system from the current On Premise Data Centres to the Cloud. This extended outage will be over the Easter weekend and therefore utilises Bank Holiday days in order to minimise impact to the Industry. Extended Outage is planned from 15th April 09:00 to 19th April 07:00 BST. Services will resume at 07:00 on Tuesday 19th April post maintenance schedule. As a result of this outage all external access to the online screens (via DES / Portal existing platform) will be unavailable during the window mentioned above Some file flow impacts are anticipated, these are currently being communicated via various forums and industry communications. All inbound files will be held in a queue at our EFT interface to be processed as soon as migration activities are complete as per the details communicated via the Change Pack. | 09/02/2022 New
XRN 5301 | UKLink Portal | 07/05/2022 | 09:00 | 09/05/2022 | 07:00 | As part of the UK Link move to Cloud Programme, an extended outage will be required to complete implementation and cutover activities for the new DES & Portal screens. These systems will be unavailable for use from 7th May 09:00 to 9th May 2022 7:00. | 09/02/2022 New

## Slide 47: CSSC Programme Dashboard
March 2022

## Slide 48
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of an Amber status due to very close proximity and dependency on the M2C Programme. The two Programmes are working hand in hand with joint plans in place to ensure joint Programme dependencies are continuously tracked as we move to the implementation of M2C. Contingency scenario planning with mitigations are in place. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini: We are continuing to liaise with the Central Programme for CR-D130 and CR-D129. We have had an initial meeting with Ofgem to walkthrough our workaround process should the issue of ‘missing messages’. We are going to continue discussion with DCC to understand their actions and then we will joining meet with Ofgem and approve the way forward for these CR’s. We have over the last couple of weeks raised a number of design issues to understand CSSP functionality. Once we have an understanding of the system and downstream processes this will feed into our understand and workaround process. We will also either enhance CR-D129 or raise a new CR in order for us to request the ‘re-send’ of a secured active message Transition: Transition testing phase 2 has completed and we are on track for preparation activities to commence transition testing stage 3. We are rapidly moving towards the data cut for the Transition Stage 1, all of our prep activities are on track and we have received an internal Go decision to move to this Programme Phase. |  |  |  | Transition: Completion of transition testing stage 2 and commencement of stage 3. Continued preparation activities for Transition Stage 1 Defect management process and readiness for TS1 being put in place
e

## Slide 49: Green Workstream Updates
RAG Previous month | RAG Current months | Work stream | SUMMARY
 |  | Transition | Activities to provision Environments for transition testing stage 3 in progress Transition test phase 2 on concluded on 18/02/22 with no further defects Detailed planning refinements are being undertaken for Transition Stages 2 & 3 All activities for Transition Stage 1 are in progress and on track. These activities commence on the 8th March with the bulk data cut Collaborative planning and combined execution continue with M2C Programme
 |  | Testing | Secondary API Testing - working with DES/API workstream for Secondary Portal functionality handover DES4 DES Parallel Testing completed on PPTE3, UAT Test Completion Report second draft review has been completed. Awaiting baselined approved document External UEPT Test Execution Bespoke E2E – Testing extended by 1 week in the UIT1 environment – there are 2 defects that will be delivered during release 6. Transition SIT (Regression) Functional testing planned for 28/02 additional testing activities have been agreed covering SME requested scenario’s Change Request - CR113 Testing in progress, critical path CR’s Testing in progress for Transition Stage
 |  | Non-Functional Test (Performance, operational acceptance testing and operational testing) | OAT Stream 4 (DR) Test execution is three weeks behind schedule due to previous SAP PO/ISU Environment defect which has now been resolved, however a new AMT issue has impacted testing. The AMT issue can only be resolved after 28/02/22 (B.A.U. Nov 21 issue takes precedence) PT – Phase 3 – DES Release 4 - DES PT testing currently blocked by above AMT server issue, awaiting resolution before continuing with Meter Reads replication testing. PT – Phase 3 – Secondary APIs – Test Plan and Workload model approved. secondary API PT started, but currently blocked by 2 performance defects OT – Test Report – Programme SI has approved, awaiting final internal CSSC Programme approval OAT – All OAT tests for CSS switching API, DES, Secondary APIs and SS delivered Stream 1 (Security) defect resolution in progress.- 40% complete, mitigations and re-testing planned with no impact to plan (monitoring closely) Stream 2 (Serv Man) to be replanned upon eDocs/ServiceNow, Design and Deployment dates being announced Stream 3 (NFR’s) awaiting Exception handling functional testing and Lazarus function deployment in to PPTE4 Stream 4 (DR) CSS API DR tests 52% complete – encountered DR defect (we revoked failure and DR didn’t respond), re-test is planned

## Slide 50: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | CSSC – UK Link | All critical path change requests required for Transition Stage 1 has been delivered Walkthrough held with SMEs for CRD124 -Uplifting the CSS Business Data Validation Rules. FS Design documents have been issued to SMEs for review and approval. Build activities in progress for CRD124 and CR152 Meter Reads Prime and Sub AREL Data provision to CSSP is being planned for 17/03 Change request approval pending for CR0196 Notification of outstanding pending registrations post CSS gate closure and CR210BAU Retrofit till 31st Jan Session planned with Tech Ops and key Programme stakeholders to define CSSC Triage group and process which would align with internal Change Freeze proposal CSS alignment to Manual Reads screens - Walkthrough held with SMEs on the Manual workaround option recommended. Actions and next steps agreed to ensure approval is obtained from the Business on the workaround solution Workshop held with Tech Ops and SMEs on the new exceptions that have emerged from CRD124 and CR110 . Additional session planned to discuss Existing Exception and solution approach for CR110 with SMEs Programme team to confirm approach for outstanding SLA discussions required with wider Correla audience
 |  | CSSC – API | Workstream at an amber status due to the potential incorporation of two additional API’s that will need to be planned into workload and sprints Customer Testing Support for QUERY APIs continues Automated retry of APIs due to a “non API” failure solution is on track to complete in the current sprint and be rolled out – on 25/2 Incorporation of the revised alerting solution Detailed implementation planning in flight with the transition workstream General bug fix support continues System support documentation ongoing Implementation planning Secondary Portal development continues and currently on track to deliver

## Slide 51: Workstream Updates
RAG previous month | RAG current months | Work stream | SUMMARY
 |  | Service Management | Preparations are ongoing and on track for Transition Phase 1 (T1) Service Now licences required and procurement is underway Full engagement with the Switching Programme continues Questions and knowledge transfer is occurring on a weekly basis via the SI led drop in sessions in readiness for Transition Phase (T1) Engagement happening with the Service Management Team within Tech Ops to get appropriate resolver groups set up to support T1 this is required by the 4th March Interim defect management process to support T1 is underway Two amber items on Transition Phase Confidence relate to Service Now procurement process but workstream overall at green
 |  | Early life support | PIS readiness ongoing Business Continuity Planning has started and is expected to be complete by end of March with the BCM Plan being shared across the wider business for review and approval Internal weekly workshop scheduled and on track for all internal business areas
 |  | Environments | The high number of environment issues recently encountered has subsided and all issues fixed AMT for PPTE5/Transition has been delivered; EFT configuration in progress. Consolidated Release Schedule is in progress
 |  | Batch | All E2E documents have been drafted, including the evidences and baseline documents these are currently under quality assurance checks ahead of being circulated for formal review The team are attending weekly huddles on the EFT Upgrade to obtain updates on the progress of the project and mitigate risk 66113 The batch jobs for PPTE4 have been configured but the team are awaiting confirmation for when these can be scheduled The team are waiting for the new EFT FOF environment to be delivered to commence the relevant configuration for PPTE4 Performance testing. An access request for this environment has been raised and completed

## Slide 52: Workstream Updates
RAG previous month | RAG Current month | Work stream | SUMMARY
 |  | Business Change | Overall status remains at amber due to ​concerns raised by the business over some of the edge cases that may take play (Quality)​​ This will continue at amber until the first analysis of the unhappy path scenarios. Discussion ongoing with the Central Programme for these escalations There are approximately 23 Business Change/Testing risks have been raised in RTC by the business/CSSC, reviewed, challenged and accepted by the programme. These should shortly be coming to a close on the back of the Unhappy Path solution approval, current proximity end dates are 28th Feb for all risks. Focused workshops were completed in December with the business around unhappy path, the unhappy path solution options have been agreed and are being progressed and there are some steps that need to be confirmed before we can have a solid confirmation on all solutions, this is currently being worked through with the business Exceptions workshops are in flight, these workshops have gone through and reviewed all existing and new exceptions, the final sessions are now around a query raised by the business CR110 and also a new exception that has been raised. The final action which is currently sat with the Business Change workstream is SLA confirmation Bus Change actions log stats: 90 actions to date identified and logged All activities in the plan have been lined against the relevant transition and ELS stages. These are currently reporting green and on track, no issues or concerns to date. No immediate impact on TS1, first iimpact is seen on TS2.
 |  | Gemini | Confirmation has been received that the Gemini annual file flow will be tested until EFT during the Performance Testing phase, currently planned for early Match Awaiting further conversations on late messages to progress with CR0043. If this change goes ahead communications will be planned with internal and external customers due to impacts to other systems Requests have been raised with the environments team for the relevant code and data to be deployment on to Gemini UT3 environment for Transition Stage 3 Connectivity test with UK Link will be planned for next week to ensure connectivity before Transition Testing Go Live

## Slide 53: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | DES | Overall DES is still Amber but on track to be moving to green in the next reporting window. Scope is now Green, whilst planning remains AMBER due to M2C activities Development of the DES switching elements tested and completed. It is being planned to be rolled out to all environments at the end of the current sprint M2C activities including the link between M2C and DES progressing. This is now forecast to complete mid March Alerting is currently being built out and the revised solution will require minor changes if the enterprise wide version of Grafana is used Analysis taking place on NFRs required for OAT. Once this is completed, it may require additional changes to be applied to environment configurations. This is being monitored DES User Guide has been re-written and issued for review, prior to being sent to Xoserve for review and then onto RECco. Detailed Implementation planning started with Transition workstream Planning updated to include 2 CRs (CR0131 and CR0136)

## Slide 54: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Discussed at Delivery Group 25/01. Minutes pending. | 01/03/22
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 18/07/22
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | DCC engagement with DCC will ramp up in 2022 we will ensure reporting requirements are on the agenda | 25/02/22
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | SoLR impacts could manifest itself during the upcoming months - continues to be monitored | 31/03/22
65122 |  | Transition/ Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Continue to monitor, low exposure at this point | 28/02/22
66480 |  | Programme | There is a risk that the Go Live date could be pushed out further because of the current market situation in the Gas Industry with suppliers going out of business leading to additional cost to the programme, significant re-planning and impacts to other Correla initiatives | Regular communication with OFGEM to understand their strategy to address this issue | Continues to be monitored | 21/01/22

## Slide 55: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
66599 |  | Programme | There is a risk that the Transition phase of the Switching Programme may be adversely impacted as a result of SoLR activities consuming the focus and efforts of Business and Operational teams who had been planned to be focused on Switching Programme Transition activities leading to a potential impact to Transitional activities as planned currently (March 2022) | Liaise with Switching Programme stakeholders to agree mitigations | Continues to be monitored | 28/02/22
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | - Xoserve have raised CR-D129 to mitigate this risk. - Discussions ongoing with programme stakeholders | Session undertaken with Ofgem with actions in place. This will be tracked until mitigation actions are completed | 31/01/22
66907 |  | Programme | There is a risk that the SLAs stipulated with the CSS NFRs (1 Hr RTO) will not be met post CSS Go-live because REC is using the Switching BCDR document as the base for REC Service Definitions which has a 4 hour RTO defined with a maximum time of 8 hours for CSS to come back into operation leading to a massive impact on UK Link downstream processing, particularly with Gemini and settlement | This is being raised with REC and relevant Ofgem stakeholders | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 31/01/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 28/02/22

## Slide 56
High Level Plan

## Slide 57: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect newupdated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | £18,500.00 | 26/11/2021 | Approved - Internal CR Created

## Slide 58: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 59: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 60
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Withdrawn
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)

## Slide 61
CR Name | CR Ref | Date Raised | Status
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Complete - No Xoserve Impact
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)