## Slide 1: Change Management Committee
13th April 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget 21/22 YTD

## Slide 4: FYE Budget v Committed Spend BP21/22
Full view of budget here
Chart: DN Budget v Spend
| Budget | Spend
 | 1248246.62 | 1253245.8415
Chart: IGT Budget v Spend
| Budget | Spend
 | 194765.1631 | 33874.2628
21/22 Committed Spend
Total 75%
Shippers 67
DNs 100%
IGTs 17%
NTS 28%
Chart: Total budget v committed spend
| Budget | Spend
 | 3589600 | 2697236.1166
Chart: Shipper Budget v Spend
| Budget | Spend
 | 2073012.3133 | 1389719.0123
Chart: NTS Budget v Spend
| Budget | Spend
 | 73575.9036 | 20397

## Slide 5: Change Pipeline

## Slide 6: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Change Development
| Capture | Initial Review | Pre-capture | Solution Review
Total | 18 | 1 | 22 | 1
Chart: Delivery Pipeline
| CSSC | Standalone | Unallocated | Proposed Nov 22
Total | 4 | 11 | 8 | 1
Chart: Changes From Last Period
| New Mod | In Delivery | CP Implemented | MOD to be implemented | Non Implementation
Total | 2 | 2 | 1 | 3 | 1

## Slide 7
2021-2022 DSC Change / MiR Pipeline
Key:
On Track
Potential Activity
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
Planning

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals
For Information only
XRN5495 - Changes to DSC Service Documents (for changes that do not require funding or resources to implement)
XRN5496 – Changes to Service Description Table v23

## Slide 10: XRN5495 – Changes to Third Party and Additional Service Policy
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
The CDSP Third Party and Additional Service document has been updated to include services provided by REC ahead of Xoserve contracting with REC to become the GES provider The text in red below highlights the amendments made to the existing version (v1) (2.3.1 e) the aggregate amount of the CDSP's turnover attributable to Third Party Services (excluding i) Charges payable under UK Link User Agreements; and ii) any charges payable by RECCo for the provision of services by CDSP to RECCO in relation to the REC) does not, and will not as a result of entering into the TPS Agreement, exceed 2.5% of the CDSP's overall turnover 2.4.1 (b) other than in respect of either i) a UK Link User Agreement with a Trader User; or ii) an agreement for the provision of service by CDSP to RECCo in accordance with REC, the term of the TPS Agreement does not exceed 24 months', or the CDSP may terminate the TPS Agreement without liability on not more than 24 months’ notice;
Change Type | Documentation
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This will be presented for approval at CoMC on 20th April | 

## Slide 11: XRN5496 – Changes to Service Description Table v23
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
A new service line ASGT-CS SA8-42 has been created to support XRN5458 which was raised to implement the solution required to be delivered as set out in the Urgent Modification 0791 - Contingency Gas Procurement Arrangements when a Supplier acts under a Deed of Undertaking
Change Type | Documentation
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This will be presented for approval at CoMC on 20th April | 
Service Requirement Description | Service Requirement Trigger
To enable National Grid NTS to procure gas where, following the termination of a Shipper User providing shipping services to one or more Gas Suppliers, no new Shipper User (a ‘Registered User’) is appointed and one or more of the Suppliers acts in accordance with its deed of undertaking until such time a new Registered User is in place. | From the point the Termination Notice is issued to a Shipper User (the Terminated Shipper) and where there is no new Registered User is in place or appointed

## Slide 12: XRN5238 – New Distribution Network Report – Forecast Invoice Values
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Funding | Preferred Option | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  | Approve | Defer | Reject
2988.2 - MT - PO | None – DDP | Service Area 9 - Customer Reporting (all forms) | Option 3 | DNO | By April 22 | CP Page | 1 |  | 
Org | Status | Comments
NGN | Approve | NGN supports solution option 3 for the utilisation of DDP to provide the DN pricing managers with the reporting requirements. Delays to implementation of this change would have adverse impacts; therefore this change should be implemented by the end of 2022 in line with Xoserve’s proposed key delivery dates for this change.
Change Proposals – Post Solution Review for Approval

## Slide 13: section 4. Design & Delivery

## Slide 14: Design Change Pack
XRN5231 Provision of FWACV Service
XRN4922 CSSC Shipper BRD
Non-CSS to and from CSS Supply Meter Point Switching Process

## Slide 15: XRN5231 Provision of FWACV Service
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
Not applicable – Issued to FWACV Focus Group only | DNO NGT | DNO, NGT | Adhoc - proposed June 2022 | CP | 2 |  | 
Organisation | Status | Comments
Cadent | Approve with comments | 5 comments received which Xoserve has accepted/will provide clarification to Cadent
NGN | Approve with comments | “NGN supports this updated design. We would like it noted that we would be averse to any scope creep that could impact costs, or the ability for delivery in the agreed timescale”
SGN | Comments | 14 comments received which Xoserve has accepted/will provide clarification to SGN
National Grid | Comments | 7 comments received which Xoserve has accepted/will provide clarification to National Grid
Note: Due to the commercially sensitive nature of some representations, these will not be published

## Slide 16: XRN4922 CSSC Shipper BRD
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
2989.1 - MT - PO | CSSC | Shipper | N/A – High Level BRD Approved | CP |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 17: Non-CSS to and from CSS Supply Meter Point Switching Process
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
2989.2 - MT - PO | CSSC | Shipper | Adhoc: CSS Implementation Date |  |  | 
Org | Status | Comments
 |  | No Reps Received

## Slide 18: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5368 - Gemini Change Programme Sustain
Voting: NGT
CCR for XRN4550 - Gemini Re-platform
Voting: NGT
CCR for XRN5450 - Demand tool to support Urgent Modification 0788 - Minimising the market impacts of ‘Supplier Undertaking’ operation
Voting: NGT, Shipper
CCR for XRN5253 – June 21 Release
Voting: IGT, Shipper, DNO

## Slide 19: December 21 - April 22 Changes in Design Update

## Slide 20: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | As per scope recommendation slide |  |  | Detailed Requirements baselined Detailed Design baselined Change Packs to be ready to be issued to ChMC on 19/04/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | As per scope recommendation slide |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | As per scope recommendation slide | Risk ID 67431: There is a risk that a MOD may be raised to include IGT sites into SoLR charging. This will cause a scope change and as different charge rates will be required for IGT sites; unknown impact to design. Mitigation: Accept risk. Design will be completed prior to a Mod being approved. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | As per scope recommendation slide |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | As per scope recommendation slide |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
Slide updated on 4th April 2022
Notes: u

## Slide 21: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction | As per scope recommendation slide | Risk ID 67731: There is a risk that the physical works required on Customer site will not be completed in line with a Nov 22 Release Date. Mitigation: Align to a future release post Nov22 release if works cannot be completed on time |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | As per scope recommendation slide |  |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | As per scope recommendation slide | Risk ID 67645: There is a risk that the detailed design change pack will not be approved if MOD0799 is still outstanding​ Mitigation: Accept risk. Complete Design. Decision will be taken at ChMC in May whether this will be taken into delivery for Nov22. Risk ID 67482: There is a risk that the CV range will not be updated for hydrogen because a change is required to Gemini leading to the CV for hydrogen being rejected Mitigation: Monitor change request to be raised by SGN and align to implementation release for this change. |  | Detailed Requirements baselined Detailed Design scheduled to be baselined on 08/04/22 Change Packs to be ready to be issued to ChMC on 19/04/22
Slide updated on 4th April 2022

## Slide 22: Dec 21 – Apr 22 Design Bundle Change Pack Plan and Delivery Release Options

## Slide 23: Purpose of ChMC Update
Confirm the changes that we are proposing to issue in April and May Change Pack for consultation
Share assessment of Release options for delivery of the changes in the Dec 21 – Apr 22 Design Bundle
Propose the next steps
Appendices: Evidence the impact assessment that has been performed on each change as part of Release optioneering

## Slide 24: Proposed Change Pack Content for April / May
Following the completion of our Detailed Design activities we are proposing to issue the following changes for Industry consultation in both the April and May Change Pack Consultation process
April 2022 - issued to customers on 19th April for 10 working day consultation
  XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M)
  XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664)
  XRN5298 - H100 Fife Project – Hydrogen Network Trial
May 2022 – issued to customers on 16th May for 10 working day consultation
  XRN4900 - Biomethane/Propane Reduction
  XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process
  XRN5091 - Deferral of creation of Class change reads at transfer of ownership
  XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs

## Slide 25
Nov 22 Release | Pts | Feb23 Release | Pts | Jun23* Release | Pts
XRN4978 | 8 | XRN4900 | 21 | XRN5091 | 21
XRN4990 | 8 | XRN4992B | 13 | XRN5186 | 13
XRN5298 | 8 |  |  |  | 
Total Pts | 24 |  | 34 |  | 34
Option 1
Nov 22 Release | Pts | Feb23 Release | Pts | Jun23* Release | Pts
 |  | XRN4900 | 21 | XRN5091 | 21
 |  | XRN4992B | 13 | XRN5186 | 13
 |  | XRN4990 | 8 |  | 
 |  | XRN5298 | 8 |  | 
 |  | XRN4978 | 8 |  | 
Total Pts | 0 |  | 58 |  | 34
Option 2
Option 1 Release Option Summary | 
Pros | Smoothens profile of changes being delivered Delivers XRN5298 to the proposed timescales
Cons | Reduces cost effectiveness as not fully utilising the Major Release bandwidth
Delivery Release Options
Option 2 Release Option Summary | 
Pros | Reduces Customer and Xoserve effort whilst CSSC is a priority Better utilizes the bandwidth of a Major Release, more cost effective to Customers
Cons | Delays the realisation of the objectives for XRN4978, XRN4990 and XRN5298 by approximately 4 months
Change Size | Points (Pts)
X Large | 21
Large | 13
Medium | 8
Small | 5
Major Release | 90
Sizing Key
*May also include additional changes that have not gone through change development as yet

## Slide 26: Proposed Next Steps
Issue the Change Packs as described for consultation in April
Present the April Change Packs to DSG on Monday 25th April
Seek approval of Change Packs at May ChMC and June ChMC
Present BERs for approval to cover off both Release options at ChMC in May

## Slide 27: Appendices for Information

## Slide 28
Change | Size of Change | Recommended Design Change Pack Approval | Recommended Release for Delivery | Recommendation Comments
XRN4900 | X-Large | May | Feb23 | In order to meet a Nov22 release timeline, the physical works and associated changes to systems will need to be completed in advance of System Integration Testing (SIT) in July 2022 Feb23 release is the earliest release after the above dependency can be met This change is not suitable for a minor release due to its size
XRN4978 | Medium | April | See Options (slide 4) | This change is not suitable for a Minor Release as extensive Performance Testing involved due to changes in NRL file. Build and Test effort is not sufficient in the Minor Release implementation window. Extended PIS is required to capture First Usage monitoring Nov22 is the earliest major release which can incorporate the delivery of this change and the realisation of Customer benefits. A later release can be utilised but will delay the realisation of those benefits
XRN4990 | Medium | April | See Options (slide 4) | This is not suited to a Minor Release as extensive Performance Testing involved due to the New batch job introduction to change the Class 2 and Class 3 sites to Class 4. A New channel/enhancement is needed to establish the connectivity with DDP system with UK link. Build and test efforts are not sufficient in the Minor Release implementation window. Extended PIS window needed to capture the First usage monitoring Nov22 is the earliest major release which can incorporate the delivery of this change and meet UNC MOD0664. This is the earliest opportunity the benefits stated in the UNC MOD can be achieved
XRN4992B | Medium / Large | May | Feb23 | This is not suited to a Minor Release due to the extensive level of Testing required particularly around Capacity invoicing. Extended PIS window is needed to capture the First usage monitoring. In order to include iGTs into solution and the introduction of a New Mod with an April Go Live expected, Feb23 is the first major release where the changes can be incorporated in advance of first usage in the May 2023 invoicing run.
Release Recommendation for Changes Part 1

## Slide 29
Change | Size of Change | Recommended Design Change Pack Approval | Recommended Release for Delivery | Recommendation Comments
XRN5091 | X- Large | May | Jun23 | Large complex change which impacts on CSSC code. Therefore this is not recommended for either a Nov22 or Feb23 release Jun23 allows stability following the exit of CSSC from Project Implementation Support (PIS) Update: see slide 9 for more detail on the impacts of a Nov22 or Feb23 release
XRN5186 | Large | May | Jun23 | Large complex change which impacts on CSSC code. Therefore this is not recommended for either a Nov22 or Feb23 release Jun23 allows stability following the exit of CSSC from Project Implementation Support (PIS) Update: see slide 10 for more detail on the impacts of a Nov22 or Feb23 release
XRN5298 | Medium | April | See Options (slide 4) | This is not suited to a Minor Release due to the Build and Test effort in introducing the Password protection logic in emails in SAP PO utilising JAVA. Extended PIS window needed to capture the First usage monitoring. Security testing likely to be required. MOD0799 adds risk as the change will not be approved in time for delivery and may specify differences to Design
Release Recommendation for Changes Part 2

## Slide 30
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework if Delivered Earlier than June 2023
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | Red | Amber/Red | SPA (all workflows CONF, change shipper and Supplier), Metering (UMR, UBR reads, AQI, Must Reads), RGMA | Common code/functionality with CSSC is: SPA, Reads (UMR, UBR), RGMA | Very High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required for XRN 5091 and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans XRN5091 also has extensive UAT and regression phases which may extend/need retesting due to any potential CSSC defects and/or CRs
Impact and risk of inclusion of XRN5091 in Nov22 and Feb23 Release

## Slide 31
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework
XRN5186 MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs Detailed Design | Red | Red | A number of key processes are undergoing change : Registration( Nom, Change of Supplier, Shipper change, Ratchets) | Touches large part of CSSC code Change touches Nomination/BRN | High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans Workflow defects in CSSC may need some code changes for 5186
Impact and risk of inclusion of XRN5186 in Nov22 and Feb23 Release

## Slide 32: November 2021 Major Release

## Slide 33: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Deferred Changes: Post Implementation Support exit agreed for XRN’s 4941, 5007, 5072 & 5180 XRN4780C to remain in Post Implementation Support as per plan Data cleanse for XRN5007 complete, cleanses for XRN’s 54941 & 5072 progressing to plan XRN4992a: Test is in progress Overall plan in final stages of approval prior to baselining XRN5188b: Test is in progress MAP ID data requested from MAPs for interim data load Overall plan in final stages of approval prior to baselining Decision in April ChMC: None |  | XRN5289 | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope - XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope - XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope - XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope - XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 1st April 2022
Complete
On Track
At Risk
Overdue
Not Baselined
XRN4992a
XRN5188b

## Slide 34: XRN5231 Flow Weighted Average CV

## Slide 35: XRN5231 Flow Weighted Average CV
April 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at purple. Project is in re-plan due to the issue that 1st April 22 implementation date was not met. The project has continued with its planned activities alongside the replan for the FWACV service & Gemini consequential changes. Several clarifications are still being discussed in conjunction with Xoserve & Customers alongside the Change Pack. Change Pack consultation closed on 28/03; review of reps completed, and this will be submitted for approval at the April ChMC to rebaseline the scope, plan and BER of the project. UAT continues to make progress with the assurance of test cases not impacted by scope change. Blocked test cases will be completed as part of the replan Dual Run Phase 2 commenced but lack of full DN connectivity to provide daily files is now causing an issue for having the files/data to validate to the existing NG service. Only NG & NGN are fully connected with NGN providing the required daily files. Issue raised at the Focus Group on 29/03. This is now an issue as the phase 2 plan is not giving the confidence planned. Re-plan in progress to include full impact assessment. Revised supplier costs received and in review. MTB cost assessment of the additional requirements to support manual processes are drafted and are being assessed to confirm MTB uplift required. Gemini consequential changes assessment defined and is part of the re-plan and revised BER Business Readiness and Service Transition work continues as per the plan Risk of FWACV Imp to CSSC assessment completed and confirmed that no risk to CSSC Transition & Cutover plans if implemented in June 2022 Next Steps: Finalise full re-plan from the changes to scope and requirements to define the revised plan and BER Change pack consultation reps to be approved at the April ChMC Continue Cutover & Transition scenarios with NG and DNs to define scope, plan and acceptance criteria Outstanding DNs to complete End To End connectivity to provide daily files to remove issue with DR/MT plan Continue with UAT assurance, DR/MT and Business Change planned activities Revised BER from re-plan to be approved at an extraordinary ChMC (to be agreed) | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  | Replan in progress to finalise the revised dates of the project. The project continues to progress key phases/activities (eg UAT assurance, DR/MT, Business Change (inc External Training) and Cutover & Transition planning) | 
Risks and Issues | There is an issue that NG and DNs do not understand the consequential changes with the removal of the FWACV service from NG and the impact to existing business processes – Update – Action for NG & DNs to review the consequences of the FWACV service moving from NG to Xoserve. This is key to understand any impacts to business/system processes as part of individual organisation Business Readiness plans There is a risk that changes to the approved scope and requirements and subsequent replan may put at risk a Mid June 2022 Go Live of the new Xoserve service – Update – Replan in progress There is an issue with Dual Run/Market Trials phase that only 1 DN is fully connected to provide daily files, this is now causing an issue with transactional date being out of synch due to only 1 DNs providing daily files to compare to NGs service running in production – Update – Continued engagement to work through connectivity is being progressed with impacted DNs and NG to provide support There is a risk that changes to the baselined scope and requirements will increase the costs of the new FWACV service in extending the project and manual process being identified – Update – The impact assessment to define the re-plan and revised business case is in progress to conclude the revised BER for review & approval with customers | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecast costs tracking to approved BER costs at present. Revised plan options will lead to updated costs which will be agreed in a revised BER for review & approval | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) – Change to scope and requirements in impact assessment Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 36: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS MAR 2022 – MAR 2024
MARCH 2022

## Slide 37
Programmes & Projects 2022-2024 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Emma Catton | XRN5368.2 Single Sign on Experience |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.3 API Enhancements |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.1 Control M and Batch Processing |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.5 Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS MAR 2022 – MAR 2024
Design to PIS -Dec 21 to June 22
Design to PIS – Sept 21 to June 22
API - Design to PIS – Jan 22 to May 22
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Jul 22
Go Live
29th Apr
Go Live
30th Jun
Go Live
29th May
Control M - Design to PIS – Jan 22 to Apr 22
Go Live
8th May
Prod ChG 1
Go Live
15th Mar
ChG 2
Go Live
1st Mar
ChG 1
Contingency
12th Jun
Go Live
18th May
Prod ChG 2
Go Live
3rd Apr – Part B
Contingency
10th Apr – Part B
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 38: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 39: CSSC Programme Dashboard
April 2022

## Slide 40
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status We continue to closely monitor joint dependencies with the Move To Cloud Programme. Contingency planning is complete. Move to Cloud is on track to Go Live for it’s planned date. The bulk data cut for transition stage 1 has been issued to the CSSP ahead of the milestone date. The CSSP have acknowledged receipt and will now commence reconciliation activities. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini We are continuing to liaise with the Central Programme for CR-D130 and CR-D129. This week we have had a session with DCC to understand the CSSP process and functionality at gate closure. We were given some comfort during this session and now understand that the system will be fully monitored during gate closure especially during PIS in order to monitor and meet NFR’s and this will be undertaken on a daily basis. DCC are supportive of the CR we are raising in order have the capability to request the ‘re-send’ of a secured active message. We are pushing to receive this ability during early life support as this will help mitigate should we see missing messages at Gate Closure. CR-D129 was presented at the Ofgem Design Forum this week. This CR will be moved forward into the REC Governance process for a post Programme CR to be delivered within the REC releases. The design issues we have raised over the past couple of months have still not been responded to. We have escalated and will continue to monitor and escalate. We will now commence engagement in relation to the workaround process should we any issues with missing messages at the appropriate governance groups. Please note we are not expecting this to happen in normal day to day processing this would be an exceptional circumstance. |  |  |  | Internal Stage Gate D has been approved during the last two weeks. This stage gate is the closure of Testing and the commencement of Transition Commencement and planning refinement for the Transition Stage 2 activities (2nd May) Continued OAT Testing Continued Business Change activities
e

## Slide 41: Move to Cloud Programme Dashboard
April 2022

## Slide 42
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of an Amber status due to the timescales in the plan and the lack of contingency to deliver prior to CSSC transition start. UK Link move to cloud project under the programme has successfully completed a second dress rehearsal in order to validate the original timescales outlined within the change pack. Go Live readiness is on track to complete for the 15th April extended outage commencement. Some high scoring risks are being tracked to ensure any impact on the project’s ability to progress with cut over have been assessed. These are on track to be mitigated ahead of cut over commencement on 15th April prior to returning to green. Portal Go Live previously planned for 9th May has been re-planned for 18th June. An updated change pack will be shared 19th April. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
UK Link Move to Cloud stream activities: The final round of test cycles have now been completed in our target production environment. These include functional, UAT, performance, penetration, extended gas day and DR testing. Final results are now being reviewed prior to stakeholder approval to enter cutover.. As part of this stream, phased delivery of some of the lower environments and associated infrastructure has been delivered within BAU successfully and these are now operational which was a big milestone for the delivery team. Second IDR was also completed successfully on 11th March. As part of this, data integrity was re-validated along with other infrastructure related scenarios executed to ensure final cut over plan has incorporated all learnings. Combination of these two activities have provided the project team with the confidence in our ability to complete cut over activities over the Easter weekend. Go live planning and readiness activities are now underway. Portal Go Live activities: The portal go live which was originally planned for 9th May has been re-scheduled to 18th June to minimise the impact to users and ensure better alignment with CSSC/DES deliveries. Final test cycles (penetration and DR tests) of the upgraded portal are underway. |  |  |  | Start of cutover cycle Entry into Post Implementation Support (PIS) Decommissioning Planning Portal solution test completion Portal solution IDRs & Implementation planning
e

## Slide 43: CMS Rebuild April Update
Update

## Slide 44: Progress to Date
The CMS Rebuild Team have commenced Sprint 1 and are now building out the foundations of the new CMS and the Shipper raised MNC (Meter Number Creation) Process.
The Customer Focus Groups have now been set up and communicated out. The first Customer Focus Group will cover a recap, objectives for these sessions and the ability to ask any questions on progress to date or the future development. In subsequent sessions we will ensure we have translated your requirements into our development, provide updates on progress, demos where appropriate, discuss any customer impacts and agree where change packs will be produced alongside agreeing the testing approach. We will provide the agenda at least 7 days ahead of the meeting so that you can ensure your relevant subject matters experts can attend where possible.
The Team are continuing the sizing exercise to determine what can be delivered in Q4 2022 alongside the Shipper raised MNC and the ToG Modification processes. As delivery will follow an Agile Framework, there is an option to deliver a Minimum Viable Product (MVP) initially with future releases improving the end-to-end functionality of that process.
Further updates will be provided in May ChMC.
Date | Time Start | Time end
06/04/2022 | 11:00 | 12:00
04/05/2022 | 11:00 | 12:00
10/06/2022 | 10:00 | 11:00
06/07/2022 | 10:00 | 12:00
09/08/2022 | 10:00 | 12:00
09/09/2022 | 10:00 | 12:00
14/10/2022 | 10:00 | 12:00
08/11/2022 | 10:00 | 12:00
09/12/2022 | 10:00 | 12:00
10/01/2023 | 10:00 | 12:00
07/02/2023 | 10:00 | 12:00
07/03/2023 | 10:00 | 12:00

## Slide 45: Section 6: AnY Other Business

## Slide 46: APPENDIX

## Slide 47: Portfolio POAP

## Slide 48: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5339 | EFT | 02/04/2022 | 3:45 | 02/04/2022 | 08:00 | This change will be the final upgrade to EFT PROD to keep the application in support. This extended outage will be on a Saturday and utilise the maintenance window for EFT to cause less impact to the industry. During the extended outage any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 9th April. | 13/09/2021 Times and description updated 13/04/2022
XRN 5339 | EFT | 21/05/2022 | TBC | 22/05/2022 | TBC | As part the Enhanced File Transfer (EFT) project we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgrade EFT. As EFT is a multiple site application we will have failed over, then failed back one site on the previous week, to complete the DR testing this weekend we will DR test the remaining site. Please be aware that the EFT DR Contingency Dates will be carried out on the following weekend. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. | 24/03/2022 Times and description updated 13/04/2022
XRN 5245 | UK Link | 15/04/2022 | 09:00 | 19/04/2022 | 07:00 | As part of UK Link Programme, an extended outage will be required to cutover UK Link system from the current On Premise Data Centres to the Cloud. This extended outage will be over the Easter weekend and therefore utilises Bank Holiday days in order to minimise impact to the Industry. Extended Outage is planned from 15th April 09:00 to 19th April 07:00 BST. Services will resume at 07:00 on Tuesday 19th April post maintenance schedule. As a result of this outage all external access to the online screens (via DES / Portal existing platform) will be unavailable during the window mentioned above Some file flow impacts are anticipated, these have been communicated via various forums and industry communications. All inbound files will be held in a queue at our EFT interface to be processed as soon as migration activities are complete as per the details communicated via the Change Pack. | 09/02/2022
XRN 5301 | UKLink Portal | 18/06/2022 | 09:00 | 20/06/2022 | 07:00 | As part of the UK Link move to Cloud Programme, an extended outage will be required to complete implementation and cutover activities for the new DES & Portal screens. These systems will be unavailable for use from 7th May 09:00 to 9th May 2022 7:00. | 09/02/2022
CHG0033559 | Gemini | 0406/2022 | 03:15 | 04/06/2022 | 07:30 | Gemini Disaster Recovery Test 2022 This is an annual activity to confirm Gemini services can be migrated to a secondary data centre location should there be a catastrophic failure within the primary data centre. During this phase of the test Gemini services will failover from the primary site to the secondary site. The activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 13/04/2022 New
CHG0033559 | Gemini | 05/06/2022 | 03:00 | 05/06/2022 | 07:30 | Gemini Disaster Recovery Test 2022 During this phase of the test Gemini services will failback from the secondary site to the primary site. Again the activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. NOTE: Contingency dates for these activities are 18th/19th June | 13/04/2022 New

## Slide 49: CSSC Programme Dashboard
April 2022

## Slide 50
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status We continue to closely monitor joint dependencies with the Move To Cloud Programme. Contingency planning is complete. Move to Cloud is on track to Go Live for it’s planned date. The bulk data cut for transition stage 1 has been issued to the CSSP ahead of the milestone date. The CSSP have acknowledged receipt and will now commence reconciliation activities. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini We are continuing to liaise with the Central Programme for CR-D130 and CR-D129. This week we have had a session with DCC to understand the CSSP process and functionality at gate closure. We were given some comfort during this session and now understand that the system will be fully monitored during gate closure especially during PIS in order to monitor and meet NFR’s and this will be undertaken on a daily basis. DCC are supportive of the CR we are raising in order have the capability to request the ‘re-send’ of a secured active message. We are pushing to receive this ability during early life support as this will help mitigate should we see missing messages at Gate Closure. CR-D129 was presented at the Ofgem Design Forum this week. This CR will be moved forward into the REC Governance process for a post Programme CR to be delivered within the REC releases. The design issues we have raised over the past couple of months have still not been responded to. We have escalated and will continue to monitor and escalate. We will now commence engagement in relation to the workaround process should we any issues with missing messages at the appropriate governance groups. Please note we are not expecting this to happen in normal day to day processing this would be an exceptional circumstance. |  |  |  | Internal Stage Gate D has been approved during the last two weeks. This stage gate is the closure of Testing and the commencement of Transition Commencement and planning refinement for the Transition Stage 2 activities (2nd May) Continued OAT Testing Continued Business Change activities
e

## Slide 51: Workstream Updates
RAG Previous month | RAG Current months | Work stream | SUMMARY
 |  | Transition | Transition stage 1 data migration activities completed, data shared with Landmark 4 days early. Landmark have returned Reg data, now being validated. The CSSC Implementation Approach and CSSC Transition Approach documents have been approved. Transition testing assurance ongoing Planning continues for stages 2 and 3, all workstreams to share their activities for actual transition planning for stages 2 and 3. Plan for Transition stage 2 due to be completed by 1st April.
 |  | Testing | Secondary Portal Functionality – Full Secondary Portal functionality handover 08/06/22 –DES and API workstream have advised that SIT testing can begin as incremental releases are planned. Meeting to be planned to discuss. DES4 – Functionality testing in progress 1 defect outstanding awaiting fix, Lazarus functionality testing is complete. External UEPT Test Execution Bespoke E2E – External UIT test phase complete, TCR has been signed off by OFGEM. Transition SIT (Regression) Functional testing – External Test Phase complete, Corella internal testing in progress (2 defects resolved, script retesting in progress), SME’s assurance in progress (Meter reads, billing and invoicing). External SIT - Supporting SI reporting Test Phase 18.0.4 planned for week commencing 4th April, we are supporting data creation and Retail Meet Point (RMP) status updates. Change Request – CR222, CR136, CR95a (additional GEA functionality), and CR172 in progress, Go Live Transition Stage 3 critical path CR’s Testing underway.
 |  | Non-Functional Test (Performance, operational acceptance testing and operational testing) | Amber trending to Green – OAT is progressing forward - Stream 1 Security (shared security analyst assigned and defects being progressed). Stream 2 Service management (Delivery expected 17th May and execution start). Stream 3 Back Up and Restore (align data restoration procedure), Stream 4 (DR) CSS API complete, DES & SEC API in progress. Stage Gate D milestone objectives completed, Integrated Pt to start pending successful SAP PO capacity upgrade retest. Transition Phase Confidence - 62 Amber OAT due to defects and resource issues. Resolution in progress with limited 1 day/week security resource. Dedicated CSSC security resource recruitment process in progress, required to return to green. PT – Phase 3 – DES Release 4 – Complete. PT – Phase 3 – Secondary APIs – Defects outstanding but expect resolve 6th April. PT – Phase 3 – Integrated PT – SAP PO blocker resolution is imminent, Test Phase to commence 4th April. PT – Phase 3 – Switchstream – ETF FOF2 deployment in progress (this section to be moved to Switchstream HLR)

## Slide 52: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | CSSC – UK Link | Change requests activities continues System Testing completed for CR0127 Nov21 retrofit release - Stage 2. Deployment of code changes for SIT Testing delayed due to BAU defects identified and issued for SME validationSystem Testing completed for CR0152 -Prime and Sub and deployed into QAS2. Validation of BAU defects identified for this CR underway by SMEs and TCS.. CR0095-GEA Process,CR0110 and CR0215 – Move in Job phase 2 Completed and deployed to QAS2. Testing team to confirm Gas day testing timelines for CR0215 CR0196 Notification of outstanding pending registrations post CSS gate closure on track for completion by 25/04. Session required with SMEs and TCS to finalize solution design queries. AMT have communicated revised release timelines for CSSC AMT IT086 - REL Data to Gas Transporters as 01/ Exceptions – Refresher session held with Tech Ops and SMEs on 28/03 to walk through latest position on exceptions. TCS to prepare a summary view of the Business and Technical exceptions collated and issue for Business and Tech Ops approval by 04/04. LWI update is in progress for existing exceptions ETA- 15/04
 |  | CSSC – API | APIs continue at Amber but only due to the ticketing solution build and readiness due to customer onboarding as we have a risk that not all customers have necessarily converted to the new solution.We are working with Customers to get their API’s converted to the new solution and test should they wish in advance of Programme Go Live. GAS Supply Switching API CR218 (to add 25 additional data items) has been completed and in SIT. The Developer portal has been updated to reflect the changes. Customers are being notified. Automated retry of APIs (Lazarus) continues to be tested Incorporation of the revised alerting solution requiring Grafana continues As per Des we are building out the ‘ticket’ solution. Design and planning completed General bug fix support continues System support documentation ongoing Secondary Portal development continues and currently on track to deliver. 1 Amber Transition Tracking relates to ‘Revised Logging to Replace eDoc Solution

## Slide 53: Workstream Updates
RAG previous month | RAG current months | Work stream | SUMMARY
 |  | Service Management | Preparations are ongoing and on track for Transition Phase 2 Service Now licences required and procurement is underway Full engagement with the Switching Programme continues Questions and knowledge transfer is occurring on a weekly basis via the SI led drop in sessions in readiness for Transition Phase (T1) Engagement happening with the Service Management Team within Tech Ops to get appropriate resolver groups set up to support T2 Two amber items on Transition Phase Confidence relate to Service Now procurement process but workstream overall at green
 |  | Early life support | PIS readiness ongoing Business Continuity Planning continues with the BCM Plan being shared across the wider business for review and approval Internal weekly workshop scheduled and on track for all internal business areas
 |  | Environments | The high number of environment issues recently encountered has subsided and all issues fixed AMT for PPTE5/Transition has been delivered; EFT configuration in progress. Consolidated Release Schedule is in progress
 |  | Batch | All E2E documents have been drafted, including the evidences and baseline documents these are currently under quality assurance checks ahead of being circulated for formal review The team are attending weekly huddles on the EFT Upgrade to obtain updates on the progress of the project and mitigate risk 66113 The batch jobs for PPTE4 have been configured but the team are awaiting confirmation for when these can be scheduled The team are waiting for the new EFT FOF environment to be delivered to commence the relevant configuration for PPTE4 Performance testing. An access request for this environment has been raised and completed

## Slide 54: Workstream Updates
RAG previous month | RAG Current month | Work stream | SUMMARY
 |  | Business Change | Overall status remains at amber for quality due to ​concerns raised by the business over some of the edge cases that may take play (Quality)​​ This will continue at amber until the first analysis of the unhappy path scenarios. Discussion ongoing with the Central Programme for these escalations Unhappy path workaround process to be presented to Industry at External Governance Workgroups Exceptions workshops are in flight, these workshops have gone through and reviewed all existing and new exceptions, the final sessions are now around a query raised by the business CR110 and also a new exception that has been raised. The final action which is currently sat with the Business Change workstream is SLA confirmation Continue to engage with customers re configuration of the new Switching API in advance of Go Live. Testing is available via sandbox environment All activities in the plan have been lined against the relevant transition and ELS stages
 |  | Gemini | Confirmation has been received that the Gemini annual file flow will be tested until EFT during the Performance Testing phase, currently planned for early Match Awaiting further conversations on late messages to progress with CR0043. If this change goes ahead communications will be planned with internal and external customers due to impacts to other systems Requests have been raised with the environments team for the relevant code and data to be deployment on to Gemini UT3 environment for Transition Stage 3 Connectivity test with UK Link will be planned for next week to ensure connectivity before Transition Testing Go Live

## Slide 55: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | DES | Overall DES workstream is Green and on track for Programme Delivery. Scope has turned amber in this period, as these has been a requirement to build an alternate eDOC ticket solution. Design, planning and milestones have been completed to include this solution in the overall plan. This build activity does not impact TS2 Devops build of the PREPROD and PROD environments in readiness for TS2 is on tgrack Activities between this workstream and M2C is progressing, however there has been a slight slippage. This slippage is in relation to the UK Link portal and will not affect M2C Go Live or CSSC Transition Stage 2.

## Slide 56: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Discussed at Delivery Group 25/01. Minutes pending. | 01/03/22
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 18/07/22
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | DCC engagement with DCC will ramp up in 2022 we will ensure reporting requirements are on the agenda | 25/02/22
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | SoLR impacts could manifest itself during the upcoming months - continues to be monitored | 31/03/22
65122 |  | Transition/ Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Continue to monitor, low exposure at this point | 28/02/22
66480 |  | Programme | There is a risk that the Go Live date could be pushed out further because of the current market situation in the Gas Industry with suppliers going out of business leading to additional cost to the programme, significant re-planning and impacts to other Correla initiatives | Regular communication with OFGEM to understand their strategy to address this issue | Continues to be monitored | 21/01/22

## Slide 57: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
66599 |  | Programme | There is a risk that the Transition phase of the Switching Programme may be adversely impacted as a result of SoLR activities consuming the focus and efforts of Business and Operational teams who had been planned to be focused on Switching Programme Transition activities leading to a potential impact to Transitional activities as planned currently (March 2022) | Liaise with Switching Programme stakeholders to agree mitigations | Continues to be monitored | 28/02/22
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | - Xoserve have raised CR-D129 to mitigate this risk. - Discussions ongoing with programme stakeholders | Session undertaken with Ofgem with actions in place. This will be tracked until mitigation actions are completed | 31/01/22
66907 |  | Programme | There is a risk that the SLAs stipulated with the CSS NFRs (1 Hr RTO) will not be met post CSS Go-live because REC is using the Switching BCDR document as the base for REC Service Definitions which has a 4 hour RTO defined with a maximum time of 8 hours for CSS to come back into operation leading to a massive impact on UK Link downstream processing, particularly with Gemini and settlement | This is being raised with REC and relevant Ofgem stakeholders | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 31/01/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | Awaiting updates re.RTO. Conversation also had with Programme Coordinator around this risk | 28/02/22

## Slide 58
High Level Plan

## Slide 59: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect newupdated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | £18,500.00 | 26/11/2021 | Approved - Internal CR Created

## Slide 60: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 61: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 62
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Withdrawn
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)

## Slide 63
CR Name | CR Ref | Date Raised | Status
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Complete - No Xoserve Impact
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)

## Slide 64
Chart: 
| 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830 | 43861 | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286 | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651 | 44681 | 44712 | 44742 | 44773 | 44804 | 44834 | 44865 | 44895 | 44926 | 44957 | 44985 | 45016
Monthly FORECAST (Cumulative) | 363976.7049 | 683029.7328 | 1009036.4267 | 1468927.7928 | 1881004.4782 | 2628016.161 | 3342082.9998 | 4458202.7929 | 5354403.925 | 6043381.565 | 7142885.7301 | 8975402.4212 | 10111304.7946 | 11388986.7429 | 13038342.2862 | 14439811.6996 | 15676651.4879 | 16871244.5253 | 18128098.1431 | 18805263.7779 | 19805071.2512 | 20880560.3257 | 21535839.521 | 22850035.6624 | 23700780.8305 | 25249490.822 | 26373752.79 | 27560286.1281 | 28743320.8196 | 29537803.1898 | 30384510.3162 | 31399998.3343 | 32343389.9958 | 33011201.9253 | 34179141.4549 | 35961286.4149 | 36970413.3716 | 38077439.8283 | 39047077.985 | 39697229.3417 | 40723492.277 | 41286767.058 | 42137791.4389 | 42359564.6551 | 42875681.6551 | 42875681.6551 | 42875681.6551 | 42875681.6551
Monthly BUDGET (Cumulative) | 489844.68 | 1174749.2 | 1918322.31 | 2859329.26 | 3600336.21 | 4373413.71 | 5301107.71 | 6054522.36 | 6844783.41 | 7587690.86 | 8469886.81 | 10016454.16 | 10772088.89 | 11466104.1 | 12171330.71 | 14216755.3 | 15951497.88 | 17098244.84 | 18223938.97 | 19242195.57 | 20253660.21 | 21199102.25 | 22074558.18 | 23123177.56 | 23700780.8305 | 25249490.822 | 26373752.79 | 27560286.1281 | 28743320.8196 | 29537803.1898 | 30384510.3162 | 31399998.3343 | 32343389.9958 | 33011201.9253 | 34179141.4549 | 35961286.4149 | 36970413.3716 | 38077439.8283 | 39047077.985 | 39697229.3417 | 40723492.277 | 41286767.058 | 42137791.4389 | 42359564.6551 | 42875681.6551 | 42875681.6551 | 42875681.6551 | 42875681.6551
Monthly ACTUALS (Cumulative) | 228433.92 | 548079.88 | 1260281.72 | 2160027.93 | 2928145.54 | 3938750.3 | 4855898.385 | 5889989.03 | 6410840.7 | 6911519.115 | 7785494.945 | 8810593.43 | 9969351.24 | 11012414.495 | 13032728.295 | 14595347.525 | 16039780.755 | 16876714.6283 | 18171730.1383 | 18895026.3383 | 20150164.6083 | 21211022.3383 | 21965343.9083 | 23586832.8183 | 24501593.2083 | 25721442.9683 | 26751681.8983 | 27948867.9383 | 29188022.9683 | 30035423.4583 | 30982878.6983 | 32234059.2067 | 33162576.7067 | 34260508.9567 | 35428448.4862 | 37210593.4463 | 38219720.403 | 39326746.8597 | 40296385.0164 | 40946536.3731 | 41972799.3083 | 42536074.0893 | 43387098.4703 | 43608871.6865 | 44124988.6865 | 44124988.6865 | 44124988.6865 | 44124988.6865
Total Approved Budget | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000