## Slide 1: Delivery Release Options for XRN5186 and XRN5091 and Possible Workarounds

## Slide 2: Purpose of ChMC Update
Summarise the analysis and options for delivery of XRN5091 (Deferral of creation of Class change reads at transfer of ownership) and XRN5186 (MOD0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs) in advance of a June 23 release
Share assessment of the impacts and risks to Customers of delivering XRN5091 and XRN5186 in advance of June 23
Share potential workaround options to reduce the impacts of a June 23 release for XRN5091 and XRN5186
Seek a decision on release options for delivery including workarounds
Appendices: Split phased delivery for XRN5186 and Impact assessments that has been shared previously on XRN5186 and XRN5091

## Slide 3: Summary
Change | De-risked earlier implementation | Workaround | Options | Recommendation
5091 Deferral of creation of Class change reads at transfer of ownership | No options have been identified to deliver earlier than June 23 safely | No workarounds have been identified which provide a material benefit | Deliver in a June 23 release Deliver in Feb 23 Release at High Risk | Xoserve continues to recommend Option 1
5186 MOD0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | A split phased option had been identified to safely deliver part of the change earlier. However, as the implementation of a MOD can not be split this is not an option (see slide 11) | A partial workaround has been identified which can provide a material benefit to Shippers (see slide 7). | Deliver in a June 23 release Deliver Feb 23 Release at High Risk Deliver in a June 23 release partially mitigated by a workaround | Xoserve recommends Option 3
Xoserve have investigated options to deliver XRN5091 and XRN5186 earlier than a June 23 release. In addition any manual workarounds have also been investigated to identify whether a material benefit can be identified in lieu of any system change.

## Slide 4
Risks and Impacts to Customers of Delivering XRN5091 in advance of June 23
XRN | Change Description | Brief description why the change impacts CSS/CSSC | Common Business Processes with CSS
5091 | Retaining the opening read window when there is a switch/registrations that results in a change in Class from Class 3 to 4 or from Class 4 to 3 allowing Shippers to submit an opening read. | As part of CSSC the opening read window is changing which impacts SPA and introduces new validations to Reads and RGMA transactions. XRN5091 will need to change SPA when there is a resultant class change and will need to update the validations to Reads and RGMA transactions. | SPA workflow Read processing (UMR, UBR, AQI, Must Reads) RGMA processing (ONUPD, ONJOB)
Risks to Customers | Impacts to Customers of Delivery earlier than June 23 Release | Impacts to Customer of delivering in June 23 Release
Delivering earlier than June 23 Release creates the following key risks as Nov22 delivery will start Build and Test before CSS Go Live and Feb23 delivery will undertake Build and Test in parallel with CSS PIS: CSSC processes will not be embedded meaning that confidence of success will be reduced for XRN5091 As XRN5091 is building on CSS code, changes in CSS PIS will result in a delay to XRN5091 delivery timescales to allow for the Build, Test and Implementation of the CSS change Code changes during PIS by CSSC may cause a conflict i.e. code might stop working for key processes, or changes would need be retro-fitted to the project track which can lead to code changes for XRN5091, resulting in rework of Design, Build and Test. We may not have stable system performance in CSS PIS which will would impact our ability to Performance Test XRN5091 | The following could occur based on the risks identified: Changes in CSSC post Go Live may result in the: change being undone when XRN5091 Goes Live. Depending on the criticality of the CSSC change this could impact consumer switching ability or consequential changes required on XRN5091. This may result in significant delays due to the associated rework in Design, Build and Test Increased costs and timelines to deliver XRN5091 and risk of not delivering within the release window The change may need to be backed out if there is a negative impact on CSSC performance | Not compliant with UNC rules relating to the opening read window until June 2023 Shippers will not be able to submit opening reads when there is a switch with a resultant class change until June 23. CSS Go Live could result in more instances of switching with a resultant class change.

## Slide 5
Ref | Workaround | Customer Benefit | Gap | Cost
WA5091_01 | Generate a daily report to Shippers for any MPRN where there has been a registration with a class change from 3 to 4 or 4 to 3 | Shippers will be aware when a registration has resulted in a class change which will close the opening read window | 1. Shippers will not be able to prevent the estimated read from being generated on D 2. Report would have to be productionised due to the volume of switches | Medium
WA5091_02 | Generate a daily report to Shippers for any MPRN where there is a pending registration with a class change from 3 to 4 or 4 to 3 | Shippers will be aware when a registration has resulted in a class change which will close the opening read window | 1. Shippers will not be able to prevent the estimated read from being generated on D 2. Report would have to be productionised due to the volume of switches 3. If the report is issued prior to D-1 then the registration may be cancelled or another BRN could be received with a different class | Medium
Workarounds Assessed and Discounted for XRN5091
Without system changes to CSSC there isn’t a workaround which will allow incoming Shippers to provide an opening read without using the Shipper Agreed Reads process.
The above workarounds have been identified which will provide incoming Shippers visibility of where a switch/registration results in a class change however Shippers will not be able to prevent the generation of an estimated read which subsequently closes the opening read window.

## Slide 6
Risks and Impacts to Customers of Delivering XRN5186 in advance of June 23
XRN | Change Description | Brief description why the change impacts CSS/CSSC | Common Business Processes with CSS
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | CSSC is introducing new processes (nomination, settlement details, associating settlement details, default values to switch or registration) to support settlement processes. These new processes will need to be updated to add in further validations to ensure that the capacity is not set higher than the NExA. | These can apply to a Change of Shipper and/or Change of Supplier, Initial Registration, Auto Confirmation 1. Nominations 2. Base Registration Nominations 3. Associating settlement details to a switch/registration 4. Default settlement values 5. DES moving to GES 6. Default values used in a switch/registration
Key Risks to Customers | Key Impacts to Customers of Delivery in advance of June 23 Release | Impacts to Customer of delivering in June 23 Release
Please note the Key Risks are the same as XRN5091 Delivering earlier than June 23 Release creates the following key risks as Nov22 delivery will start Build and Test before CSS Go Live and Feb23 delivery will undertake Build and Test in parallel with CSS PIS: CSSC processes will not be embedded meaning that confidence of success will be reduced for XRN5186 As XRN5186 is building on CSS code, changes in CSS PIS will result in a delay to XRN5186 delivery timescales to allow for the Build, Test and Implementation of the CSS change Code changes during PIS by CSSC may cause a conflict i.e. code might stop working for key processes, or changes would need be retro-fitted to the project track which can lead to code changes for XRN5186, resulting in rework of Design, Build and Test. We may not have stable system performance in CSS PIS which will would impact our ability to Performance Test XRN5186 | Please note the Key Impacts are the same as XRN5091 The following could occur based on the risks identified: Changes in CSSC post Go Live may result in the: change being undone when XRN5186 Goes Live. Depending on the criticality of the CSSC change this could impact consumer switching ability or consequential changes required on XRN5186. This may result in significant delays due to the associated rework in Design, Build and Test Increased costs and timelines to deliver XRN5186 and risk of not delivering within the release window The change may need to be backed out if there is a negative impact on CSSC performance | MOD0701 cannot be implemented until June 2023. Capacity can could exceed the capacity in the NExA until June 2023

## Slide 7
Ref | Workaround | Customer Benefit | Gap | Cost
WA5186_01 | Obtain the additional NExA information from Networks and manually check against current capacity. This would then be completed in regular intervals (weekly/monthly) against the current capacity and any inflight processes until full functionality is delivered. Any capacity that is / due to exceed the capacity in the NExA will be shared with the relevant customers (DN and Shipper). | 1. Will identify any capacity currently set higher that the NExA sooner than delivery timescales. 2. Can identify any NExA sites that are not valid. 3. In-flight processes could be cancelled by the Shipper to prevent the capacity being set higher than the NExA 4. Will provide visibility of any capacity set higher than the NExA capacity | 1. The capacity can still be set higher than the NExA 2. This activity would need to take place multiple times until the full solution is implemented due to processes being able to increase capacity. 3. Networks will need to provide the data to CDSP early | Low
Workarounds Assessed and Viable for XRN5186
The benefits of this workaround are dependant on customer action.

## Slide 8: Decisions
Change | Recommendation | Decision
5091 | Prepare XRN5091 for delivery in June 23 Release | Prepare for delivery in Feb 23 Release - Approve or Reject Prepare for delivery in Jun 23 Release - Approve or Reject
5186 | Prepare XRN5186 for delivery in June 23 Release | Prepare for delivery in Feb 23 Release- Approve or Reject Prepare for delivery in Jun 23 Release - Approve or Reject
Change | Recommendation | Decision
5186 | Develop partial workaround with costs and timelines for delivery ASAP | Approve or Reject
If decision is to deliver XRN5186 in June 23 Release then:

## Slide 9: Proposed Next Steps
Present BERs for approval with the inclusion of XRN5091 and XRN5186
  For approval in July or August ChMC if February 23 Release
  For approval in November or December ChMC if June 23 Release
Provide Costs and Timelines of workaround if requested

## Slide 10: Appendices for Information

## Slide 11
Options for Delivering XRN5186 in advance of June 23
Option | Description | Pros | Cons
Option 1. Deliver XRN5186 and XRN5091 in June 23 Release | Full delivery of XRN5186 in June 23 | Synergies in delivery costs of delivering XRN5186 and XRN5091 together CSSC code is more stable reducing the risks & impacts identified in slide 3 Xoserve resources can focus on change as not dependent on volume of CSSC impacts in PIS safeguarding delivery timescales and costs | Does not meet obligations of UNC MOD 0701 until June 23
Option 2. Split XRN5186 into 2 phases Phase 1 Feb 23 Phase 2 June 23 | Delivery of elements less impacted by CSS/CSSC in Phase 1. This includes: Validations to capacity amendments Validations to class change requests Ratchet changes Change to PMN file to notify DNs when the PMSOQ has been capped at the NExA All reporting elements Update to DES/GES with NExA details Phase 2 include: Nomination validations added Confirmation validations added BRN validations added ASN validations added Default rules validations added | Provide functionality improvements to Customers Limits processes that can set the capacity higher than the NExA limits Shipper from paying for capacity they can’t use Capacity reduction window will be open allowing Shippers to reduce capacity when higher that the NExA Ratchets will prevent the capacity being set higher than the NExA Partially meets the obligations of UNC MOD 0701 in February 2023 | Will not fully meet the obligations of UNC MOD 0701 in Feb 2023 Customers have not agreed to Feb 23 functionality release More expensive to deliver: Loss of synergies in delivering XRN5091 in parallel More testing and potential re-work Duplication of effort due to undertaking delivery phases twice Capacity can be still be set higher than the NExA until June 23
The implementation of a MOD cannot be split and therefore, as Option 2 only provides partial MOD obligations in Feb 23, Option 2 is not feasible.

## Slide 12
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework if Delivered Earlier than June 2023
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | Red | Amber/Red | SPA (all workflows CONF, change shipper and Supplier), Metering (UMR, UBR reads, AQI, Must Reads), RGMA | Common code/functionality with CSSC is: SPA, Reads (UMR, UBR), RGMA | Very High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required for XRN 5091 and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans XRN5091 also has extensive UAT and regression phases which may extend/need retesting due to any potential CSSC defects and/or CRs
Impact and risk of inclusion of XRN5091 in Nov22 and Feb23 Release

## Slide 13
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework
XRN5186 MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs Detailed Design | Red | Red | A number of key processes are undergoing change : Registration( Nom, Change of Supplier, Shipper change, Ratchets) | Touches large part of CSSC code Change touches Nomination/BRN | High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans Workflow defects in CSSC may need some code changes for 5186
Impact and risk of inclusion of XRN5186 in Nov22 and Feb23 Release