## Slide 1: XRN5231 Flow Weighted Average CV
May 22 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at purple. Project is in re-plan due to the issue that 1st April 22 implementation date was not met. The project has continued with its planned activities alongside the replan for the FWACV service & Gemini consequential changes. Several clarifications are still being discussed in conjunction with Xoserve & Customers alongside the Change Pack. Change Pack consultation closed on 28/03; review of reps completed, and this will be submitted for approval at the April ChMC to rebaseline the scope, plan and BER of the project. UAT continues to make progress with the assurance of test cases not impacted by scope change. Blocked test cases will be completed as part of the replan Dual Run Phase 2 commenced but lack of full DN connectivity to provide daily files is now causing an issue for having the files/data to validate to the existing NG service. Only NG & NGN are fully connected with NGN providing the required daily files. Issue raised at the Focus Group on 29/03. This is now an issue as the phase 2 plan is not giving the confidence planned, though testing will commence with 2 connected shippers and progress monitored Re-plan in progress to include full impact assessment. Revised supplier costs received and in review. MTB cost assessment of the additional requirements to support manual processes are drafted and are being assessed to confirm MTB uplift required. Gemini consequential changes assessment defined and is part of the re-plan and revised BER Business Readiness and Service Transition work continues as per the plan Risk of FWACV Imp to CSSC assessment completed and confirmed that no risk to CSSC Transition & Cutover plans if implemented in June 2022 Next Steps: Finalise full re-plan from the changes to scope and requirements to define the revised plan and BER Continue Cutover & Transition scenarios with NG and DNs to define scope, plan and acceptance criteria Outstanding DNs to complete End To End connectivity to provide daily files to remove issue with DR/MT plan Continue with UAT assurance, DR/MT and Business Change planned activities Revised BER from re-plan to be approved at an extraordinary ChMC (to be agreed) | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  | Replan in progress to finalise the revised dates of the project. The project continues to progress key phases/activities (eg UAT assurance, DR/MT, Business Change (inc External Training) and Cutover & Transition planning) | 
Risks and Issues | There is an issue that NG and DNs do not understand the consequential changes with the removal of the FWACV service from NG and the impact to existing business processes – Update – Action for NG & DNs to review the consequences of the FWACV service moving from NG to Xoserve. This is key to understand any impacts to business/system processes as part of individual organisation Business Readiness plans There is a risk that changes to the approved scope and requirements and subsequent replan may put at risk a Mid June 2022 Go Live of the new Xoserve service – Update – Replan in progress There is an issue with Dual Run/Market Trials phase that only 1 DN is fully connected to provide daily files, this is now causing an issue with transactional date being out of synch due to only 1 DNs providing daily files to compare to NGs service running in production – Update – Continued engagement to work through connectivity is being progressed with impacted DNs and NG to provide support. Phase 2 to progress with 2 connected shippers There is a risk that changes to the baselined scope and requirements will increase the costs of the new FWACV service in extending the project and manual process being identified – Update – The impact assessment to define the re-plan and revised business case is in progress to conclude the revised BER for review & approval with customers | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecast costs tracking to approved BER costs at present. Revised plan options will lead to updated costs which will be agreed in a revised BER for review & approval | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) – Change to scope and requirements in impact assessment Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  |