## Slide 1: Change Management Committee
8th June 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Budget v Committed Spend BP22
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 154400 | 56800 | 8800 | 0
Uncommitted | 1724961.4529 | 1074896.3319 | 168102.9397 | 66021.5255
Full view of budget here

## Slide 5: Change Pipeline

## Slide 6: Change Development & Delivery Pipeline (DSC Change / Minor Release Budget)
* Pre-capture may contain changes that won’t require delivery / funding
Chart: Change Development
| Capture | Initial Review | Pre-capture
Total | 17 | 3 | 17
Chart: Delivery Pipeline
| CSSC | Standalone | Unallocated
Total | 4 | 9 | 9
Chart: Changes From Last Period
| New Mod | New CP | MOD to be implemented | Withdrawn
Total | 1 | 3 | 4 | 2

## Slide 7
2021-2022 DSC Change / MiR Pipeline
Key:
On Track
Potential Activity
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
Planning

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals
For Approval:
XRN5515 - Hydeploy close down (links to XRN 5014)
XRN5517 - Hydrogen checker website
XRN5455 - Implementation of Entry Capacity Assignments Process (UNC0779/779A)
XRN5316 - Rejecting a replacement read with a pre-Line in the Sand (LIS) read date
Change Proposal Updates
DSC Service Lines Update (XRN5505 – Amendments to the Service Description table v24)

## Slide 10: XRN5515 - Hydeploy close down (links to XRN 5014)
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Northern Gas
Change Description
As part of XRN5014, the effected Supply Meter Points within the HyDeploy2 Live Pilot had an “AQ Backstop” set to retain the integrity of the AQ while the supply meter point was consuming 20% Hydrogen Blend. HyDeploy2 Live Pilot has now finished, so there is a need for the ‘AQ Backstop’ to be removed, ensured that there has been no detrimental impact on the SMP AQs values, and the balancing/settlement process has been unaffected, as per original project plan. Discussion are ongoing and confirmation from NGN when the invoicing payments will stop will dictate the delivery date for this change as both would need to be in alignment. Confirm that no backend processes are still utilising the HyDeploy2 flag (as flag needs to remain) to treat these MPRN’s differently to a standard MPRN.
Change Type | Non-Regulatory
Priority Score | Low
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 

## Slide 11: XRN5517 - Hydrogen checker website
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Cadent
Change Description
Design website options – need something like Findmysupplier, where an end consumer can enter address details and determine if Hydrogen is available currently, or see when it is coming, and log interest in becoming a Hydrogen consumer. This should be for both domestic and I&C consumers if possible. Something similar was built by BT for the rollout of broadband. Ideally needs to show the same details as Findmysupplier but with the addition of a hydrogen ready section.
Change Type | Non-Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 

## Slide 12: XRN5455 - Implementation of Entry Capacity Assignments Process (UNC0779/779A)
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | National Grid
Change Description
Implementation of UNC Modification 0779/0779A as per the solutions set out in the modifications and subsequent requirement gathering workshops. The proposal from this CP should align and integrate with NG’s agile framework of change delivery. UNC 0779 / 0779A: Introduction of Entry Capacity Assignments or alternatively Introduction of Entry Capacity Assignments with defined end dates – Inflight Modification Proposals - Please see the Change Proposal for the full Change Description
Change Type | Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | X
IGT’s | 

## Slide 13: XRN5316 - Rejecting a replacement read with a pre-Line in the Sand (LIS) read date
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
This change seeks to reject replacement Meter Reads, using an existing rejection code, provided by either the DMSP or Shipper User where the read date is prior to the current LIS date. The LIS date is set each year and estimated reads are generated for 01/04/YYYY where no reading(s) exist for 3 years prior to the new LIS date and no reading exists after this date. Therefore, where there is no estimated or actual LIS read, then the read immediately prior to the LIS date will remain a valid read to be replaced and subject to all other read validations and reconciliation/invoicing processes. In these cases, re-reconciliation will be triggered to correct the post LIS period, only.
Change Type | Non - Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 14: • XRN5505 – Amendments to the Service description Table v24 - Update
Change Management Committee
June 2022

## Slide 15: DSC Service Lines
Mod 0804 Consultation closed out on 1st April 2022 – no detailed comments raised regarding the UNC drafting
Stable version of the SCR text against which to assess the DSC Service Lines
Change raised with Change Management Committee – 28th April 2022 – with a view to seeking approval at the May Contract Management Committee
  Propose 10 New Service Lines due to CSS – NB: plus further Service Line related to 0728B CNCCD
  Moving of 1 Service Line from Direct Service Code Services to Agency Services Non Code
  Amendments to a large number of Service Lines to reflect new Code References / terminology change for CSS Supply Points
Amendments to ‘Agency Services GT and IGT - Non-Code’
  Deletions of 5 Agency Services GT Non Code Service Lines, and 2 from ASIGTNC
  New Service Lines will be required
Amendments to ‘Specific Services’
  Deletion of some existing Service Lines

## Slide 16: DSC Service Lines
It is planned that this change will be approved at the June CoMC

## Slide 17: Why is this relevant to ChMC?
When we are making changes to the Service Description Table we raised a change, XRN5505, and this was presented to this Committee ‘for information’
This change is slightly different, we have also circulated three documents in the Change Pack on 16th May 2022 (3035.1-MT-PO- CSSC UKLM Updates) – two of which are relevant to the SDT documentation as the UKLM is cross referenced
  UKLCD1 - Code Communications Reference
  UKLBD2 UK Link IS Service Definition
These documents sought to consistently define:
  the SLAs
  the maximum design volumes for the new processes

## Slide 18: Why is this relevant to ChMC?
An amendment to the version of the document issued in the 16th May change pack was communicated on 25th May…
This sought to clarify the SLA end time (in addition to the start time that we had already defined):

## Slide 19: Direct Services Code Services
Following CSS DSC SLs are proposed:

## Slide 20: Direct Services Code Services
Further Service Line added as a result of 0728B to reflect the CNCCD:
Following DSC Service Line is proposed to be moved to Agency Services Non Code:

## Slide 21: Agency Services GT / IGT - Non-Code
A number of new obligations are placed on the CDSP as the GRDA in the REC, expect that we will require New Service Lines to reflect these
We think that this is the correct approach:
  Non Code as it’s REC, not UNC
  [Doing these activities to ultimately meet your obligation in the Licence]
  [Consistent with where other REC Obligations reside]
Proposed Deletions from the Agency Services GT/IGT Non Code
  RDP File removal
  SPAA Schedule 23 / REC Transition Schedule DES Services

## Slide 22: Agency Services GT/IGT - Non-Code
Proposed Service Lines:
  Notification of Registerable Metering Point Data to CSS
    RMP Creation / move into scope of CSS
    MPL Address Change detail
    RMP Status Notification – incl Transformation of MP Status / Isolation Status / Meter Status
  Provision of [Regulatory Alliance] Data to CSS - (collated by the CDSP under the UNC as Shipper-Transporter Alliance Data G 5.8)
  Provision of a Registration Block Notice or Withdrawal of a Registration Block Notice – following update by Transporter (G5.8 / V3.3.29(c) / S3.5.3)
  Provision of [Commercial Alliance] Data to CSS - (collated by the CDSP under the UNC as Supplier-Shipper Alliance Data G 5.7)
  Notification of Supplier Agent Appointment to CSS
    MEM [and MAP] data to CSS
  Reporting on GRDA Performance for REC Performance Assurance Board
  Receipt of messages by GRDA from CSS

## Slide 23: Agency Services GT/IGT - Non-Code
As above - Proposed Service Lines:

## Slide 24: Agency Services GT/IGT - Non-Code
Service Lines proposed for deletion:
  Reference to SPAA Schedule 23 can be removed – other ‘Information Services’ have retained Service Lines**
  RDP File to DCC is being decommissioned
  Xoserve was required to execute confidentiality agreements – as responsibility transfers to REC (RECCo) then this is not relevant to be retained**
** - An equivalent Agency Services IGT Non Code Service did not exist

## Slide 25: Specific Services
To reflect the movement of services into the Gas Enquiry Service the following lines are proposed to be deleted:
Please note that this includes the MNumber Data File Service.

## Slide 26: Questions?

## Slide 27: section 4. Design & Delivery

## Slide 28: Design Change Pack
For Approval:
XRN4900 – Biomethane Sites with Reduced Propane Injection
XRN4992b – Modification 0797 (Urgent)
CSSC – UK Link Manual updates
XRN4990 - Transfer of Sites with Low Read Submission Performance -MOD0664

## Slide 29: XRN4900 – Biomethane Sites with Reduced Propane Injection
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3034.1 - MT - PO | DNO | Shipper, DNO | February 2023 (TBC) | CP | 1 |  | 
Organisation | Status | Comments
Wales and West | Approve | In the XRN4900 detailed design the CV range is proposed to be between 36-43. Currently, WWU sends a CV of 35 to indicate an invalid CV rather than sending a blank field. Therefore we request that the CV range is amended to incorporate this. Is the CV range hard coded or parameterised? This might enable a more flexible solution to allow hydrogen projects in the future.
SGN | Approve | In response to the question posed to DNs by Xoserve "Does the range of CV (36-43) meet the needs of any biomethane site?" The CV range will meet the needs of the solution to be used within the settlement and billing processes. Although a default CV of 35 is sent by Biomethane sites as an indication of a zero flow the range proposed for this process will ensure that any submissions of this value will be excluded from the solution calculation.

## Slide 30: XRN4992b – Modification 0797 (Urgent) – Last Resort Supply Payments Volumetric Charges (Enduring Solution)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3034.2 - MT - PO | Shipper? | Shipper, DNO | TBC | CP | 1 |  | 
Organisation | Status | Comments
Wales and West Utilities | Approve | In general, we support the detailed design for this change (XRN4992b) but have the following points that need to be resolved: Invoice type- It is mentioned in the design that the current invoice type is ANC when actually it is an INR invoice type. The slides presented at DSG on the 23.5.22 stated 'Any under or over recovery through the SoLR Customer Charge will be managed by the Distribution Networks via the K balancing mechanism'. This is not correct, it will be recovered under the process described in standard special condition A48.
EON | Support with comments | We are supportive of now moving to an enduring solution but have the following comments: 1. There needs to be test files for invoices (CAZ) and market testing for this following the issues loading the interim files, there needs to be a clear plan when these will be released so it can be linked into Representation the plan and work around the Xmas code freeze (as it is a Feb release). 2. There needs to be test files for backing files (ZCS) and market testing for this as the interim process didn’t have backing data, like the invoice testing there needs to be a clear plan on testing as part of delivery. 3. We are a bit concerned about post-implementation support. As this is proposed to be released in the Feb '23 major release, the first invoices won't be received until May which would usually be outside the period for post implementation support.

## Slide 31: XRN4990 - Transfer of Sites with Low Read Submission Performance - MOD0664
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3034.3 - MT - PO | Service Area 3 90% Shipper, 10% DNO | Shipper | Proposed Nov 22 | CP | 1 |  | 
Organisation | Status | Comments
EDF | Approve | In the supply point read benchmarks - if one is not hit for example aggregate is not met but individual is met, would all of the MPRNs in the aggregate be moved class irrespective of individual MPRNs hitting their target measures? Could we have some further clarification on the benchmarks please?
Centrica |  | Please clarify, does a site need to be Class 2 or 3 for a full calendar month before being considered for performance? For example, Supply Point is class changed to Class 3 mid January, the first 3 months of performance to be considered will be February, March, April? It also states that the CDSP will halt Class change activity to Class 2 or 3 after the 20th business day. Please confirm, if a Supply Point has to be effective for a full month to be considered in performance (as with other DDP reporting, has to be a full month to be considered for performance) Class 2 sites have D+5 days to submit actuals read. However, in this modification Class 2 sites have a failure after D+1, This is not acceptable as it will impact sites with intermittent comms that submit actual reads within the UNC specified D+5. The lack of transparency for service cost for the CDSP to move sites is not acceptable. There is no indication on price; Please confirm the difference in approach. Please confirm why we should not move them using DDP reports for other admin charges, like changing monthly read frequency as per MOD 0692

## Slide 32: CSSC - UK Link Manual updates
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3035.1 - MT - PO | CSSC | Shipper | CSS Implementation Date – July 2022 | CP |  |  | 
Organisation | Status | Comments
 |  | No representations yet.

## Slide 33: Standalone Change Documents for Approval (BER, CCR, EQR)
CCR for XRN5458 - Contingency Gas Procurement Arrangements when a Supplier acts under a Deed of Undertaking
BER for XRN5516 – November 22 Major Release Scope

## Slide 34: Delivery Release Options for XRN5186 and XRN5091 and Possible Workarounds

## Slide 35: Purpose of ChMC Update
Summarise the analysis and options for delivery of XRN5091 (Deferral of creation of Class change reads at transfer of ownership) and XRN5186 (MOD0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs) in advance of a June 23 release
Share assessment of the impacts and risks to Customers of delivering XRN5091 and XRN5186 in advance of June 23
Share potential workaround options to reduce the impacts of a June 23 release for XRN5091 and XRN5186
Seek a decision on release options for delivery including workarounds
Appendices: Split phased delivery for XRN5186 and Impact assessments that has been shared previously on XRN5186 and XRN5091

## Slide 36: Summary
Change | De-risked earlier implementation | Workaround | Options | Recommendation
5091 Deferral of creation of Class change reads at transfer of ownership | No options have been identified to deliver earlier than June 23 safely | No workarounds have been identified which provide a material benefit | Deliver in a June 23 release Deliver in Feb 23 Release at High Risk | Xoserve continues to recommend Option 1
5186 MOD0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | A split phased option had been identified to safely deliver part of the change earlier. However, as the implementation of a MOD can not be split this is not an option (see slide 11) | A partial workaround has been identified which can provide a material benefit to Shippers (see slide 7). | Deliver in a June 23 release Deliver Feb 23 Release at High Risk Deliver in a June 23 release partially mitigated by a workaround | Xoserve recommends Option 3
Xoserve have investigated options to deliver XRN5091 and XRN5186 earlier than a June 23 release. In addition any manual workarounds have also been investigated to identify whether a material benefit can be identified in lieu of any system change.

## Slide 37
Risks and Impacts to Customers of Delivering XRN5091 in advance of June 23
XRN | Change Description | Brief description why the change impacts CSS/CSSC | Common Business Processes with CSS
5091 | Retaining the opening read window when there is a switch/registrations that results in a change in Class from Class 3 to 4 or from Class 4 to 3 allowing Shippers to submit an opening read. | As part of CSSC the opening read window is changing which impacts SPA and introduces new validations to Reads and RGMA transactions. XRN5091 will need to change SPA when there is a resultant class change and will need to update the validations to Reads and RGMA transactions. | SPA workflow Read processing (UMR, UBR, AQI, Must Reads) RGMA processing (ONUPD, ONJOB)
Risks to Customers | Impacts to Customers of Delivery earlier than June 23 Release | Impacts to Customer of delivering in June 23 Release
Delivering earlier than June 23 Release creates the following key risks as Nov22 delivery will start Build and Test before CSS Go Live and Feb23 delivery will undertake Build and Test in parallel with CSS PIS: CSSC processes will not be embedded meaning that confidence of success will be reduced for XRN5091 As XRN5091 is building on CSS code, changes in CSS PIS will result in a delay to XRN5091 delivery timescales to allow for the Build, Test and Implementation of the CSS change Code changes during PIS by CSSC may cause a conflict i.e. code might stop working for key processes, or changes would need be retro-fitted to the project track which can lead to code changes for XRN5091, resulting in rework of Design, Build and Test. We may not have stable system performance in CSS PIS which will would impact our ability to Performance Test XRN5091 | The following could occur based on the risks identified: Changes in CSSC post Go Live may result in the: change being undone when XRN5091 Goes Live. Depending on the criticality of the CSSC change this could impact consumer switching ability or consequential changes required on XRN5091. This may result in significant delays due to the associated rework in Design, Build and Test Increased costs and timelines to deliver XRN5091 and risk of not delivering within the release window The change may need to be backed out if there is a negative impact on CSSC performance | Not compliant with UNC rules relating to the opening read window until June 2023 Shippers will not be able to submit opening reads when there is a switch with a resultant class change until June 23. CSS Go Live could result in more instances of switching with a resultant class change.

## Slide 38
Ref | Workaround | Customer Benefit | Gap | Cost
WA5091_01 | Generate a daily report to Shippers for any MPRN where there has been a registration with a class change from 3 to 4 or 4 to 3 | Shippers will be aware when a registration has resulted in a class change which will close the opening read window | 1. Shippers will not be able to prevent the estimated read from being generated on D 2. Report would have to be productionised due to the volume of switches | Medium
WA5091_02 | Generate a daily report to Shippers for any MPRN where there is a pending registration with a class change from 3 to 4 or 4 to 3 | Shippers will be aware when a registration has resulted in a class change which will close the opening read window | 1. Shippers will not be able to prevent the estimated read from being generated on D 2. Report would have to be productionised due to the volume of switches 3. If the report is issued prior to D-1 then the registration may be cancelled or another BRN could be received with a different class | Medium
Workarounds Assessed and Discounted for XRN5091
Without system changes to CSSC there isn’t a workaround which will allow incoming Shippers to provide an opening read without using the Shipper Agreed Reads process.
The above workarounds have been identified which will provide incoming Shippers visibility of where a switch/registration results in a class change however Shippers will not be able to prevent the generation of an estimated read which subsequently closes the opening read window.

## Slide 39
Risks and Impacts to Customers of Delivering XRN5186 in advance of June 23
XRN | Change Description | Brief description why the change impacts CSS/CSSC | Common Business Processes with CSS
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | CSSC is introducing new processes (nomination, settlement details, associating settlement details, default values to switch or registration) to support settlement processes. These new processes will need to be updated to add in further validations to ensure that the capacity is not set higher than the NExA. | These can apply to a Change of Shipper and/or Change of Supplier, Initial Registration, Auto Confirmation 1. Nominations 2. Base Registration Nominations 3. Associating settlement details to a switch/registration 4. Default settlement values 5. DES moving to GES 6. Default values used in a switch/registration
Key Risks to Customers | Key Impacts to Customers of Delivery in advance of June 23 Release | Impacts to Customer of delivering in June 23 Release
Please note the Key Risks are the same as XRN5091 Delivering earlier than June 23 Release creates the following key risks as Nov22 delivery will start Build and Test before CSS Go Live and Feb23 delivery will undertake Build and Test in parallel with CSS PIS: CSSC processes will not be embedded meaning that confidence of success will be reduced for XRN5186 As XRN5186 is building on CSS code, changes in CSS PIS will result in a delay to XRN5186 delivery timescales to allow for the Build, Test and Implementation of the CSS change Code changes during PIS by CSSC may cause a conflict i.e. code might stop working for key processes, or changes would need be retro-fitted to the project track which can lead to code changes for XRN5186, resulting in rework of Design, Build and Test. We may not have stable system performance in CSS PIS which will would impact our ability to Performance Test XRN5186 | Please note the Key Impacts are the same as XRN5091 The following could occur based on the risks identified: Changes in CSSC post Go Live may result in the: change being undone when XRN5186 Goes Live. Depending on the criticality of the CSSC change this could impact consumer switching ability or consequential changes required on XRN5186. This may result in significant delays due to the associated rework in Design, Build and Test Increased costs and timelines to deliver XRN5186 and risk of not delivering within the release window The change may need to be backed out if there is a negative impact on CSSC performance | MOD0701 cannot be implemented until June 2023. Capacity can could exceed the capacity in the NExA until June 2023

## Slide 40
Ref | Workaround | Customer Benefit | Gap | Cost
WA5186_01 | Obtain the additional NExA information from Networks and manually check against current capacity. This would then be completed in regular intervals (weekly/monthly) against the current capacity and any inflight processes until full functionality is delivered. Any capacity that is / due to exceed the capacity in the NExA will be shared with the relevant customers (DN and Shipper). | 1. Will identify any capacity currently set higher that the NExA sooner than delivery timescales. 2. Can identify any NExA sites that are not valid. 3. In-flight processes could be cancelled by the Shipper to prevent the capacity being set higher than the NExA 4. Will provide visibility of any capacity set higher than the NExA capacity | 1. The capacity can still be set higher than the NExA 2. This activity would need to take place multiple times until the full solution is implemented due to processes being able to increase capacity. 3. Networks will need to provide the data to CDSP early | Low
Workarounds Assessed and Viable for XRN5186
The benefits of this workaround are dependant on customer action.

## Slide 41: Decisions
Change | Recommendation | Decision
5091 | Prepare XRN5091 for delivery in June 23 Release | Prepare for delivery in Feb 23 Release - Approve or Reject Prepare for delivery in Jun 23 Release - Approve or Reject
5186 | Prepare XRN5186 for delivery in June 23 Release | Prepare for delivery in Feb 23 Release- Approve or Reject Prepare for delivery in Jun 23 Release - Approve or Reject
Change | Recommendation | Decision
5186 | Develop partial workaround with costs and timelines for delivery ASAP | Approve or Reject
If decision is to deliver XRN5186 in June 23 Release then:

## Slide 42: Proposed Next Steps
Present BERs for approval with the inclusion of XRN5091 and XRN5186
  For approval in July or August ChMC if February 23 Release
  For approval in November or December ChMC if June 23 Release
Provide Costs and Timelines of workaround if requested

## Slide 43: December 21 - April 22 Changes in Design Update

## Slide 44: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) |  |  |  | Change Pack approved at ChMC on 11/05/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | June 2022 - Approval |  |  | Change Pack deferred at ChMC on 11/05/22 to include consultation comments into Change Pack Seeking approval at ChMC on 08/06/22
XRN4992B - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | June 2022 - Approval | Risk ID 67431: There is a risk that a MOD may be raised to include IGT sites into SoLR charging. e Mitigation: Accept risk. Design will be completed as per the current scope and has been issued for consultation in May 2022. This will not form part of any Nov22 Release. |  | Change Pack issued to ChMC for consultation on 16/05/22 Seeking approval at ChMC on 08/06/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | June 2022 – Consultation​ ​July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | June 2022 – Consultation July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
Slide updated on 26th May 2022
Notes: u

## Slide 45: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction | May 2022 – Consultation ​June 2022 - Approval | Risk ID 67731: There is a risk that the physical works required on Customer site will not be completed in line with a Nov 22 Release Date. Mitigation: Align to a future release post Nov22 release |  | Change Pack issued to ChMC for consultation on 16/05/22 Seeking approval at ChMC on 08/06/22
XRN5186 - MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | June 2022 – Consultation July 2022 - Approval |  |  | Change Pack submission date revised to 13/06/22 as quality criteria for submission not met Seeking approval at ChMC on 13/07/22
XRN5298 - H100 Fife Project – Hydrogen Network Trial | June 2022 - Approval | Issue ID 67645: The detailed design change pack was not be approved as MOD0799 is still outstanding​ Mitigation: Accept risk. Decision will be taken at ChMC in June as to whether this will be taken into delivery for Nov22. Risk ID 67482: There is a risk that the CV range will not be updated for hydrogen because a change is required to Gemini leading to the CV for hydrogen being rejected Mitigation: Monitor change request to be raised by SGN and align to implementation release for this change. |  | Change Pack deferred at ChMC on 11/05/22 as UNC MOD0799 is still under consultation Seeking approval at ChMC on 08/06/22
Slide updated on 26th May 2022

## Slide 46: November 2021 Major Release

## Slide 47: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Deferred Changes: Post Implementation Support completed for XRN 4780C to plan Data cleanse for XRN5072 completed XRN4992a: Post Implementation Support on track to complete on 26/05 Issue identified with the level of aggregation in the RTB invoice, fix identified and build/test in progress, deployment planned for 27/05 XRN5188b: Post Implementation Support on track to complete on 26/05 MAP ID data interim load on track to complete by 25/05 CCR planned to be presented in July ChMC Decision in June ChMC: None |  | XRN5289 | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope - XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope - XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope - XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope - XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 25th May 2022
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 48: XRN5231 Flow Weighted Average CV

## Slide 49: XRN5231 Flow Weighted Average CV
June 22 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at Red. The 2nd Project replan is in progress to baseline the Lowest CV requirement change. The project has continued with its planned activities alongside the replan for the FWACV service & Gemini consequential changes. DNs have approved the option to automate the Lowest CV requirements; DNs need to confirm their own internal dependencies will support a proposed End of August 22 Go Live Date. UAT for the revised Change Pack is planned for completion 24th May. Performance Testing started 24th May with Regression Testing planning in-flight in readiness to commence as part of the 2nd project replan Dual Run Phase 2 is in progress. SGN has completed full connectivity with engagement continuing for Cadent to complete its connectivity. Daily files are being received from WWU & NGN and the new FWACV service CV calculation largely matches NG’s existing service (MIPI); differences are down to DN data flows Re-plan to be reviewed/baselined: Once DNs confirm support of the dependencies of DR/MT to achieve the acceptance criteria/outcomes to the proposed plan timescales. An assessment of the proposed implementation date will be conducted across the wider CDSP change delivery portfolio The revised Business Case & BER remains draft and requires DN confirmation on the proposed implementation date of the end of August 22; DNs should consider their internal dependencies to support this date Business Readiness/Service Transition planned activities continue to progress (training, End to End Process definition, Service Management readiness etc) Next Steps: Finalise full re-plan once DN readiness is confirmed and define the revised BER for the costs of the project Plan out the revised design, build and test activities (ST, UAT & RT) to support the Lowest CV change Finalise the draft of the Data Migration, Cutover & Transition Scope & Approach (inc the Go No Go Criteria) to review with DN & NG Stakeholders at the Focus Group All DNs to complete End To End connectivity to provide daily files to remove issue with DR/MT plan Continue with UAT assurance, DR/MT and Business Change planned activities Revised BER from re-plan to be approved at an extraordinary ChMC (to be agreed) | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  | Replan baseline requires DNs’ assurance that key phase milestones for DR/MT and Migration/Transition can be met by all parties. The project continues to progress key phases/activities (eg UAT assurance, DR/MT, Business Change (inc External Training) and Cutover & Transition planning). Plan rebaseline is a dependency to confirm the overall plan, governance (e.g. BER) and confirm the Service Go Live date | 
Risks and Issues | There is an issue that NG and DNs do not understand the consequential changes arising with transfer of the FWACV service from NG and the impact to existing business processes – Update: Action for NG & DNs to review the consequences of the FWACV service moving from NG to Xoserve, this will be left open to monitor through the Business & Transition phase Business Readiness phase There is a risk that changes to the approved scope and requirements will be identified through the deliver plan – Update: 2nd replan in progress following the Lowest CV requirement change for revised plan to be baselined There is an issue with Dual Run/Market Trials phase that not all DNs are fully connected to provide daily files to progress the approved scope and plan to compare the new FWACV calculation to NGs service running in production – Update: Continued engagement for full connectivity is being progressed with impacted DNs and NG to provide support. Phase 2 to progress with 2 connected shippers There is a risk that changes to the baselined scope and requirements will increase the costs of the new FWACV service in extending the project and manual process being identified – Update: Finalise the impact assessment following the decision on Lowest CV automation to be progressed. The revised plan and business case will be defined for the BER to be review & approved | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Revised costs to be presented in an updated BER for review & approval by DNs and National Grid | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 50: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS MAR 2022 – MAR 2024

## Slide 51
Programmes & Projects 2022-2024 |  |  |  | 2022 |  |  |  |  |  |  |  | 2023 | 2023 |  | 
 |  |  |  | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Emma Catton | XRN5368.2 Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.3 API Enhancements |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.5 Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS MAY 2022 – APR 2024
Design to PIS
Dec 21 to May 22
Design to PIS – Sept 21 to June 22
API - Design to PIS
Jan 22 to May 22
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
PIS – From Apr 22 to Jun 22
Design to PIS - Nov 21 to Jul 22
Go Live
6th May
Go Live
30th Jun
Go Live
29th May
Go Live
8th May
Prod ChG 1
Contingency
12th Jun
Go Live
18th May
Prod ChG 2
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 52: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 53: CSSC Programme Dashboard
June 2022

## Slide 54
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status with all activities tracking to plan Predominant activities include Transition Stage 3 planning refinement and readiness, Business Change including target operating model and Post Implementation Support activities. Test activities continue for PT and OAT. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Potential Mismatch Between CSS & UK Link & Gemini We continue to discuss this subject with the central programme and Xoserve are hosting a session with Industry participants on Thursday 26th May to walk through architecture and business processes in order to gain a greater understanding of the central and PUI systems during this workshop. Following this session we will be assess our understanding and reflect within our identification workaround processes should we see an instance of late secured messages Transition Stage 2 This Programme phase is tracking to plan and currently ahead of schedule. A number of defects have been identified, these are being tracked by the Central Programme with mitigations and resolution in place to resolve. Transition Phase 2 continues until the week before Transition Stage 3 commences (Go Live 18th July) Transition Stage 3 Planning activities for Transition Stage 3 continue, these planning activities include all of the Programme workstreams plus the wider business. We continue to liaise with the Central Programme and attend the combined DWG meeting. Go/No meetings are in place both internally and with the wider programme via the Governance Groups PIS Planning activities continue for both Go Live and post implementation support. This includes the revision of the target operating model to incorporate requirements for 24/7 support plus the addition of the inclusion of the DCC service desk |  |  |  | Transition Stage 2 continued monitoring Refinement of Transition Stage 3 Activities Continue OAT and PT Testing Continued Business change activities which includes new operating model Continued Post Implementation Support Activities
e

## Slide 55: CMS Rebuild May Update
Update

## Slide 56: Progress to Date
The CMS Rebuild Team continue to build out the foundations of the new CMS, the Shipper raised MNC (Meter Number Creation) Process along with non process specific functionality such as Data Clarifications and Site Visits.
Weekly sessions with Recco and Xoserve have been scheduled to continue the development the Theft of Gas (Modification 0734) process.
The CMS Customer Focus Groups are now published on the Xoserve Calendar alongside the website, of which the remaining dates are:
The Customer Focus Group on 10th June will cover an update of progress to date, a walk through of the ToG Mod 0734 process alongside a live demo. To register please use the link: https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild-product/
As a reminder the delivery will follow an Agile Framework, there is an option to deliver a Minimum Viable Product (MVP) initially with future releases improving the end-to-end functionality of that process.
Further updates will be provided in July ChMC.
Date | Time Start | Time end
10/06/2022 | 10:00 | 11:00
06/07/2022 | 10:00 | 12:00
09/08/2022 | 10:00 | 12:00
09/09/2022 | 10:00 | 12:00
14/10/2022 | 10:00 | 12:00
08/11/2022 | 10:00 | 12:00
09/12/2022 | 10:00 | 12:00
10/01/2023 | 10:00 | 12:00
07/02/2023 | 10:00 | 12:00
07/03/2023 | 10:00 | 12:00

## Slide 57: Section 6: AnY Other Business

## Slide 58: DSC Delivery Sub-Group Xoserve Insight for Consideration June 2022

## Slide 59: Recap – Purpose of DSC Delivery Sub Group
The DSC Delivery Sub Group (DSG) is a monthly meeting facilitated by Xoserve to collaborate with Data Service Customers on change requirements, solutions and detailed design
This meeting was established following FGO implementation in June 2017, at the request of DSC Change Management Committee (ChMC) members
The objective of DSG was to allow the industry to consult and provide input to requirements and solutions for changes that are being progressed
DSG intends to provide its advisory inputs to support the Change Management Committee – including recommendations based on technical input that supports decisions that are required from ChMC
Xoserve have continued to facilitate DSG on a monthly basis, adhering to structured and formal practices
  e.g. 5 working day notice for meeting paper publication, formally documented meeting minutes and actions

## Slide 60: DSG Insights
DSG is attended by approx. 10 customer representatives each month
Xoserve has continued to use DSG as an opportunity to talk through DSC change material
Over time there has been a decline in the level of customer input being provided at DSG
Attendees appear to be positioned to gather information from DSG and socialise this across their organisation
This is resulting in a lack of customer input into proposed solution options and detailed design
It is difficult to gauge how well understood and how supportive customers are of the technical or operational changes that are being proposed by DSC Change Proposals
As a result of the above findings, DSG may no longer be providing ChMC with the consultative and advisory support it requires

## Slide 61: Options for ChMC Consideration
What do ChMC want going forward from the Delivery Sub Group?
Can DSG be better utilised – are we able to gain technical and operational input within these sessions?
Would a more fluid approach to gain customer input work better? e.g. Change Pack Clinics during consultation phase?
Do customers prefer a ‘self serve’ process – akin to other industry change processes such as SEC?
Are there any views from customers on how we support you more in gaining your input in the change development process?

## Slide 62: APPENDIX

## Slide 63: Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5301 | UKLink Portal | 02/07/2022 | 09:00 | 04/07/2022 | 07:00 | As part of the UK Link move to Cloud Programme, an extended outage will be required to complete implementation and cutover activities for the new DES & Portal screens. These systems will be unavailable for use from 2nd July 09:00 to 4th July 07:00 | 09/02/2022 Dates updated
CHG0033709 | Gemini | 18/06/2022 | 03:15 | 18/06/2022 | 07:30 | Gemini Disaster Recovery Test 2022 This is an annual activity to confirm Gemini services can be migrated to a secondary data centre location should there be a catastrophic failure within the primary data centre. During this phase of the test Gemini services will failover from the primary site to the secondary site. The activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 13/04/2022 Dates and RFC number updated
CHG0033709 | Gemini | 19/06/2022 | 03:00 | 19/06/2022 | 07:30 | Gemini Disaster Recovery Test 2022 During this phase of the test Gemini services will failback from the secondary site to the primary site. Again the activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 13/04/2022 Dates and RFC number updated
CHG0033562 | CMS | 16/07/2022 | 00:00 | 16/07/2022 | 07:00 | CMS Disaster Recovery Test 2022 This is an annual activity to confirm CMS (Contact Management Service) services can be migrated to a secondary data centre location should there be a catastrophic failure within the primary data centre. During this phase of the test CMS services will failover from the primary site to the secondary site. NOTE: This activity will run during the normal CMS maintenance window so no extended outage is expected however if we experience issues when the system is released there may be an extended outage until 11:00 as we revert the system back | 08/06/22 New
CHG0033562 | CMS | 17/07/2022 | 00:00 | 17/07/2022 | 07:00 | CMS Disaster Recovery Test 2022 During this phase of the test CMS services will failback from the secondary site to the primary site. NOTE: This activity will run during the normal CMS maintenance window so no extended outage is expected however if we experience issues when the system is released there may be an extended outage until 11:00 as we revert the system back | 08/06/22 New

## Slide 64: Portfolio POAP

## Slide 65: Delivery Release Options for XRN5186 and XRN5091 and Possible Workarounds – For Information

## Slide 66
Options for Delivering XRN5186 in advance of June 23
Option | Description | Pros | Cons
Option 1. Deliver XRN5186 and XRN5091 in June 23 Release | Full delivery of XRN5186 in June 23 | Synergies in delivery costs of delivering XRN5186 and XRN5091 together CSSC code is more stable reducing the risks & impacts identified in slide 3 Xoserve resources can focus on change as not dependent on volume of CSSC impacts in PIS safeguarding delivery timescales and costs | Does not meet obligations of UNC MOD 0701 until June 23
Option 2. Split XRN5186 into 2 phases Phase 1 Feb 23 Phase 2 June 23 | Delivery of elements less impacted by CSS/CSSC in Phase 1. This includes: Validations to capacity amendments Validations to class change requests Ratchet changes Change to PMN file to notify DNs when the PMSOQ has been capped at the NExA All reporting elements Update to DES/GES with NExA details Phase 2 include: Nomination validations added Confirmation validations added BRN validations added ASN validations added Default rules validations added | Provide functionality improvements to Customers Limits processes that can set the capacity higher than the NExA limits Shipper from paying for capacity they can’t use Capacity reduction window will be open allowing Shippers to reduce capacity when higher that the NExA Ratchets will prevent the capacity being set higher than the NExA Partially meets the obligations of UNC MOD 0701 in February 2023 | Will not fully meet the obligations of UNC MOD 0701 in Feb 2023 Customers have not agreed to Feb 23 functionality release More expensive to deliver: Loss of synergies in delivering XRN5091 in parallel More testing and potential re-work Duplication of effort due to undertaking delivery phases twice Capacity can be still be set higher than the NExA until June 23
The implementation of a MOD cannot be split and therefore, as Option 2 only provides partial MOD obligations in Feb 23, Option 2 is not feasible.

## Slide 67
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework if Delivered Earlier than June 2023
XRN5091 - Deferral of creation of Class change reads at transfer of ownership | Red | Amber/Red | SPA (all workflows CONF, change shipper and Supplier), Metering (UMR, UBR reads, AQI, Must Reads), RGMA | Common code/functionality with CSSC is: SPA, Reads (UMR, UBR), RGMA | Very High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required for XRN 5091 and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans XRN5091 also has extensive UAT and regression phases which may extend/need retesting due to any potential CSSC defects and/or CRs
Impact and risk of inclusion of XRN5091 in Nov22 and Feb23 Release

## Slide 68
Change | Nov 2022 | Feb 2023 | Functionality change | CSSC | Code Complexity | Build | Testing | PT | Rework
XRN5186 MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs Detailed Design | Red | Red | A number of key processes are undergoing change : Registration( Nom, Change of Supplier, Shipper change, Ratchets) | Touches large part of CSSC code Change touches Nomination/BRN | High | Potential of rework is high For Nov22 release – Build completes before CSSC Go Live For Feb23 release – Build completes early PIS period. | For Nov22 release – UT, ST/SIT & UAT complete before CSSC go Live For Feb23 release – UT/ST/SIT Testing in CSSC PIS | PT required and will clash with CSSC PIS | Yes – High potential for rebuild and retesting as a result of Defect Detection and Change Requests. This poses a risk by requiring multiple rounds of retesting (UAT/Regression) and possible slippage of plans Workflow defects in CSSC may need some code changes for 5186
Impact and risk of inclusion of XRN5186 in Nov22 and Feb23 Release

## Slide 69: CSSC Programme Dashboard
June 2022

## Slide 70: Workstream Updates
RAG Previous month | RAG Current months | Work stream | SUMMARY
 |  | Transition | Overall Transition RAG is Green and trending green no significant risks are apparent Key critical activities are on-track or planned in the case of stage 3 implementation planning. An incident fix release is planned and tracking towards 28th implementation and the release for 4th June is also on track
 |  | Testing | The overall RAG is Green 3 defects with AMT have been escalated and planned for release pre-Go Live SME assurance activities continue for regression packs and CR’s
 |  | Non-Functional Test (Performance, operational acceptance testing and operational testing) | The overall RAG is Amber with mitigations in place to move back to green NFR's for Reporting KPI scope to be confirmed with work off plan scoped Dependency on IPT before OAT internal can proceed Integrated OAT – there are internal identified OAT NFR’s to be defined and scoped for testing within phase

## Slide 71: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | CSSC – UK Link | The overall RAG is Green All change requests still on track for delivery CR0196 Reconciliation Report – TS and System testing documentations issued for review to Tech Ops and testing workstream. CR252 Schema Changes and Go-live Configuration. CR issued for approval, planning and preparatory activities in progress. Production deployment planned for 04/06 New exceptions SLA’s agreed as part of the business change activities
 |  | CSSC – API | The overall RAG IS Green All build activities complete Portal activities on track

## Slide 72: Workstream Updates
RAG previous month | RAG current months | Work stream | SUMMARY
 |  | Service Management | The overall RAG is Green Service Management is in a good position a number of tickets have been received following TS2 go live, these are being worked through by the Central Programme CR137 RMP Status which is causing a number of the tickets allows the same status can be accepted following refresh is due to be implemented early June. The majority of the tickets have been investigated have been passed back to Landmark.
 |  | Early life support | The overall RAG is Green PIS readiness ongoing Resources due to be in place to commence six week knowledge transfer to support target operating model TOM tracking to plan
 |  | Environments | The overall RAG is Green Post Go Live environment confirmation has been provided to the Central Programme following mandatory request PPTE5 due to be closed down due to assurance testing completion
 |  | Batch | The overall RAG is Green Estimated volumes have been provided for both CSSC and SwitchStream to analyse the potential impact on EFT performance. The impact is looking to be less than we originally estimatedas been raised and completed

## Slide 73: Workstream Updates
RAG previous month | RAG Current month | Work stream | SUMMARY
 |  | Business Change | The overall RAG is Green Prioritised areas of work are planned and in progress as per the change impact assessment For the unhappy path we are pending the update from the Industry Workshop to understand cut off times for messages Raised questions with DCC and the SI in respect of customer queries, pending a definitive answer on how a customer raises a query and if a set of FAQ’s is being raised and published by the Programme Continue to work through internal business awareness sessions with the whole organisation via a set of dedicated topics. Each topic is recorded A further external CSSC training day has been planned and open for any customers that wish to attend again or missed the first session
 |  | Gemini | The overall RAG is Green All activities are tracking to plan Conversations ongoing for a couple of minor topics, these are to be concluded over the next week

## Slide 74: Workstream Updates
RAG previous month | RAG current month | Work stream | SUMMARY
 |  | DES | Overall RAG status is Green Closely monitoring planned Go Live of UK Link portal as DES has a fundamental dependency on this Go Live Date Plan B is being discussed to understand implications of slippage

## Slide 75
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64002 |  | Programme | There is a risk that ongoing pipeline of customer driven and regulatory change within the industry could impact the CSSC and wider Switching Programme delivery because of technical conflict with the design of other changes and demand on resources across Xoserve and the customer teams involved in Switching Programme delivery leading to additional regression testing activity, CRs raised to modify solutions already developed and tested by the programme, delays to the overall Switching Programme, and therefore unplanned costs for Xoserve. | 1. Discuss the potential for change moratoria with Ofgem that could restrict the volume of change being made and in particular mitigate some of this risk in relation to coding impacts 2. Investigate the availability of and if necessary invest in tooling to support more enhanced branching and merging in terms of development to mitigate the technical impact of any non-CSSC changes. 3. Work with the SI to monitor for any potential impact on programme resources, including customer resources, that may result from change initiatives running in parallel with critical path Switching Programme phases. | Continues to be monitored | 18/07/22
67421 |  | Transition | There is a risk that Xoserve activities are delayed during actual transition or contingency is lost because CSS do not deliver the required dependency as per the planned dates leading to xoserve activities needing to be replanned and contingency reduced or potentially all transition activities needing to be replanned | Raise with SI transition group | Continue to monitor throughout transition | 18/07/22
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | Probability has reduced however there is no monitoring of the cleansing so risk remains open but minimal. | 18/07/22
66480 |  | Programme | There is a risk that the Go Live date could be pushed out further because of the current market situation in the Gas Industry with suppliers going out of business leading to additional cost to the programme, significant re-planning and impacts to other Correla initiatives | Regular communication with OFGEM to understand their strategy to address this issue | Continues to be monitored | 31/05/22
67839 |  | Business Change | There is a risk that not all customers will have migrated to new APIs that have changed as part of the programme ahead of go live because of a lack of understanding of the need to do this and the consequences of not doing this leading to a loss of relevant switching service API activities that the user has access to today. | 1. Send information pack to affected parties with key dates 2. CAM outreach to users 3. Simplify forms that users need to complete to sign up 4. Send comms to customers via RECco. | Discussed with Tim (SI) & Richard (DCC) - this will be raised to the wider programme | 18/07/22
67959 |  | Programme | There is a risk that the GES contract between RECCo and Xoserve cannot be agreed because of the draft MSC terms provided by RECCo misaligning with the terms of the DSC that binds Xoserve, leading to services being provided without a contract and at risk, or in the non- provision of the Gas Enquiry Service unless funded directly by DSC Customers. | Xoserve proposed draft terms based on previously agreed industry terms (DSC) Continued discussions between both parties Escalation to Xoserve and RECCo CEOs Discuss further with CoMC | New | 08/07/22

## Slide 76
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | Xoserve have raised CR-D129 to mitigate this risk. Discussions ongoing with programme stakeholders | Workshop taking place next week to understand the position. | 31/05/22
66599 |  | Programme | There is a risk that the Transition phase of the Switching Programme may be adversely impacted as a result of SoLR activities consuming the focus and efforts of Business and Operational teams who had been planned to be focused on Switching Programme Transition activities leading to a potential impact to Transitional activities as planned currently (March 2022) | Liaise with Switching Programme stakeholders to agree mitigations | Continues to be monitored | 18/07/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | Continues to be discussed. No update received to date. | 03/06/22
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | Continues to be monitored | 18/07/22
65122 |  | Transition and Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all programme work groups to monitor and mitigate this risk. | Continue to monitor, low exposure at this point | 15/07/22

## Slide 77
High Level Plan

## Slide 78: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect new updated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Interface Specification Design document from v8.5 to v8.7 and the CSS Business Data Validation Rules document from v1.2 to v1.3 | CR-D134 | £15,680.00 | 10/03/2022 | Approved - Internal CR Created
Additional explanatory notes added to Switching Supplier of Last Resort Service Design document | CR-D141 | £15,680.00 | 20/05/2022 | Pending IA

## Slide 79: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect new updated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Interface Specification Design document from v8.5 to v8.7 and the CSS Business Data Validation Rules document from v1.2 to v1.3 | CR-D134 | £15,680.00 | 10/03/2022 | Approved - Internal CR Created
Additional explanatory notes added to Switching Supplier of Last Resort Service Design document | CR-D141 | £15,680.00 | 20/05/2022 | Pending IA

## Slide 80: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 81: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact

## Slide 82: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | 26/11/2021 | Withdrawn
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Withdrawn
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Gas gate closure message cut-off timing | CR-D129 |  | Post Go-Live Change
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Further amendments to the Data Cleansing Catalogue v1.6 following DA605 (Pre-Transition Data Quality Checkpoint) Milestone. | CR-D131 | 22/03/2022 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Update to Data Migration Artefacts to reflect fortnightly Registration Delta Files | CR-D133 | 14/03/2022 | Complete - No Xoserve Impact
Update of CSS Business Rules to resolve MPRS Refresh Design Issue | CR-D137 | 23/03/2022 | Complete - No Xoserve Impact
Additional explanatory notes to DCC Service Design documents | CR-D138 | 28/03/2022 | Complete - No Xoserve Impact
Updates to MAD Log v2.6 and replacement of D-4.3.5 E2E Post Implementation Plan | CR-D139 | 05/04/2022 | Complete - No Xoserve Impact

## Slide 83: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 84: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact

## Slide 85: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | 26/11/2021 | Withdrawn
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Withdrawn
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Gas gate closure message cut-off timing | CR-D129 |  | Post Go-Live Change
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Further amendments to the Data Cleansing Catalogue v1.6 following DA605 (Pre-Transition Data Quality Checkpoint) Milestone. | CR-D131 | 22/03/2022 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Update to Data Migration Artefacts to reflect fortnightly Registration Delta Files | CR-D133 | 14/03/2022 | Complete - No Xoserve Impact
Update of CSS Business Rules to resolve MPRS Refresh Design Issue | CR-D137 | 23/03/2022 | Complete - No Xoserve Impact
Additional explanatory notes to DCC Service Design documents | CR-D138 | 28/03/2022 | Complete - No Xoserve Impact
Updates to MAD Log v2.6 and replacement of D-4.3.5 E2E Post Implementation Plan | CR-D139 | 05/04/2022 | Complete - No Xoserve Impact