## Slide 1: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER has been approved in eChMC on 29/07. Currently in delivery start up / initiation phase, with build phase commenced on 01/08 Progress update: UK Link build in progress, delivery on track to complete by 30/09 DDP build for XRN4990 to commence 12/09 System Testing preparation to commence 12/09 On track to complete delivery start-up/initiation on 23/09 XRN4900 DSG Meeting in September to discuss the change to the treatment of updating estimated CVs internally This will be followed by a revised Detailed Design Change Pack issued for information only in October No impacts to delivery timelines or cost No impacts to customer processes Decision in September ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to build activities halted and possibly design to be revisited. Mitigation: ChMC approved the change to progress delivery at risk; with the assumption that the MOD will be approved. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 24th August 2023
Complete
On Track
At Risk
Overdue