## Slide 1: Change Management Committee
10th August 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Budget v Committed Spend BP22
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 636759 | 423510 | 16425 | 0
Uncommitted | 1242602.4529 | 708186.3319 | 160477.9397 | 66021.5255
The Change budget can be found here

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Pipeline July 22 – December 23
CSSC Go-Live
February 23 – Major Release
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992, XRN5298
July 22
February 23
June 23 – Major Release
XRN5091, XRN5186, XRN5482
November 22
June 23
November 23
XRN5515
XRN5316
XRN5231
XRN5469
November 23 – Major Release
XRN5472
XRN5143
No Major Release
XRN5379
XRN5236 – CMS Release1
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
Delivery Key

## Slide 7: Change Pipeline - Delivery Plan July 2022 – February 2023
Slide produced 22nd July 2022
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | July 2022 | Standalone | Firm
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | August 22 | Standalone | Indicative
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £60K | September 22 | Standalone | Firm
5231 | FWACV Service | SGN | DN NG | DN NG | *£936K | 1st September 22 | Standalone | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | October 2022 | Standalone | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems (Modification 0734) | Gazprom | Shipper | Shipper | N/A | Oct / Nov 22 | CMS Rebuild Release 1 | Firm
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £150k | February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | SSE | Shipper | Shipper | £150k | February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | £10k | February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £150k | February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | February 23 | Major | Firm

## Slide 8: Change Pipeline – Delivery Plan April 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | Tbc | 1st April 23 | Standalone | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | DN WWU, Cadent, NGN only | Tbc | 1st April 23 | Standalone | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | Tbc | 1st April 23 | Standalone | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | 350,000 | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | 200,000 | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 | Major | Indicative
Slide produced 22nd July 2022

## Slide 9: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | Mod0651 – Retrospective Data Update Provisions | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5286 | Clarification Change to the AQ amendment process to be applied retrospectively (MO0746) | CDSP | Shipper DN | Shipper | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
Slide produced 22nd July 2022

## Slide 10
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5529 | UNC Derogation Process – Mod 0800 | NGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5532 | Hydrogen Town Trial | WWU | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued
Slide produced 22nd July 2022

## Slide 11: Section 3: Capture

## Slide 12: New Change Proposals
New Change Proposals - For Approval
XRN5541 - Amendment to the UIG Additional National Data Reporting
XRN5545 - Hydrogen Trial Visualisation dashboards
XRN5546 - Resolution of Address Interactions between DCC and CDSP
XRN5547 - Updating the Comprehensive Invoice Master List and INV template
New Change Proposals - For Information
XRN5533 - (Feb 23) February 23 Major Release
Solution Review – For Approval
XRN5379 - Class 1 Read Service Procurement Exercise - Mod0710

## Slide 13: XRN5541 - Amendment to the UIG Additional National Data Reporting
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Scottish Power
Change Description
This Change Proposal seeks to amend the existing version of the UIG Additional National Data report, to provide the requested aggregate energy values for each of the four respective End User Category Sub-Bands, as detailed below: Non-Prepayment/Domestic Prepayment/Domestic Non-Prepayment I&C Prepayment I&C The changes to the UIG Additional National Data report to include energy by Class by EUC sub band could be delivered as an additional data tab as opposed to changes to existing tabs. For clarity, the End User Category Sub-Bands are applicable to EUC01 and EUC02 only.
Change Type | Non - Regulatory
Priority Score | Low
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 

## Slide 14: XRN5545 - Hydrogen Trial Visualisation dashboards
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Northern Gas
Change Description
A form of data visualisation is required to be made available for all Hydrogen trials (100% + blend) being progressed. Industry parties that will be impacted by a Hydrogen trial will need to be able to access data that shows any changes or updates to the trial area SMPs and receive notification of the update being undertaken.
Change Type | Non-Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X

## Slide 15: XRN5546 – Resolution of Address Interactions between DCC and CDSP
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
The DCC have identified a number of potential scenarios in relation to the REL address and the details held within CDSP systems. This could potentially cause issues when communicating flows between CDSP and CSS. To remedy this, we would need to evaluate the DCC findings and look to take appropriate action to mitigate the potential data quality issues.
Change Type | Non-Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X

## Slide 16: XRN5547 - Updating the Comprehensive Invoice Master List and INV template
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Eon
Change Description
Part 1) Comprehensive invoice / charge type master list: This document is written by experts for experts and does not always come across as very user friendly. It requires additional information to make it more understandable by industry Parties e.g. including new and existing shippers. Part 2) INV Template and clauses: There are a number of standard clauses used on invoices but clause 3 refers to treatment of VAT / tax and this statement is not always appliable to the charge type invoiced. There needs to be improved wording to ensure Parties in receipt of these invoices are clear on what is being applied so there is consistent use of the tax codes (e.g. VA, VE, etc). This change is to be split into two parts 1) the addition of supporting/clarifying information and 2) technical charges to support the update of the INV temple. Please see the Change Proposal for a full description of the Change.
Change Type | Non - Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 
For Information | 

## Slide 17: XRN5533 - (Feb 23) February 23 Major Release
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | N/A
Change Description
Change Type | N/A
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For Information | 

## Slide 18: Solution Review XRN5379 - Class 1 Read Service Procurement Exercise - Mod0710
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Funding | Preferred Option | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  | Approve | Defer | Reject
3069.4 - KL - PO | £70-£150K | Implementation costs TBC | 1 | Shipper, DNO, IGT, NTS | TBC | CP | 1 |  | 
Org | Status | Comments
Wales & West | Approve | Support- As the proposer of Mod 710 we support this change.

## Slide 19: section 4. Design & Delivery

## Slide 20: Design Change Pack
For Approval:
Contact Management Service (CMS) Rebuild Release 1
  Shipper Meter Number Creation (MNC)
  Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734)
XRN4713 - Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690)
XRN5316 – Rejecting a replacement read with a pre-Line in the Sand (LIS) read date – Revised Detailed Design
XRN4900 - Biomethane Sites with Reduced Propane Injection
Administrative Amendments to UK Link Communication Formats

## Slide 21: Contact Management Service (CMS) Rebuild Release 1 - Shipper Meter Number Creation (MNC)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
3069.2 - KL - PO | N/A – CMS Investment funded | Shipper & DNOs | Proposed October 23 | 1 |  | 
Organisation | Status | Comments
Wales & West | Approve | Wales & West Utilities support this change. Consideration should be given to the impact that implementation might have on parties IT systems following the technical difficulties experienced during the DES migration to the cloud. This should include, as a minimum, testing of any changes to interfaces including testing of URLs against firewalls.

## Slide 22: Contact Management Service (CMS) Rebuild Release 1 - Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3069.5 - KL - PO | N/A – CMS Investment funded | Shipper | TBC | CP | 1 |  | 
Organisation | Status | Comments
Wales & West | Approve | Wales & West Utilities support this change. Consideration should be given to the impact that implementation might have on parties IT systems following the technical difficulties experienced during the DES migration to the cloud. This should include, as a minimum, testing of any changes to interfaces including testing of URLs against firewalls.

## Slide 23: XRN4713 - Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3069.3 - KL - PO | MTB Funded | Shipper | Adhoc October 22 | CP |  |  | 
Organisation | Status | Comments
 |  | No Reps received

## Slide 24: XRN5316 – Rejecting a replacement read with a pre-Line in the Sand (LIS) read date – Revised Detailed Design
Detailed Design Consultation Summary
Organisation | Status | Comments
 |  | No Reps received
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3069.1 - KL - PO | MTB | Shipper | Adhoc | CP |  |  | 

## Slide 25: XRN4900 - Biomethane Sites with Reduced Propane Injection
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3069.6 - KL - PO | Decarb Investment funded | Shipper, DNO | TBC | CP | 1 |  | 
Organisation | Status | Comments
Wales & West | Approve | Wales & West Utilities supports this change as it furthers progress towards net zero.

## Slide 26: Administrative Amendments to UK Link Communication Formats
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
3069.7 - KL - PO | N/A | Shipper, DNO | Adhoc August 22 | 1 |  | 
Organisation | Status | Comments
Wales & West | Approve | Wales & West Utilities supports this change.

## Slide 27: Standalone Change Documents for Approval (BER, CCR, EQR)
CCR for XRN5393 - fulfil the requirements of MOD0752, MOD755, MOD759 and MOD0785)
  - Voting: NTS
CCR for XRN5485 – Resource to support the Retail Energy Code (REC)
  - Shippers, IGTs, DNOs

## Slide 28: XRN5402 - Request impact assessment on proposed REC Change Management Impact Assessment
ChMC 10 August 2022

## Slide 29: Background
The REC has been live since 01 Sept 2020 with change demand being low, however this is expected to drastically increase following REC v3 and CSS go live.
Change Demand
In agreement with ChMC members, XRN5402 was raised to look at options available to support the REC Change Development process and to fulfil the CDSPs obligations set out within the REC.
DSC ChMC Agreement
REC Code Obligations
Xoserve has a number of different roles under the Retail Energy Code (REC) which require us to impact assess any REC Change that may affect a service we provide.
The following slides provide the different options proposed by the CDSP for supporting the REC Change process.
Solution Options
DSC have already approved to align with the REC in regards to implementation dates and the introduction of the third Major Release (February).
Release Alignment
Impact Assessments are triggered at different stages of the REC Change process. Adherence of these are monitored by the REC Performance Assurance Board (PAB).
Impact Assessments

## Slide 30: CDSP REC Change Process
REC Change Proposal
Initial (5) Assessment*
Preliminary (15) Assessment
Detailed (25+) Assessment
DSC Change Proposal
Release Management
DIA undertaken, equivalent to HLSO inc elements of detail design
RECCo have stated that Service Provider Impact Assessment are expected to be triggered linearly.
Discussions prior to these being triggered are expected to assist in the management of change demand.
ChMC Constituents, through the ChMC meetings, to have visibility of all Impact Assessments being carried out by the CDSP throughout the REC Change Process.
Potential DSC CP raised to progress approved REC solution for implementation
DSC CP feeds standard Change & Release Management
PIA undertaken, equivalent to ROM, inc Solution Opts
SPs undertake IIA and advise if impacted
REC CP raised and initial assessment undertaken
* Optional, no PAB reporting

## Slide 31: ChMC Ask
Discuss the different options for the facilitation of the REC Impact Assessment and Change process.
Provide feedback on the options presented and any views / questions constituents may have.
CDSP to seek an approved solution option in September’s ChMC meeting.

## Slide 32: General Considerations
Proposed for any increase to be added to the General Change Budget (currently set as £250k in BP22).
Proposed to continue as investment funding for BP22 (current) and BP23 (planning cycle) until REC Change demand is more visible.
Proposed Funding Split:
Service Area 13: Managing Change
SHP 52% | GT 40% | NTS 7% | IGT 1%

## Slide 33: Option 1 - Dedicated REC Change Team
DSC Impacts
Assumptions
Resources
Benefits
Challenges
Minimal. Dedicated team to ensure that there is minimal degradation to the development of DSC Change as REC Change is progressed. Includes increased DSC Development & Release capacity.
REC Change to increase post CSS implementation
Ringfenced REC change team, including Business Analysist, Solution Architect, Business Process Consultants and Change Development Leads etc.
Dedicated Team that would be on hand to focus on the progression of REC Impact Assessments, development and delivery of REC Change looking to mitigate risk on DSC Change.
£1.4m
Option 1
Dedicated REC Change Team
Level of IA conforms to existing processes (ROM / HLSO)
Demand for REC change is currently unknown
Full dedicated team for REC change
Mitigates risk to DSC Change Development
Increases DSC Development and Release capacity

## Slide 34: Option 2 - Dedicated Resources
DSC Impacts
Assumptions
Resources
Benefits
Challenges
Low/Medium. This would ensure that the pull on existing resources would be low for the progression of REC Change. Some de-prioritisation for DSC Change may still be needed.
Ringfenced resources, including Business Analyst, Solution Architect and Change Development Lead.
Additional core resources to support the progression of REC Impact Assessments and the development of REC Change.
£350k
Option 2
Dedicated Resources
Dedicated REC Change resources
Increases DSC Development capacity
Lowers risk to DSC Change Development
No increase to DSC Release capacity
REC Change to increase post CSS implementation
Level of IA conforms to existing processes (ROM / HLSO)

## Slide 35: Option 3 - Existing Resources
DSC Impacts
Assumptions
Resources
Benefits
Challenges
High. The use of existing resources would mean that DSC Change Development and Delivery would be de-prioritised if REC Changes are to be progressed. No increase in DSC Development & Release capacity.
None. Utilisation of existing resources.
Utilisation of existing resources to manage and progress with REC Impact Assessments and the development of REC Change.
£0k
Option 3
Existing Resources
No additional uplift in DSC Change budget
Potential to not meet REC IA obligations
DSC Change Development could be halted/ stopped
No increase in DSC dev / delivery capacity
High risk of conflicts in prioritisation against DSC Change
REC Change to increase post CSS implementation
Level of IA conforms to existing processes (ROM / HLSO)

## Slide 36: Options Summary
Dedicated team of resources focusing fully on REC IA and Change Development.
------------------------
Minimal Risk to DSC
Change progression.
------------------------
Increase in both DSC Change Development and Release Capacity.
Option 1
Dedicated REC Change Team
Additional core resources dedicated to support REC IA and Change Development.
----------------------
Low/Medium Risk to DSC Change progression.
------------------------
Increase in DSC Change Development Capacity only (no increase in Release Capacity).
Option 2
Dedicated Resources
No additional resources or capacity to account for REC IA and Change Development.
----------------------
High Risk to DSC
Change progression.
------------------------
No increase in DSC Change Development and Release Capacity.
Option 3
Existing Resources
£0
£350k
£1.4m

## Slide 37: CDSP Recommendation
Dedicated team of resources focusing fully on REC IA and Change Development.
------------------------
Minimal Risk to DSC
Change.
------------------------
Increase in both DSC Change Development and Release Capacity.
Option 1
Dedicated REC Change Team
Additional core resources dedicated to support REC IA and Change Development.
----------------------
Low/Medium Risk to DSC Change.
------------------------
Increase in DSC Change Development Capacity only (no increase in Release Capacity).
Option 2
Dedicated Resources
No additional resources or capacity to account for REC IA and Change Development.
----------------------
High Risk to DSC
Change.
------------------------
No increase in DSC Change Development and Release Capacity.
Option 3
Existing Resources
£0
£350k
£1.4m

## Slide 38: XRN5231 Provision of a FWACV Service Update

## Slide 39: XRN5231 Flow Weighted Average CV
August 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at Amber on basis a revised Go Live date of 1st September 2022 has been agreed, though remains Amber due to lack of contingency within plan and risk that further new requirements could impact Go Live date. Cost has returned to Green following BER approval Revised Go Live date set for 1st September with contingency date of 14th September Dual Run/ Market Trials is in progress with full end to end testing being undertaken. Phase due to complete in early August ahead of Implementation Dress Rehearsal (IDR) execution Internal Testing phases progressed to plan. UAT, Performance Testing all completed BER and CCP Addendum (contractual documentation) approved at July ChMC and forecast spend within reived budget Data Migration and Cutover plans have been presented to DNs and National Grid at the Project Focus Group Go No Go Criteria reviewed and published to DNs and National Grid Internal Business Readiness activities continue to progress to plan Next Steps: Complete Dual Run and Market Trials phase Complete Implementation Dress Rehearsal Complete Cutover on 1st September Commence Post Implementation Support phase | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | There is a risk that changes to the baselined scope and requirements will increase the costs of the new FWACV service in extending the project and manual process being identified – Update: Revised costs finalized and approval to be sought in revised BER. Risk will be monitored up to point of Cutover. | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Revised BER approved at July Change Meeting and costs within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 40: December 21 - April 22 Changes in Design Update

## Slide 41: Dec 21 - April 22 Changes in Design – Shipper Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4978 - Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) |  |  |  | Change Pack approved at ChMC on 11/05/22
XRN4990 - Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD 0664) |  |  |  | Change Pack approved at ChMC on 08/06/22
XRN4992B - MOD 0797 Creation of New Charge to Recover Last resort Supply Payments |  | Issue ID 67431: There is a issue that Modification 0809S has been raised to include IGT Supply Points into SoLR charging Action: Submit Change request to impact assess the inclusion of IGT sites and incorporating the change in Feb23 release |  | Change Pack approved at ChMC on 08/06/22
XRN5091 - Deferral of creation of Class change reads at transfer of ownership |  |  |  | Change Pack approved at ChMC on 13/07/22
XRN5186 – MOD 0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  |  | Change Pack approved at ChMC on 13/07/22
Slide updated on 27th July 2022
Notes: u

## Slide 42: Dec 21 - April 22 Changes in Design – DN Status Update
XRN Title | Target Detailed Design Date | Risk & Issues / RAG | Cost RAG | Key Messaging
XRN4900 - Biomethane/Propane Reduction |  |  |  | Change Pack approved at ChMC on 08/06/22
XRN5186 – MOD 0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  |  | Change Pack approved at ChMC on 13/07/22
XRN5298 - MOD 0799 - H100 Fife Project – Hydrogen Network Trial |  | Issue ID 67645: The detailed design Change Pack has not be approved as MOD 0799 is still outstanding​ Action: Accept Issue. Decision was taken at ChMC in July to include into delivery for Feb23 release |  | Change Pack baselined for delivery in Feb23 release in July ChMC Approval of Change Pack expected in September ChMC following approval of MOD 0799
Slide updated on 27th July 2022

## Slide 43: DDP August CHMC update

## Slide 45
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast
Release 3 – Golden Bullet invoice & IGT data quality analysis
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 – tbc
REC / Golden Bullet data modelling
Ti

## Slide 46
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 47
Data Discovery Platform | Inflight Sprint Update
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 48: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS JUNE 2022 – MAY 2024
August 2022

## Slide 49
Programmes & Projects 2022-2024 |  |  |  | 2022 |  |  |  |  |  | 2023 |  |  |  |  | 
 |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Emma Catton | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  | 
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Karl Davidson | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain | PM Emma Catton | Gemini Change Programme Sustain |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS JULY 2022 – MAY 2024
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Design to PIS - Nov 21 to Nov 22
Deployment
1st Sep
Closedown in Progress
Closedown in Progress
Design to PIS –Apr 22 to Nov 22
Deployment
18th Sept
Functionality Parameterised
Ofgem Decision
23rd Dec
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 50: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 51: CSSC Programme Dashboard
August 2022

## Slide 52
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status We are in week 3 of PIS where we are tracking first usage, defects liaising with the Central Programme and customers where any impacting defect have been seen | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
PIS We have three main defects that are affecting customers, we have been providing regular comm updates to enable you to track progress. These are: Irregularities with File Sequence Numbers for the new CSS files (BRR, TMC & ASN file types) – we are continuing to provide information to AMT to enable them to identify a fix. AMT are supporting and have confirmed their senior developers are working on this issue Files unable to be processed/issued due to ‘special characters’ with the file – An incident has been raised with the vendor and the issue continues to be investigated internally. Customers are being contacted where a file has been identified as it contains a ‘special character’. The customer is being asked to re-submit the file or we will remove the special character with the customers approval Users experiencing issues with accessing Portal – Support has been provided to customers for a range of differing issues. We are seeing issues with browser compatibility, functionality of LSO/MAU within the portal and difficulties accessing the Gas Enquiry Service (GES) and UK Link Services Portal. We have and continue to support technical triage sessions to understand root cause with these customers. We are also investigating cause and resolution for a data being displayed incorrectly within GES and does not reflect what is recorded in UK Link. Missing Secured Active Messages (SAM’s) – over the past week we have seen instances of missing SAM’s being issued to Xoserve from the CSSP. We have raised incidents and escalated these issues. In total we have 9 missing SAM’s (at the point of writing these slides). The CSSP have confirmed a defect and are working with Microsoft to fix. Any customers affected by this issue are being contacted. |  |  |  | Continued Business change activities which includes new operating model Continued Post Implementation Support Activities
e

## Slide 53: August ChMC CMS Rebuild Update

## Slide 54: Progress to Date
The CMS Rebuild Team are still on track for V1 in October and are currently developing the Supplier Theft of Gas (SUT) process to be delivered alongside the MNC process. Address amendments (ADD) is no longer in V1 but duplicates (DUP) will be delivered shortly after MNC/SUT.
As a brand-new solution, MNC will be delivered as a soft launch to the Customer Focus Group attendees at the beginning of October [target 10th October] and to all customers on [19th October]. SUT will be implemented a few days later [26th October]. Change packs have/will be published to ensure all customers are aware and can impact assess any changes. Transition arrangements will be agreed and communicated as we move contacts from old CMS to new CMS.
We launched Alpha Trials in July to the Customer Focus Group attendees. This has provided those attendees access to a sandbox environment where they can navigate through the processes as they are being developed. Alpha Trials will be available throughout August and into September and will enable us to obtain real-time feedback from customers on the solution, showcase Agile delivery and generate familarisation. This will also provide lessons learned to assist with the Beta Trials (External UAT) rollout which is scheduled for September 2022.
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild-product/ ) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued 7 days prior to the session:
Further updates will be provided in September ChMC.
Date | Time Start | Time end
09/08/2022 | 10:00 | 12:00
09/09/2022 | 10:00 | 12:00
14/10/2022 | 10:00 | 12:00
08/11/2022 | 10:00 | 12:00
09/12/2022 | 10:00 | 12:00
10/01/2023 | 10:00 | 12:00
07/02/2023 | 10:00 | 12:00
07/03/2023 | 10:00 | 12:00

## Slide 55: GES/UK Link Portal update & signal sign on
August 2022

## Slide 56: Portal Summary Update
As part of the broader UK Link Roadmap, GES (old DES) and its user management have gone live in the cloud (18th of July)
The migration and application go live were very successful, we are experiencing a higher than expected Service Tickets/queries.
Wide ranging engagement with various Shipper, Supplier and Network organisations has been ongoing to resolve the queries/issues being highlighted to us.
‘Drop-in clinics’ are being offered to organisations with a higher number of tickets while we continue to focus on individual ‘reach-out’ to originators to clear down the tickets as soon as possible and deal with all customer queries and tickets.
As we plan to stabilise the service and respond to all customer enquiries in the coming weeks, active planning and lessons learnt are being undertaken for UKL Portal Phase 2.
We want to engage with you over the coming weeks on what is being implemented and where there is customer impact (e.g. URL changes)
A number of engagement points including drop-in sessions are being planned for Portal Phase 2 to cover the technical requirements (e.g. Whitelisting IPs) and Business needs(e.g. user awareness).

## Slide 57: Section 6: AnY Other Business

## Slide 58: XRN5186 - Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs – interim process
Verbal update to be presented by Ellie Rogers

## Slide 59: REC Release Management
Verbal update to be presented by Simon Harris

## Slide 60: Appendix

## Slide 61: Portfolio POAP

## Slide 62: CSSC Programme Dashboard
August 2022

## Slide 63
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status We are in week 3 of PIS where we are tracking first usage, defects liaising with the Central Programme and customers where any impacting defect have been seen | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
PIS We have three main defects that are affecting customers, we have been providing regular comm updates to enable you to track progress. These are: Irregularities with File Sequence Numbers for the new CSS files (BRR, TMC & ASN file types) – we are continuing to provide information to AMT to enable them to identify a fix. AMT are supporting and have confirmed their senior developers are working on this issue Files unable to be processed/issued due to ‘special characters’ with the file – An incident has been raised with the vendor and the issue continues to be investigated internally. Customers are being contacted where a file has been identified as it contains a ‘special character’. The customer is being asked to re-submit the file or we will remove the special character with the customers approval Users experiencing issues with accessing Portal – Support has been provided to customers for a range of differing issues. We are seeing issues with browser compatibility, functionality of LSO/MAU within the portal and difficulties accessing the Gas Enquiry Service (GES) and UK Link Services Portal. We have and continue to support technical triage sessions to understand root cause with these customers. We are also investigating cause and resolution for a data being displayed incorrectly within GES and does not reflect what is recorded in UK Link. Missing Secured Active Messages (SAM’s) – over the past week we have seen instances of missing SAM’s being issued to Xoserve from the CSSP. We have raised incidents and escalated these issues. In total we have 9 missing SAM’s (at the point of writing these slides). The CSSP have confirmed a defect and are working with Microsoft to fix. Any customers affected by this issue are being contacted. |  |  |  | Continued Business change activities which includes new operating model Continued Post Implementation Support Activities
e

## Slide 65
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
66906 |  | Programme | There is a risk that UK Link may become out of sync because CSS may send secure active messages later than expected (circa 5:35pm) because of any upstream delays from CSS leading to a data mismatches between UK Link and CSS and more importantly Gemini and settlement issues which are incredibly difficult to correct. | Xoserve have raised CR-D129 to mitigate this risk. Discussions ongoing with programme stakeholders | This will now be a REC change post go-live and will be managed under a different reference. Date pushed out until after go live. | 28/10/22
66908 |  | Programme | There is a risk that the industry has not defined and agreed joint processes should key central components such as CSS go down during key times in the day (e.g. Gate Closure) because CSS BC/DR processes have been approved without addressing the queries and caveats called out during the consultation process leading to the possibility that should a DR event occur, downstream impacts are not understand or mitigated | This will be raised with REC and Ofgem | This has been escalated as part of the Xoserve Readiness assessment. No further updates currently. | 30/09/22

## Slide 66: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect new updated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Interface Specification Design document from v8.5 to v8.7 and the CSS Business Data Validation Rules document from v1.2 to v1.3 | CR-D134 | £15,680.00 | 10/03/2022 | Approved - Internal CR Created
Additional explanatory notes added to Switching Supplier of Last Resort Service Design document | CR-D141 | £15,680.00 | 20/05/2022 | Pending IA

## Slide 67: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Approved - Internal CR Created
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £10,000.00 | 23/08/2021 | Approved - Complete
Changes to DB4 document; “E2E Transition Plan – Implementation Approach’ to remove the requirement to expose the REL | CR-D105 | £0.00 | 31/08/2021 | Approved - Internal CR Created
Additional Regression Testing cycles | CR-D113 | £20,000.00 | 19/11/2021 | Approved - Internal CR Created
Amendments to NCD-0008 Data Cleansing Catalogue v1.5 to reflect new updated data cleansing requirements following DA310 analysis of industry data cleansing progress | CR-D115 | £0.00 | 25/10/2021 | Approved - Internal CR Created
Uplifting the CSS Interface Specification Design document from v8.5 to v8.7 and the CSS Business Data Validation Rules document from v1.2 to v1.3 | CR-D134 | £15,680.00 | 10/03/2022 | Approved - Internal CR Created
Additional explanatory notes added to Switching Supplier of Last Resort Service Design document | CR-D141 | £15,680.00 | 20/05/2022 | Pending IA

## Slide 68: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 69: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact

## Slide 70: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | 26/11/2021 | Withdrawn
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Withdrawn
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Gas gate closure message cut-off timing | CR-D129 |  | Post Go-Live Change
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Further amendments to the Data Cleansing Catalogue v1.6 following DA605 (Pre-Transition Data Quality Checkpoint) Milestone. | CR-D131 | 22/03/2022 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Update to Data Migration Artefacts to reflect fortnightly Registration Delta Files | CR-D133 | 14/03/2022 | Complete - No Xoserve Impact
Update of CSS Business Rules to resolve MPRS Refresh Design Issue | CR-D137 | 23/03/2022 | Complete - No Xoserve Impact
Additional explanatory notes to DCC Service Design documents | CR-D138 | 28/03/2022 | Complete - No Xoserve Impact
Updates to MAD Log v2.6 and replacement of D-4.3.5 E2E Post Implementation Plan | CR-D139 | 05/04/2022 | Complete - No Xoserve Impact

## Slide 71: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 72: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Continuation of support for UEPT | CR-D098 | 03/08/2021 | Withdrawn
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact

## Slide 73: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | Date Raised | Status
Elaborations for Service Management Requirements DB4 | CR-D104 | 17/08/2021 | Complete - No Xoserve Impact
Update of the Code of Connection Document to reflect the Enduring PKI Process Updates | CR-D106 | 22/09/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D093 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Transition Stage 1 – CSS ad-hoc data removal solution development based on Source Data Provider in response to DI-1655 remedial solution] | CR-D111 | 14/10/2021 | Complete - No Xoserve Impact
End to End Test Exit Criteria refinement and clarification of the decision making process | CR-D112 | 01/10/2021 | Complete - No Xoserve Impact
Clarification of Performance NFRs by apportioning the current target between Gas and Electricity and then further apportioning the Electricity targets by MPID | CR-D114 | 15/11/2021 | Complete - No Xoserve Impact
Update to E2E Transition Inflight Switches Management Approach Document | CR-D116 | 27/10/2021 | Complete - No Xoserve Impact
Operational Change Window and Type | CR-D117 | 25/10/2021 | Complete - No Xoserve Impact
Change to effect a Gas Supplier of Last Resort (SoLR) | CR-D118 | 03/11/2021 | Complete - No Xoserve Impact
GES Data Refresh SLA | CR-D119 | 10/11/2021 | Complete - No Xoserve Impact
Updates to NCT-0188 REL Testing Gap Analysis Report | CR-D120 | 10/11/2021 | Complete - No Xoserve Impact
Additional CSS Non-functional Requirements | CR-D121 | 11/01/2022 | Complete - No Xoserve Impact
ServiceNow Data Model Development - DNO/iDNO Adaptors | CR-D122 | 11/01/2022 | Complete - No Xoserve Impact
Addition of Network Operator Market Share to CSS Billing Report | CR-D123 | 26/11/2021 | Complete - No Xoserve Impact
Uplifting the CSS Business Data Validation Rules document to v1.3 | CR-D124 | 26/11/2021 | Withdrawn
Uplifting the CSS Interface Specification document to v8.7 | CR-D125 | 26/11/2021 | Withdrawn
Updates to the MAD Log v2.5 following RA110 Proposal | CR-D126 | 07/12/2021 | Complete - No Xoserve Impact
E2E Remove invalid test scenarios | CR-D127 | 03/12/2021 | Complete - No Xoserve Impact
Proposal for the implementation of Failed Supplier Portfolio report within CSS | CR-D128 | 07/12/2021 | Complete - No Xoserve Impact
Gas gate closure message cut-off timing | CR-D129 |  | Post Go-Live Change
Clarification of Performance NFRs for Operational Readiness | CR-D130 | 17/12/2021 | Complete - No Xoserve Impact
Further amendments to the Data Cleansing Catalogue v1.6 following DA605 (Pre-Transition Data Quality Checkpoint) Milestone. | CR-D131 | 22/03/2022 | Complete - No Xoserve Impact
Updates to the MAD Log V2.5 for Data and Regulatory Milestones | CR-D132 | 23/12/2021 | Complete - No Xoserve Impact
Update to Data Migration Artefacts to reflect fortnightly Registration Delta Files | CR-D133 | 14/03/2022 | Complete - No Xoserve Impact
Update of CSS Business Rules to resolve MPRS Refresh Design Issue | CR-D137 | 23/03/2022 | Complete - No Xoserve Impact
Additional explanatory notes to DCC Service Design documents | CR-D138 | 28/03/2022 | Complete - No Xoserve Impact
Updates to MAD Log v2.6 and replacement of D-4.3.5 E2E Post Implementation Plan | CR-D139 | 05/04/2022 | Complete - No Xoserve Impact