## Slide 1: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, Start up and Initiation phase completed on 23/09 as per plan Currently in build phase, with system testing in progress for XRNs where build completed from 03/10 Progress update: UK Link build in progress, delivery on track to complete by 30/09 DDP build for XRN4990 commenced on 12/09, delivery on track to complete by 23/12 System Testing preparation in progress, test case execution to commence 03/10 User Acceptance Testing (UAT) preparation to commence on 17/10 Decision in October ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update - SGN confirmed that Ofgem are due to provide an update on the status of the Modification w/c 26/09/22, which ultimately could result in this change being descoped from Feb-23 release. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 27th September 2023
Complete
On Track
At Risk
Overdue