## Slide 1: Change Management Committee
12th October 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1387949 | 476940 | 13455 | 0
Uncommitted | 491412.4529 | 654756.3319 | 163447.9397 | 66021.5255
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Committed spend has increased since last month by £0.8m - £0.1m adjusted following approvals in Aug-ChMC and £0.7m for illustrative / forecasting purposes (embedded spreadsheet provides XRN-level detail)
The Change budget can be found here

## Slide 5: General Change Budget BP23

## Slide 6
Guiding Principles
General Change (formerly called ‘UNC Change’) is an investment budget that iteratively funds UNC, REC and DSC Changes, once approved for delivery in ChMC
Investment funds are only utilised from design phase onwards (via approval of EQRs) and also cover build/test/implement/PIS phases (via approval of BER) for major release or standalone change delivery
Regulation-driven change (UNC, REC) is prioritised as per DSC Change Management procedures 46768906.01 (gasgovernance.co.uk)
Unutilised funds rebated at end of financial year

## Slide 7
Chart: General Change Historic Totals £m
| BP20 £m | BP21 £m | BP22 £m | Proposed BP23 £m
General Change | 3.1 | 3.6 | 3.25 | 3.4
Non-standard data items for reporting | 0.1 | 0.1 | 0.1 | 0.1
The purpose and size of the investment has remained relatively static over the last three BPs as the graph below shows. The proposed budget in BP23 is £3.5m
Previous BPs included investment associated with Decarbonisation and Minor Release. From BP22 Decarbonisation was communicated as its own investment and Minor Release moved into Operate. Only elements that have been consistently applied across the period depicted in the graph below have been included for comparison)
How does this relate to previous investments?

## Slide 8
The shape of the investment has evolved. As with BP22, there is a continued need to ring-fence funds to cover the following items:
Breakdown per element / constituency
Chart: Proposed BP23 Shape & £m Breakdown per Constituency
| Major Release | Standalone Delivery | Design | PAC | Market Trials | REC Change Development
Shipper £m | 1.262 | 0.12989 | 0.15466 | 0.1022 | 0.11546 | 0.20206
DN £m | 0.75966 | 0.078187 | 0.093095 | 0.062125 | 0.0695 | 0.12162
IGT £m | 0.11827 | 0.012172 | 0.014493 | 0.010675 | 0.01082 | 0.018935
NTS £m | 0.046126 | 0.0047475 | 0.0056527 | 0 | 0.00422 | 0.007385
Cost splits the same as in BP20 and BP21:
PAC funding split |  | 58.4% | 35.5% | 6.1% | 0%
All other categories funding split |  | 57.7% | 34.8% | 5.4% | 2%
Shipper
DN
IGT
NTS

## Slide 9
Plan v investment
The graph below depicts how maximum utilisation of the budget could be committed through the course of the BP:
Chart: £m forecast total committed funds (@maximum utilisation)
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
£m Monthly Forecacst (Maximum Utlisation) | 0.079 | 0.874 | 0.167 | 0.079 | 0.079 | 0.874 | 0.079 | 0.167 | 0.079 | 0.874 | 0.079 | 0.079
£m Cumulative Forecast (Maximum Utlisation) | 0.079 | 0.953 | 1.12 | 1.199 | 1.278 | 2.152 | 2.231 | 2.398 | 2.477 | 3.351 | 3.43 | 3.509

## Slide 10
Release bandwidth & impacts to budget BP23
MiR 12
Design
Build/Test
PIS
Develop
Build/Test
PIS
Build/Test
PIS
Build/Test
PIS
F23
J23
N23
BP22 Delivery Budget Impact
2023
2024
2025
Activity
2023
2024
2025
Design
Develop
Build/Test / Imp
PIS
Build/Test /Imp
PIS
Build/Test/Imp
PIS
PIS
Design
Build/Test/Imp
Design
Key
BP23 Delivery Budget Impact
Development
No £ Impact to BP23
F23
J23
N23
F24
PIS
Build/Test/Imp
J24
Standalone*
Major Release
Build/Test /Imp
PIS
N24
XRN
XRN
XRN
XRN
XRN
* Standalone for illustration only
Costs for release or individual changes are considered committed upon approval of EQR/BER
Major release costs based on average cost of previous releases (£0.8m)

## Slide 11: Change Pipeline

## Slide 12: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 – Major Release
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992, XRN5298
July 22
February 23
June 23 – Major Release
XRN5091, XRN5186, XRN5482
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
XRN5472
XRN5143
No Major Release
XRN5379
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 30th September 2022
XRN5565
XRN5529
XRN5561

## Slide 13: Change Pipeline Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | Standalone | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | Standalone | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | Standalone | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | Standalone | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | Standalone | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | October 22 | Standalone | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Indicative
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm

## Slide 14: Change Pipeline April 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 23 | Standalone | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | N/A | 1st April 23 | Standalone | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | 1st April 23 | Standalone | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 | Major | Indicative

## Slide 15: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | Mod0651 – Retrospective Data Update Provisions | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5286 | Clarification Change to the AQ amendment process to be applied retrospectively (MO0746) | CDSP | Shipper DN | Shipper | Tbc | Tbc | Tbc | N/A
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A

## Slide 16
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5532 | Hydrogen Town Trial | WWU | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | DN IGT NGT Shipper | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued

## Slide 17: Section 3: Capture

## Slide 18: New Change Proposals
New Change Proposals - For Approval
XRN5564 - Gemini Sustain Plus Programme
XRN5567 - Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067)
XRN5569 – Contact Data Provision for IGT Customers
XRN5573 - Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent
New Change Proposals – For Information
XRN5556B - New CMS - Version 1.1
XRN5566 - Amendments to v25 of the Service Description Table
XRN 5565 - Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824)

## Slide 19: XRN5564 - Gemini Sustain Plus Programme
DSC Service Area: | Service Area 14
Link to Change Proposal | Link to CP
Sponsor Representative | National Grid
Change Description
NGG wishes to modernise the Gemini platform in order to continue to provide required Capacity & Balancing Services as well as delivering system compliance against new UNC modifications. NGG also wants to deliver change more efficiently whilst improving the customer experience. The change will be known as the Gemini Sustain Plus programme. The scope of delivery will include: -Conversion of all the current Gemini functionality and code into modern (Java Microservices) code -Delivery of additional functional requirements -Delivery in line with non-functional requirements -Consolidation and re-design of Gemini screens -Implementation of Azure cloud infrastructure components (including replacing the current Oracle database) -Improvements to the support service arrangement to respond better to incidents and change (in line with new service levels and KPIs) NGG require all of the programme scope to be delivered within a 2- year period, implementation to be specified in the Correla Delivery Plan. Xoserve will contract with Correla to underpin the delivery of the Gemini Sustain Plus (covering the Correla Statement of Work).
Change Type | Non - Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | 

## Slide 20: XRN5567 – Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067)
DSC Service Area: | Service Area 1
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
The REC Change Proposal R0067 summarises the solution as follows: Change Proposal R0067 aims to introduce refresh, or resend functionality to four CSS messages, that have been deemed of high priority. Refresh, or re-send functionality will be made available to the central CSS Data Providers, to ensure high impact incidents, such as late gate closure messages can be resolved. The intention is to progress a future REC Change Proposal to widen the scope to encompass all messages and make the functionality available to all parties which interface with CSS, such as Suppliers. The scope of the change currently includes a total of four messages, however two are deemed high priority for inclusion and the remaining two as medium priority. A Preliminary Impact Assessment will be required to confirm the most cost-efficient scope. Messages to be assessed in the Preliminary Impact Assessment include: High Priority: Registration SecuredActive Synchronisation; Registration Cancelled Synchronisation Medium Priority: RMP Event Synchronisation; Registration Event Synchronisation
Change Type | Non - Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X
Other - Suppliers, and other recipients of messages from CSS | X

## Slide 21: XRN5569 – Contact Data Provision for IGT Customers
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Brookfield Utilities UK
Change Description
IGTs request that Xoserve, as Central Data Service Provider, assess solutions that enable IGTs to gain access to Contact Data held against their associated IGT Supply Meter Points. Xoserve should consider the following key requirements; ease in which that data is provided to, and processed by, IGT customers frequency that data is made available to IGT customers completeness of data to ensure a full view of all forms of Contact Data against the associated IGT Supply Meter Points is made available where necessary that data is provided in a secure and robust manner that data is provided in a efficient manner, taking into account respective IGT portfolio sizes By taking into account these key requirements and developing a solution that provides associated capabilities to IGT Customers, the problems statement and benefits outlined within this Change Proposal can be addressed and realised.
Change Type | Non - Regulatory
Priority Score | Medium
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | X

## Slide 22: XRN5573 – Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) - Urgent
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
Priority Consumers are those that must be prioritised where there is a national gas emergency. Reference to Priority Consumers is mentioned in Uniform Network Code, section Q1.7.1. The changes look to: Replace the obsolete Category B with a new category which permits the protection of sites of significance to national security or whose loss would pose a significant threat to welfare. Change Category C from a fixed financial threshold of damage to, damage costs calculated as a percentage of site value. This is relevant for sites over 2 million therms (58,600,000 kWhs) per annum. The process for a site to apply to be a Priority Consumer must be updated to reflect these changes. More information can be found on the Change Proposal page.
Change Type | Non - Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | X

## Slide 23: XRN5556B - New CMS - Version 1.1
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Correla
Change Description
This XRN will be a child XRN to 5556 and covers the Duplications Process (DUP), minor enhancements to the UI of the new system and the set to Extinct new process.
Change Type | Non - Regulatory
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This Change is being presented for information. | 

## Slide 24: XRN5566 - Amendments to v25 of the Service Description Table
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
The following DSC Services Lines can now be removed from the Data Services Contract as National Grid now issue the Termination notice to both the authority (Ofgem) and the User whereas previously this would have been done by Xoserve. We have confirmed with National Grid that they now have a Termination Committee in place which ratifies the decision of the EBCC to issue a termination notice and they have confirmed that these lines can be removed from the SDT
Change Type | Documentation
Priority Score | N/A
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This Change is for information and will be presented at CoMC on 19/10/22 for approval. | 

## Slide 25: XRN5565 Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824)
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Northern Gas
Change Description
The Government has proposed the EPG (Gas) Scheme, for domestic customers, to secure reductions in the energy bills of domestic customers within Great Britain. The intention is for the Central Data Service Provider (CDSP) to perform the function of the EPG (Gas) Scheme (the ‘Scheme’) Administrator and that the scheme to be implemented by 1st October 2022. More information can be found on the Change Proposal page.
Change Type | Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
This Change is being presented for information. | 

## Slide 26: Solution Review XRN5472 – Creation of a UK Link API to consume daily weather data for Demand Estimation processes
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Funding | Preferred Option | Voting | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  | Approve | Defer | Reject
3087.1 - RT - PO | £35,000 to £75,000 | Service Area 5 – Demand Estimation obligations | 1 | Shipper, DNO | Adhoc | Link to CP |  |  | 
Org | Status | Comments
 |  | No Representations received

## Slide 27: XRN5379 – Class 1 Read Service Procurement Exercise (Modification 0710) Detailed Design Change Pack Update

## Slide 28: Change Summary XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710)
The current contracts for the Class 1 Read Service between the DNOs and the Daily Metered Service Providers (DMSPs) will expire on 31 March 2023.
From 01 April 2023, UNC Modification 0710 and IGT Modification 148 will be implemented, and a new contract must become effective between the CDSP and the appointed Class 1 Service Provider.
To ensure this happens, a procurement process is in progress to appoint a Service Provider (SP) and put in place a new contract.
As required by the Modifications, it is the responsibility of the CDSP to appoint the new SP on behalf of Shippers, to provide the Class 1 Daily Read Service, from 01 April 2023 onwards.
The Solution Option Change Pack was approved at the ChMC on 10th August 2022.
This presentation seeks to provide an update on the plan for key next steps with XRN5379.

## Slide 29: Detailed Design Change Pack Update
We intend to issue the Detailed Change Pack for consultation in October 2023 for Approval in November 2023 ChMC:
  If approved in November, this provides 4.5 months notice prior to the required delivery date of 01 April 2023.
  Please note, we do not anticipate any system changes for customers as a result of XRN5379 implementation and the main changes relate to how the service is invoiced (via the Specific Service invoice rather than UK Link invoices).
  We are not anticipating any File Format changes as a result of this change
The BER for XRN5379 for Delivery to PIS is expected to be submitted for approval in November 2023 ChMC

## Slide 30: Future Discussions at CoMC
For awareness, we will also be discussing XRN5379 at CoMC. This will relate to the following topics:
  Service Provider access to data
  Permissions and information about Class 1 read additional services
  Class 1 read service Incentives document

## Slide 31: section 4. Design & Delivery

## Slide 32: XRN5556.B - CMS Rebuild - 1.1 Duplicate Meter Points (DUP) Process V1.0XRN5186 - Modification 0701 - Interim Process
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Representation Summary |  | 
 |  |  |  | Approve | Defer | Reject
3087.2 - RT - PO | N/A | Shipper, DNO, IGT | Proposed December 2022 | 1 |  | 
Organisation | Status | Comments
Northern Gas Networks |  | Northern Gas Networks support the principle of improving functionalities, such as the DUP process, to address existing pain points that prove barriers to the efficient resolution of issues such as duplicate MPRNs. Given that a cut-off date is intended where no new DUP Contacts can be raised via the existing version, we would request that all training materials, FAQs etc. referred to in the Change Design Description, as well as the timelines to delivery are clearly communicated with plentiful notice to enable a smooth changeover. We would also request that sufficient dedicated customer support is made available at the time of the transition.

## Slide 33: Standalone Change Documents for Approval (BER, CCR, EQR)
CCR for XRN5469 - Increasing the Frequency of FSG Payments
- Voting: DNO

## Slide 34: March 23 Adhoc Release Change Status & Scope Approval

## Slide 35: Background
There are 3 changes in the pipeline that need to be delivered by 1st April 2023:
XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP
Obligations will transfer to CDSP from 1st April so this change has to be delivered by then so that the CDSP can fulfil those obligations.
The solution change pack for this change has been reviewed and approved by the three DNs and detailed design is in progress.
XRN5379 DM Class 1 Read Service
As a result of MOD0710S, the CDSP will be obligated to take on Class 1 Read Service provision and a new contract will be in place from 1st April 2023.
The solution option change pack for this change has been approved and a detailed design change pack will be presented to ChMC in November 2022 for approval.
XRN5472 Creation of a UK Link API to consume daily weather data for Demand Estimation
Weather data is interfaced into UK Link to support demand estimation. This change is required to provision an API so that the weather data can be consumed. Currently the data is passed over via file transfer but this will no longer be possible after 1st April 2023.
The solution change pack for this change is being presented for approval at ChMC in October 2022 and detailed design will follow with a change pack being shared for information at a future meeting, as there is no customer impact of this change the detail design does not need approval from ChMC.
Because all three need to be delivered within a similar time frame, the proposal is to deliver them together as part of a single adhoc release in March 2023.
The following slide confirms the scope for this release and, if approved, a BER will be presented to the ChMC in November 2022 for approval of the costs to complete the delivery.

## Slide 36: Proposed Scope
Release | March 23 Adhoc Release
Implementation Date | 25th March 2023
Contingency Implementation Date | 1st April 2023
BER Approval being sought from ChMC | 9th November 2022 subject to prior approval of scope
Decision: | Required from the committee on proposed scope above
Note: | Funding mechanism for the individual changes is still to be fully confirmed but this will be clearly articulated for necessary approval of the BER at November 2022 ChMC
XRN | Title | Proposer | Benefitting | Funded By | HLSO Est. | Points | Comments
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | Cadent, WWU, NGN | Cadent, WWU, NGN | £100k | 5 | Solution Change Pack approved by three DNs Design Change Pack to be approved by relevant DNs by end of November
5379 | DM Class 1 Read Service | CDSP | GT, IGT Shipper DNO | Shipper | £150k | 8 | Solution approved at August ChMC. Design Change Pack to be approved at November ChMC
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | GT, IGT Shipper DNO | Shipper DNO | £75k | 5 | Solution Change Pack submitted for approval at October ChMC Design Change Pack to be submitted at December ChMC
 |  |  |  | Total | £325k | 18 | 

## Slide 37: February 23 Release Update

## Slide 38: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, Start up and Initiation phase completed on 23/09 as per plan Currently in build phase, with system testing in progress for XRNs where build completed from 03/10 Progress update: UK Link build in progress, delivery on track to complete by 30/09 DDP build for XRN4990 commenced on 12/09, delivery on track to complete by 23/12 System Testing preparation in progress, test case execution to commence 03/10 User Acceptance Testing (UAT) preparation to commence on 17/10 Decision in October ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update - SGN confirmed that Ofgem are due to provide an update on the status of the Modification w/c 26/09/22, which ultimately could result in this change being descoped from Feb-23 release. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 27th September 2023
Complete
On Track
At Risk
Overdue

## Slide 39: XRN5231 Provision of a FWACV Service Update

## Slide 40: XRN5231 Flow Weighted Average CV
October 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is now tracking as GREEN. All implementation activities are complete. PIS activity is progressing to plan. 1st Usage monitoring and assurance taking place. Requirements traceability activities have completed. No major issues have been reported and the service is largely working as expected since 1st Sept. A number of PIS tickets have been raised; 10 key PIS activities are now closed and work is in progress for the remaining 5 issues. The resolution activities for these issues will conclude within the PIS phase. Regular calls are taking place with the DNs as appropriate, NG and key stakeholders. These will continue for the remainder of PIS. Next Steps: Conclude PIS phase. Commence Closedown activity | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | There are currently no key issues or risks. | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs are within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 41: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS SEP 2022 – AUG 2024
SEPTEMBER 2022

## Slide 42
Programmes & Projects 2022-2024 |  |  | 2022 |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain Yr 1 | XRN5368 Gemini Change Programme Sustain Yr1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2022 – 2024
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Design to PIS
Nov 21 to Nov 22
Design to PIS
Apr 22 to Nov 22
Closedown
in Progress
Functionality Parameterised
Ofgem Decision
23rd Dec
Design to PIS
Oct 22 to Oct 24
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 43: DDP October CHMC update

## Slide 44: DDP Roadmap
Key:
Themes
Deliverable

## Slide 45
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast & IGT MDD data analysis
Release 3 – Golden Bullet invoice
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 – tbc
REC / Golden Bullet data modelling
Ti

## Slide 46
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 47
Data Discovery Platform | Release 3
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 48
Data Discovery Platform | Inflight Sprint (part of release 3)
Goals: Build the golden bullet invoice report Build the detailed design for the XRN4990 solution | 
User Stories: Build the dashboards to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on as well that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year Performance optimisation for read dashboards Detailed Design for the XRN4990 Solution pertaining to DDP Stretch Target: Must read enhancement to align BAU enhancement to DDP Industry view of number of MPRN associated to MRF (part of Shipper Pack XRN 5200) | 

## Slide 49: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 50: XRN5402 - Request impact assessment on proposed REC Change Management Impact Assessment
ChMC 12 October 2022

## Slide 51: ChMC Ask
Provide feedback on the previously presented details and recommend an option to progress with.
CDSP to continue with the Business Planning process and feed into it the recommended option.
CDSP to produce CCR for constituents to approval closedown of XRN5402 at a future ChMC.

## Slide 52: Background
The REC has been live since 01 Sept 2020 with change demand being low, however this is expected to drastically increase following REC v3 and CSS go live.
Change Demand
In agreement with ChMC members, XRN5402 was raised to look at options available to support the REC Change Development process and to fulfil the CDSPs obligations set out within the REC.
DSC ChMC Agreement
REC Code Obligations
Xoserve has a number of different roles under the Retail Energy Code (REC) which require us to impact assess any REC Change that may affect a service we provide.
The following slides provided ChMC the different options proposed by the CDSP for supporting the REC Change process.
Solution Options
DSC have already approved to align with the REC in regards to implementation dates and the introduction of the third Major Release (February).
Release Alignment
Impact Assessments are triggered at different stages of the REC Change process. Adherence of these are monitored by the REC Performance Assurance Board (PAB).
Impact Assessments

## Slide 53: CDSP REC Change Process
REC Change Proposal
Initial (5) Assessment*
Preliminary (15) Assessment
Detailed (25+) Assessment
DSC Change Proposal
Release Management
DIA undertaken, equivalent to HLSO inc elements of detail design
RECCo have stated that Service Provider Impact Assessment are expected to be triggered linearly.
Discussions prior to these being triggered are expected to assist in the management of change demand.
ChMC Constituents, through the ChMC meetings, to have visibility of all Impact Assessments being carried out by the CDSP throughout the REC Change Process.
Potential DSC CP raised to progress approved REC solution for implementation
DSC CP feeds standard Change & Release Management
PIA undertaken, equivalent to ROM, inc Solution Opts
SPs undertake IIA and advise if impacted
REC CP raised and initial assessment undertaken
* Optional, no PAB reporting

## Slide 54: General Considerations
Proposed for any increase to be added to the General Change Budget (currently set as £250k in BP22).
Proposed to continue as investment funding for BP22 (current) and BP23 (planning cycle) until REC Change demand is more visible.
Proposed Funding Split:
Service Area 13: Managing Change
SHP 52% | GT 40% | NTS 7% | IGT 1%

## Slide 55: Option 1 - Dedicated REC Change Team
DSC Impacts
Assumptions
Resources
Benefits
Challenges
Minimal. Dedicated team to ensure that there is minimal degradation to the development of DSC Change as REC Change is progressed. Includes increased DSC Development & Release capacity.
REC Change to increase post CSS implementation
Ringfenced REC change team, including Business Analysist, Solution Architect, Business Process Consultants and Change Development Leads etc.
Dedicated Team that would be on hand to focus on the progression of REC Impact Assessments, development and delivery of REC Change looking to mitigate risk on DSC Change.
£1.4m
Option 1
Dedicated REC Change Team
Level of IA conforms to existing processes (ROM / HLSO)
Demand for REC change is currently unknown
Full dedicated team for REC change
Mitigates risk to DSC Change Development
Increases DSC Development and Release capacity

## Slide 56: Option 2 - Dedicated Resources
DSC Impacts
Assumptions
Resources
Benefits
Challenges
Low/Medium. This would ensure that the pull on existing resources would be low for the progression of REC Change. Some de-prioritisation for DSC Change may still be needed.
Ringfenced resources, including Business Analyst, Solution Architect and Change Development Lead.
Additional core resources to support the progression of REC Impact Assessments and the development of REC Change.
£350k
Option 2
Dedicated Resources
Dedicated REC Change resources
Increases DSC Development capacity
Lowers risk to DSC Change Development
No increase to DSC Release capacity
REC Change to increase post CSS implementation
Level of IA conforms to existing processes (ROM / HLSO)

## Slide 57: Option 3 - Existing Resources
DSC Impacts
Assumptions
Resources
Benefits
Challenges
High. The use of existing resources would mean that DSC Change Development and Delivery would be de-prioritised if REC Changes are to be progressed. No increase in DSC Development & Release capacity.
None. Utilisation of existing resources.
Utilisation of existing resources to manage and progress with REC Impact Assessments and the development of REC Change.
£0k
Option 3
Existing Resources
No additional uplift in DSC Change budget
Potential to not meet REC IA obligations
DSC Change Development could be halted/ stopped
No increase in DSC dev / delivery capacity
High risk of conflicts in prioritisation against DSC Change
REC Change to increase post CSS implementation
Level of IA conforms to existing processes (ROM / HLSO)

## Slide 58: Options Summary
Dedicated team of resources focusing fully on REC IA and Change Development.
------------------------
Minimal Risk to DSC
Change progression.
------------------------
Increase in both DSC Change Development and Release Capacity.
Option 1
Dedicated REC Change Team
Additional core resources dedicated to support REC IA and Change Development.
----------------------
Low/Medium Risk to DSC Change progression.
------------------------
Increase in DSC Change Development Capacity only (no increase in Release Capacity).
Option 2
Dedicated Resources
No additional resources or capacity to account for REC IA and Change Development.
----------------------
High Risk to DSC
Change progression.
------------------------
No increase in DSC Change Development and Release Capacity.
Option 3
Existing Resources
£0
£350k
£1.4m

## Slide 59: CDSP Recommendation
Dedicated team of resources focusing fully on REC IA and Change Development.
------------------------
Minimal Risk to DSC
Change.
------------------------
Increase in both DSC Change Development and Release Capacity.
Option 1
Dedicated REC Change Team
Additional core resources dedicated to support REC IA and Change Development.
----------------------
Low/Medium Risk to DSC Change.
------------------------
Increase in DSC Change Development Capacity only (no increase in Release Capacity).
Option 2
Dedicated Resources
No additional resources or capacity to account for REC IA and Change Development.
----------------------
High Risk to DSC
Change.
------------------------
No increase in DSC Change Development and Release Capacity.
Option 3
Existing Resources
£0
£350k
£1.4m

## Slide 60: CSSC Programme Dashboard
October 2022

## Slide 61
Programme Health – RAG |  |  |  | 
Overall Programme Status | Previous | Current | The programme is reflective of a Green Status The Programme is in the last month of PIS, this phase concludes on the 31st October at which point the Programme will cease with the service moving into BAU | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Programme Closedown This month brings about the closedown of the CSSC Programme which I am very proud to have been apart of and also like to thank all of you for contribution and support for the duration By the time we exit PIS the service will have been adopted into BAU with knowledge transfer, operational model and support activities all in place The Programme has been a success and a huge multi party activity which has seen many high’s and low’s throughout it’s duration which you would expect from a Programme for this size We will continue our relationships with all customers involved in the Switching Programme so please be assured that support is still available through your BAU channels We will continue to report any issues that are encountered as a consequence of the Programme via our Issue Resolution team as per the BAU process that has been in place since Programme implementation We will continue to provide you updates in relation to the missing secured active messages (SAM’s) until we reach resolution of this issue |  |  |  | Programme closedown
e

## Slide 62: October ChMC CMS Rebuild Update

## Slide 63: Progress to Date
One of the main pain points we identified during analysis of current CMS was the high customer effort in data entry, specifically relating to populating addresses. To eradicate this pain point we will be utilising an address lookup tool which will allow you to put in minimal information, choose the address which will in turn auto populate the required fields. Unfortunately, this will not be ready in time for the soft launch on the 10th October.
We want to ensure that your first experience of the new solution is a highly positive one. Therefore, we are now targeting a soft launch date of 24th October so that you can get the full benefit of this feature. This date will be confirmed during the week commencing 10th October.
Although this only gives a gap of two days between soft launch and full launch, October 26th for all customers, we believe that this is enough time as a lot of testing on connectivity etc. was undertaken in Alpha Trials.
As well as the Found Meter process (MNC), the new Supplier Theft process (SUT), as per Modification 0734, is due to go live on 26th. In terms of the SUT / Modification 0734 process, theft data will be sent by RECCo to the CDSP. Currently RECCo are working through their process to ensure the release of required theft data to the CDSP via the appropriate REC change. Please be aware that the SUT / Modification 0734 technical solution will continue to be deployed as planned, however the new process will not commence until the relevant REC change is implemented. As a result, all customers should continue to use the current “TOG” contact / process in CMS until the SUT / Modification 0734 process has been implemented fully (alongside the relevant REC change).
We will provide an update as soon as we know when the relevant REC change is due to be raised and implemented to ensure you have as much notice as possible of the SUT / Modification 0734 process commencing (and the cessation of the current Shipper "TOG" process.
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild-product/ ) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued 7 days prior to the session.
The October Customer Focus Group will discuss: Progress update, updating the QMP File preferences and options, walkthrough of the new Set to Extinct process and an end-to-end Demo.

## Slide 64: Section 6: AnY Other Business

## Slide 65: XRN4914_Modification 0651 Retrospective Data Update Provision ChMC Clarification Required

## Slide 66: Recap – XRN4914_Retrospective Data Update Provision
Over recent months, Xoserve have re-introduced the topic of XRN4914_Retrospective Data Update Provisions (Modification 0651)
At September’s ChMC Xoserve confirmed that we would assess the High Level Solution Option, as outlined under Modification 0651
Our immediate next step is to produce an EQR for approval of funds to commence the Detailed Design Phase of the project
During our review of the High Level Solution Option and Modification 0651, several points have been identified which could impact the accuracy and validity of any Detailed Design costs and timescales of the project
These points require clarification from DSC Customers in order to set the project up for success and ensure that customers understand what is required from their respective organisations
  e.g. involvement in the development of the solution - including Data Preparation, Testing of the enduring solution and management of consequential impacts

## Slide 67: Key Clarification Points for ChMC
To establish accurate Detailed Design costs, a clearer understanding on the likely take up of the solution is needed from DSC Customers
Notably Xoserve need clarification on the likely number of customers that will be participating in Data Preparation and Market Trials phases, and volume of their respective portfolios
This information will enable Xoserve to ensure technology, environments and resource can be appropriately sized for the project, and allow the project to be planned in a meaningful way, with customers' needs in mind
Customers are asked to note that the Modification Business Rules do not refer to how downstream impacts are to be monitored and managed - this would need to be carefully analysed and assessed during solution testing
The High Level Solution Option costs of the project are in excess of the remaining budget for the delivery of XRN4914 - Xoserve need to ensure that we are starting the project with a clear position on how any excess costs will be funded by DSC Customers
*Xoserve therefore is seeking clarification from ChMC on the above points in order to progress in deriving accurate Detailed Design and remaining Solution Delivery costs of the project

## Slide 68: ChMC Input Required
Will Customers be fully participating in Data Preparation and Migration phase?
If so, will this be for your entire portfolio or only where asset data misalignment has been identified?
Can Customers commit to participate in a Market Trials phase?
Do Customers understand that the scope of the Modification does not take into account monitoring and managing of downstream impacts to industry?
Do we have an agreed funding arrangement for the excess delivery costs for the project?
Do ChMC feel it is necessary to bring Mod0651 implementation date to the attention of the UNCC for consideration?

## Slide 69: XRN5431 - Temporary community access to pre-covid AQ values for shippers Verbal Update by Kate Lancaster

## Slide 70: Appendix

## Slide 71: Portfolio POAP