## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber, Design phase continues for all three XRNs scoped for this release. Build due to commence from 28th November for 5379 and 5472 but this is at risk due to status of design. Return to green is completion of design as planned and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Workshops to aide understanding of the changes, in lieu of design completion taking place Commenced engagement with the DM service provider for 5379 Project in startup and initiation phase including development of detailed project plan and project artefacts Decision in December ChMC: None |  |  | 
Risks and Issues | 68488 & 68489: The design has not yet completed for the changes in this release, therefore the aspirational build timescales are at risk 68126: The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68498: The DM SP is agreed, but not yet fully engaged, until the DM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) XRN5472 - Creation of a UK Link API to consume daily weather data for Demand Estimation processes |  |  | 
Slide updated on 24th November 2022
Complete
On Track
At Risk
Overdue