## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber, Design phase continues for all three XRNs scoped for this release. Build commenced as planned from 28th November for 5379 and 5472 but this is at risk due to status of design. Return to green is completion of design as planned and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Build continues as planned for 5379 and 5472, build for 5143 due to commence in January 2023 Workshops to aide understanding of the changes, in lieu of design completion have completed for 5379 and 5472 Engagement with DM service provider continues for 5379 including resolving of design queries Project in startup and initiation phase including development of detailed project plan and project artefacts Decision in December ChMC: None |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | 68488 & 68489: (R) The design has not yet completed for the changes in this release, therefore the aspirational build timescales are at risk 68126: (R) The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged, and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68498: (R) The DM SP is agreed, but not yet fully engaged, until the DM SP is engaged, and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68501: (I) Build of March-23 will commence before detailed design is complete |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) XRN5472 - Creation of a UK Link API to consume daily weather data for Demand Estimation processes |  |  | 
Slide updated on 20th December 2022
Complete
On Track
At Risk
Overdue