## Slide 1: March 23 Release XRN5472 Creation of a UK Link API to consume daily weather data for Demand Estimation processes
*ChMC Decision Required*
Withdrawal from scope of March23 Release

## Slide 2: Project Update – Change to Weather Data Service Provider API and implications to XRN 5472 Delivery Approach
Background
Following ongoing engagement with our weather data service provider on the proposed API solution, we have been informed that they intend to move all of their clients onto a new version of their API services
This activity is expected to take place in late 2023 and will require all clients to upgrade any existing APIs to this new version (version 2) in order to continue to receive the relevant weather data
In light of this upgrade, the weather data service provider has offered to extend the existing data transfer mechanism (File Transfer Protocol)
This would allow our service to transition to the new API version later in the year without impacting our DSC services continuity
As a result this would also avoid the need for the proposed XRN5472 changes to be deployed on 1st April as have been previously communicated and approved
Following completion of our associated Detailed Design phase (issued in January-23 Change Pack), we have established that the required technical change do not impact or have any interaction with DSC Customers – confirming that the change is entirely internal to the CDSP

## Slide 3: XRN 5472 Proposal to withdraw Change
CDSP Recommendation and related Next Steps
Having confirmed that the technical changes do not impact or involve DSC customers we recommend that XRN5472 is withdrawn from the scope of March-23 Release
The associated funds that were reserved for this change within the March-23 BER will be returned to DSC Customers
  The CCR will be the mechanism to reconcile funds to the DSC Change Budget
Technical upgrade to the weather data service providers new API version will be planned and coordinated as an internal CDSP project
This approach allows the scope of the March Release, and any later Release to consist of only changes that are Customer impacting and benefitting
DSC ChMC Decision – Approval of Xoserve’s recommendation to withdraw XRN5472 from March-23 Release scope
Vote required from DN and Shipper Customer Classes