## Lists Tab (hidden)
Review | Version | Category | Author Response | Reviewers & Approvers Initials | Author Accepts Response | Reviewer Acceptance | Approver Acceptance
R1 | 0.1 | Cosmetic | A |  | Yes | 1 | 1
R2 | 0.2 | Minor | R |  | No | 2 | 2
A1 |  | Query | C |  |  | 3
A2 |  | Substantial
Note on A1: List 1
Note on B1: List 2
Note on C1: List 3
Note on D1: List 4
Note on F1: List 6
Note on E1: List 5
Note on G1: List 7
Note on H1: List 8

## Settlement
|  |  | Document for Review: |  | Project Nexus Settlement BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Mike Fensome @ npower | [6 empty] | 2015-04-03
Leigh Chapman @ firswt-utility | [6 empty] | 2015-04-07
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
4.4 | 4 | 1.2 |  |  | Updates to the document refers to changes in sections 5.11.6, 5.11.7, 5.11.10 which do not exist. A new section 5.12 as been inserted which knocks out the numbering. |  |  | Mike Fensone | Accept | Thank you. References updated to 5.12.
4.4 | 35 | 5.12 |  |  | Although the new Section 5.12 helps to clarify its actually making it difficult to maintain traceability of all requirements. |  |  | Mike Fensone | Reject | The business rules for a Class Change as been removed from the original section 5.11 as the process is different for a Class change to a change to Meter Read Frequency & Batch. The two processes need to be seperated. Traceability will be maintained as all changes are tracked.
4.4 | 13 | 2.1 |  |  | The 'Summary of the 4 Meter Reading and Settlement Processes' table on page 14 (v4.4 of Settlement BRD) is no longer correct. For Product 4 the read submission deadline has changed from 25 calendar days to 25 business days as per section 5.17.3. |  |  | Leigh Chapman | Accept | Thank you. I shall correct the information in the table. It was changed from 'calendar days' to 'business days' to reflect the current timescales for submitting reads for NDM meter points.
Note on H7: i.e. Full Document or Section*** etc

## Reconciliation
|  |  | Document for Review: |  | Project Nexus Reconciliation BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
Note on H7: i.e. Full Document or Section*** etc

## AQ
|  |  | Document for Review: |  | Project Nexus AQ BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Mike Fensome @ npower | [6 empty] | 2015-05-16
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
5.5 |  | 8.8 | 8.6.3 |  | Section states: An AQ Correction can only be raised following a calculation of the AQ except where an AQ was unable to be calculated due to the meter read failing the Outer Tolerance ( Market Breaker) validation. Question: Does this mean you have resolved the issue we have been discussing at PNUNC whereby you couldn't send an AQ correction if it failed market breaker but the AQ hadn't previously been calculated? |  |  | Mike Fensome | Reject | Where a read has failed the Outer Tolerance (Market Breaker) but the read is correct an AQ Correction needs to be raised to amend the AQ to enable reads to be accepted. The issue discussed at PN UNC is the read submitted will still not be accepted as the AQ used to validate the read will be the AQ effective on the date of the read. A new read will need to be obtained & submitted with a read date equal to or later than the AQ effective date.
Note on H7: i.e. Full Document or Section*** etc

## SPR
|  |  | Document for Review: |  | Project Nexus Supply Point Register BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Emily Wells @ Corona Energy | [6 empty] | 2015-04-28
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
3.5 | 19 | 8.1 |  |  | Text states that the last Check Read will be issued in the MRI file to the new Shipper has been deleted however the last Check Read date is included in the MRI file formats. |  |  | Emily Wells | Accept | Apologies the statement in the BRD is incorrect and this will be updated in version 3.6 of the BRD. As you state, the date of the last Check Read will be issued to the new Shipper in the MRI file. The MIN file is used to notify the registered shipper 1 month before the Check Read is due.
Note on H7: i.e. Full Document or Section*** etc

## Retro
|  |  | Document for Review: |  | Project Nexus Retrospective Updates BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Emily Wells @ Corona Energy | [6 empty] | 2015-04-28
Mike Fensome @ npower | [6 empty] | 2016-01-13
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
4.2 | 25 | 8.2.7 |  |  | This requirement and discussions at previous UKLIEF suggest it will not be possible to submit retrospective update removals, however, the RTO file formats do suggest a removal is possible (TRANS line REMVE is an option) |  |  | Emile Wells |  | An asset can not be removed (unless part of an exchange) for a date prior to actual reads recorded on UKLink. However, the REMVE is still required on the RTO file to allow the registered Shipper to remove an asset in a previous Shippers ownership. The update will only be accepted where no actual reads are recorded and the transfer read was estimated.
4.4 |  |  |  |  | Are there any updates needed following the final RAASP workshops in December/January. I know you plan to add the updated presentations as an appendix, but were there any principle/generic rule changes that need updating in the body of the BRD? |  |  | Mike Fensome |  | New Section 8.1 (V4.4) has been added to include all the rules documented from the RAASP workshops. Also, in the table under section 2.1, any updates as a result of RAASP have been specified.
4.4 |  |  |  |  | I can’t see in the original BRD where it states that you have to replace the read with a read for the same date. I see 8.1.17 has been added in the latest version, but this isn’t that clear and I couldn’t see it in the original BRD |  |  | Mike Fensome |  | Section 8.4.4 states: For Product 3 and 4, reads can not be ‘inserted’ where a read has not already been recorded with the exception of a read associated to an asset installation , removal or isolation i.e meter installation or removal reading. Further clarification added to version 4.5 of the BRD.
Note on H7: i.e. Full Document or Section*** etc

## Invoicing
|  |  | Document for Review: |  | Project Nexus Invoicing BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
Note on H7: i.e. Full Document or Section*** etc

## Transition
|  |  | Document for Review: |  | Project Nexus Transition BRD
|  |  | Author: |  | Xoserve
REVIEWER DETAILS
Reviewers | [5 empty] | Review Criteria | Date | Outcome (1,2,3) | Remarks
Sue Cropper, British Gas | [6 empty] | 2015-08-10
Sue Cropper, British Gas | [6 empty] | 2015-06-23
Project Nexus Workgroup | [6 empty] | 2015-07-15
Sue Cropper, British Gas | [6 empty] | 2015-07-28
Outcome: |  | 1 = Accept. 2 = Accept with minor comments. No further review required. 3 = Further review required.
BRD Version | Page | Section | Paragraph | Bullet | Comment |  |  | Reviewer | Comments Accepted /Rejected | Author Comments | Response to Authors comments
1.3 |  | 7.1 |  | 3rd | correct' should be 'incorrect' |  |  | BG | Accept | Document updated
1.3 |  | 7.1 |  | 7th | spear' should be 'smear' |  |  | BG | Accept | Document updated
1.3 |  | 7.11 |  | 7th | Sentenance is confusing. Add an example to explain the rule |  |  | BG | Accept | Document updated
1.2 |  | 5.1 |  |  | T he last bullet point that has been recently added, at PNUNC on 15 July it was said that as the system will be suspended, by default the C&D obligations will be suspended for the appropriate number of days too. This reads to be the opposite, can you clarify please |  |  | BG | Accept | Removed from the document as C&D obligations should not be referenced in a UNC document.
1.2 |  | 7.1 |  |  | The last but one bullet on changing class post go live. The legal text 5.2.8 clarifies this in more detail than the BRD, suggest expand the BRD explanation as this is the document that people will be referring to. |  |  | BG | Accept | Document updated
1.2 |  | 7.11 |  |  | Meter Readings, there appears to be a lot more detail in the legal text, section 7.4 than in the BRD. Given that strictly speaking the legal text should be based on the BRD I would anticipate and suggest that more detail be added to the BRD. |  |  | BG | Accept | Updated relevant section of the document. Some parts of the legal text under 7.4 is covered in the BRD in Section 7.8
1.2 |  | 7.1.3 |  |  | Dead to Live, can this be made clearer on what the transition impacts are please i.e. an MPR that is DE before go live can be made LI after go live, as opposed to an MPR that is made DE after go live. |  |  | BG | Accept | Document updated
1.2 |  |  |  |  | Do we need something on AUG? There is something in the legal text, although see my note below on this. |  |  | BG | Accept | Transitional rule which establishes initial allocation factors by reference to the AUG document, rather than the annual statement and table process. We could move this to the new Part IIE so the transitional rules are kept together
Legal Text |  |  |  |  | there are numerous date references in sections 5,6 and 7 and I would suggest a thorough review |  |  | BG | Accept | Updated
Legal Text |  | 3.6 |  |  | AUG Given the implementation of Mod 473, does this legal text still work? I’m not sure and would welcome an experts view |  |  | BG | Accept | Transitional rule which establishes initial allocation factors by reference to the AUG document, rather than the annual statement and table process. We could move this to the new Part IIE so the transitional rules are kept together
Legal Text |  |  |  |  | Do we need anything adding to cover the C&D obligations mentioned in the BRD under section 5.1, I’m not sure whether these sit in UNC though so will be guided by the experts |  |  | BG | Reject | Not needed in legal text
Legal Text |  |  |  |  | A section on MPRN lifecycle has been added to the BRD under section 7.13, and see above note on 7.1.3. Do we need some legal text adding? |  |  | BG | Reject | Not needed in legal text
1.1 |  | N/A |  |  | Include MPRN Creation arrangements |  |  | PN UNC | Accept | Document updated
1.1 |  | N/A |  |  | Include arrangements for address updates |  |  | PN UNC | Accept | Document updated
1.1 |  | N/A |  |  | Add assumption regarding DMSP activities |  |  | PN UNC | Accept | Updated in assumptions
1.1 |  | N/A |  |  | Add assumption regarding C&D obligations on the Shipper & GT |  |  | PN UNC | Accept | Updated in assumptions
1.1 |  | N/A |  |  | Include arrangements for RGMA updates |  |  | PN UNC | Accept | Document updated
1.1 |  | N/A |  |  | Include list of invoices that will be issued in old file formats after Go Live |  |  | PN UNC | Accept | Document updated
1.1 |  | 7.1 |  |  | Update section regarding CMS activities |  |  | PN UNC | Accept | Document updated
1 |  |  | All |  | The document assumes and references a 1 October go live date so will need to be updated once a new date is agreed. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Enquiries |  | Need clarification on “in flight” web requests, can phone calls continue during non effective days? |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Nominations |  | Will we be notified of a lapsed nomination? Needs to be clear and explicit in the document. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Offers |  | Will we receive any notification of live offers being invalidated, needs to be clear. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Referrals |  | “Any Referrals outstanding as a result of a Supply Point Nomination at Go Live will be cancelled and will not be migrated over" Will Shippers receive a cancellation flow. If so when and in what format |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Confirmation |  | Not clear whether in flight conformations with an effective date pre go live but in the non effective days will be processed. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Confirmation |  | Final bullet point around class change and registered Shipper sending a confirmation doesn’t make sense at all, need clarification. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Confirmation |  | No rules defined for confirmation cancellations |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Confirmation |  | No rules for transfer effective flow |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Confirmation |  | “All In-Flight Confirmations, accepted pre Go Live with an effective date post Go Live, will continue to be processed and will be effective and categorised under the default Class (see section 7.1 Supply Point Category).” Will Shippers receive a response be it acceptance or rejection prior to the non-effective days starting? So if we send a confirmation on D-1 will we receive a response the same day? I am not sure that this is the case? If not will we get the acceptance after the non effective days and in what format. |  |  | BG | Accept | Updated in assumptions
1 |  |  | Supply Point Confirmation |  | It appears that you cannot have a confirmation effective date during the non effective days for GT supplires but that you can for iGT supplies. Is this correct. |  |  | BG | Accept | A Confirmation can be effective on a 'non-effective day'.
1 |  | 7.2 | Supply Point Opening Reads |  | Not clear what happens to in flight opening reads. |  |  | BG | Accept | BRD updated
1 |  | 7.2 | Supply Point Opening Reads |  | Are non effective days treated as non working days. |  |  | BG | Reject | See Modification 0528
1 |  | 7.2 | Supply Point Opening Reads |  | What are the rules for flows associated with opening read submission e.g. acceptance flow. |  |  | BG | Accept | Updated in assumptions
1 |  | N/A | Ceased Responsibility |  | Ceased responsibility flow not captured CFR.S88 |  |  | BG | Accept | BRD updated
1 |  | N/A | Withdrawals |  | Nothing captured for withdrawals CFR.S10 |  |  | BG | Accept | BRD updated
1 |  | N/A | Voluntary Withdrawals |  | No rules defined for voluntary withdrawals |  |  | BG | Accept | BRD updated
1 |  | N/A | MRI, Meter Read Instructions |  | No rules for MRI (meter read instructions) flow |  |  | BG | Accept | BRD updated
1 |  | N/A | Connections and Disconnections |  | Need to understand what rules will be applied around compliance to C&D obligations |  |  | BG | Accept | No change to the existing obligations
1 |  | N/A | Erroneous Transfers |  | Rules for managing Erroneous Transfers |  |  | BG | Reject | Inter Shipper Dispute process
1 |  | N/A | Query Management |  | Will need the rules for the various query types in CMS |  |  | BG | Reject | Section 7.10
1 |  | N/A | N/A |  | For all files/transactions sent to Xoserve on the last day before go-live, will responses be created by Xoserve for all, and be sent back to the Shipper in the pre-Nexus format. This would include files/transactions sent just before go-live cut-off. |  |  | BG | Accept | Updated in assumptions
1 |  | N/A | N/A |  | What is the latest time Xoserve will return responses to Shippers on the last day before the non effective days |  |  | BG | Reject | Modification 0528
1 |  | N/A | N/A |  | For all files/transactions sent from Xoserve on the last day before go-live, will Xoserve accept and process responses sent by the Shipper in the pre-Nexus format |  |  | BG | Accept | Updated in assumptions
1 |  | N/A | N/A |  | What is the latest time the Shipper can return the responses by |  |  | BG | Reject | Modification 0528
1 |  | N/A | N/A |  | If flows miss the last batch before NEXUS then will: • Unchanged flows be processed post NEXUS? • Changed flows be rejected post NEXUS as invalid? |  |  | BG | Accept | Updated in assumptions
1 |  | N/A | N/A |  | What, if anything, will be reported to or sent to Shippers for files/transactions not processed at migration |  |  | BG | Accept | Updated in assumptions
1 |  | N/A | N/A |  | Can Xoserve produce a generic timeline (similar to one produced for iGT) that illustrates from pre-‘Go Live Date’ schedule that illustrates the rules for transition e.g. all confirmations to be submitted by GLD – 1 Working Day |  |  | BG | Reject | This will need to be done with Modification 0528
1 |  | N/A | N/A |  | What would happen to the daily MDR data logger readings during the non effecive day period, would we still receive them |  |  | BG | Reject | Modification 0528
1 |  | N/A | N/A |  | We would suggest that the transition documentation should detail every flow so we can be assured that we treat them correctly in our systems. |  |  | BG | Reject | This will be done with Modification 0528
1 |  | N/A | N/A |  | We would like to see some explantory text indicating the customer impacts particularly with regard to Change of Supplier and Objections scenarios. |  |  | BG | Reject | This will be done with Modification 0528
Note on H7: i.e. Full Document or Section*** etc