## Sheet1
Count | File Format | Tranche | Hierarchies | Version | File Format | Version | Record | Record Name | Revised Version Post UKLP | Included in Phase 1? | Included in Phase 2? | Recorded outcome of 24/11/14 | Comments
1 | AML | Billing & Invoicing | AML | V1 | AML | V1 | K43 | RT_K43_STANDARD_INDIVIDUAL_SMP_FILE_DETAIL |  |  | CA | Hierarchy App'd A | NWO Short Code / Invoice Number to be Mandatory (Ph2 00138) EUC Number update to Numeric for Core Invoice files (Ph3 00020)
[7 empty] | K92 | RT_K92_AMENDMENTS_SMP_DETAIL_CLASS_3_AND_4 |  |  |  | A | Note: Ph3 00197/198 response regarding default values.
2 | ASP | Billing & Invoicing | ASP | V1 | ASP | V1 | J13 | RT_J13_REC_INV_RBD_CHARGE |  |  |  | Hierarchy App'd A
[7 empty] | J14 | RT_J14_REC_INV_RBD_LDZ_AGGREGATE |  |  |  | A
[7 empty] | J15 | RT_J15_REC_INV_RBD_SPG_DETAIL |  |  |  | A
[7 empty] | J42 | RT_J42_ DAILY_SUMMARY_NTS_OPTIONAL_TARIFF |  |  |  | A
[7 empty] | K42 | RT_K42_COMM_CHARGE_ITEM |  |  | CA / A (various) | A | No specific comments against this record in Phase 2
[7 empty] | K84 | RT_K84_CAPACITY_RECONCILIATION_CHARGE |  |  |  | A | Context to be added to Charge Amount fields to denote that this should only ever be a charge value (Ph3 00205/587/588).
[7 empty] | K88 | RT_K88_RECONCILIATION_INVOICE_CHARGE_CLASS_4_LSP |  |  |  | A | Context to be updated for Organisation Short Code to denote organisation types (Ph3 00002) Note: Ph3 00207/00208 response regarding default values.
[7 empty] | K89 | RT_K89_RECONCILIATION_INVOICE_CHARGE_CLASS_1_2_3_LSP |  |  |  | A
[7 empty] | K90 | RT_K90_RECONCILIATION_INV_AGGREGATE_DETAIL_CLASS_3_4_SSP |  |  |  | A
[7 empty] | K91 | RT_K91_RECONCILIATION_INVOICE_UG_SMEAR |  |  |  | A
[7 empty] | K93 | RT_K93_AMENDMENT_SMP_DETAIL |  |  |  | A | MRF_TYPE_CODE to be amended to reflect that this is the billing version of this field (Ph3 00210)
[7 empty] | Q28 | RT_Q28_STANDARD_INVOICE_SUMMARY |  |  | CA | A | Billing Month AVs to be amended (Ph2 00284) Deleted Field to be Reinstated as SAP Reference Number (Ph2 WT006)
3 | CFR | Stakeholder, RGMA, SPA | CFR | V7 |  |  | K12 | RT_K12_MAM_GAO_DETAIL | V7 |  | A | Hierarchy App'd CA | No specific comments against this record in Phase 2 Phase 3 format needs to have total corrected (Ph3 50, 73, 507)
[7 empty] | K14 | RT_K14_ADDITIONAL_METERING INFORMATION | V4 |  | CA |  | Version control table to be amended (Ph2 00194)
[7 empty] | K85 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 |  | CA |  | Not yet implemented Mod 487 (Phase 2)
[7 empty] | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D | D
[7 empty] | Q45 | RT_Q45_DNI_INFO | V1 |  |  | A
[7 empty] | S07 | RT_S07_ACCEPTED_CONFIRMATION | V7 |  |  | CA | Customer Capacity Rate will be removed from record (Ph2 00023). Rate Units will be added to the descriptions (Ph3 00097 / 00098 / 00099) Interuptible_Allowance - decription to be amended to include days.
[7 empty] | S09 | RT_S09_REJECT_COMPETITIVE_CONF | V3 |  |  | A
[7 empty] | S10 | RT_S10_SP_WITHDRAWAL_NOTICE | V8 |  |  | A
[7 empty] | S16 | RT_S16_REJECT_NON_COMPTITVE_CONF | V4 |  |  | CA | REQUESTED_DM_SHQ description to relect SSP sites can not be in Class 1 portfolio (Ph3 WT00002) SUPPLY_POINT_CLASS to be updated to Mandatory (Ph3 WT002) - nb - it is already.
[7 empty] | S66 | RT_S66_CONTACT_DETAILS | V2 | A |  |  | No specific comments against this record in Phase 1
[7 empty] | S67 | RT_S67_ELECTRONIC_DEVICE | V2 | A |  | D | No specific comments against this record in Phase 1 OUTSTANDING Q RE CHANGE TO FIELD CHARACTERS
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D | A
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | S75 | RT_S75_METER_POINT_DETAILS | V6 |  | CA |  | Name change to Operational Status EFD (Ph2 00223)
[7 empty] | S77 | RT_S77_WITHDRAWAL_MP_DETAILS | V6 |  |  | A
[7 empty] | S83 | RT_S83_END_CONSUMER_DETAILS
[7 empty] | S84 | RT_S84_SPECIAL_CONDITIONS | V2 | A |  |  | No specific comments against this record in Phase 1
[7 empty] | S98 | RT_S98_SMART_DATA | V2 | D | NR | A | Deferred in Phase 1 in error. U06/N90 deferred due to questions outstanding. No matters outstanding with respect to S98.
[7 empty] | T06 | RT_T06_CONF_CANCELLATION_RESPONS | V2 |  |  | A
[7 empty] | T07 | RT_T07_CONF_CANCELLATION_NOTICE | V7 |  |  | A
[7 empty] | U70 | RT_U70_NTS_OPTIONAL_RATE_REQ | V1 |  | A | CA | NOTE: this record inserted into control sheet 24/11/14 No specific comments against this record in Phase 2 SPECIFIED_ENTRY_POINT_NAME to be extended to 40 characters (Ph3 00613)
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U72 | RT_U72_LDZ_OPTIONAL_RATE_REQ | V1 |  | A | CA | NOTE: this record inserted into control sheet 24/11/14 No specific comments against this record in Phase 2
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U74 | RT_U74_CSO_DETAILS | V1 |  | CA |  | CSO Contact Tel Number to be Text, 15 (Ph2 00165)
[7 empty] | U75 | RT_U75_METER_ASSET_DETAILS | V6 |  | A |  | No specific comments against this record in Phase 1
4 | CNF | Stakeholder, RGMA, SPA | CNF | V3 |  |  | S38 | RT_S38_CONFIRM_COMPTVE_SUPPLY_PT | V3 |  |  | Hierarchy App'd A
[7 empty] | S42 | RT_S42_CONFIRM_NON_COMPETVE_SP | V4 |  |  | A
[7 empty] | S66 | RT_S66_CONTACT_DETAILS | V2 | A |  |  | No specific comments against this record in Phase 1
[7 empty] | S67 | RT_S67_ELECTRONIC_DEVICE | V2 | A |  | D | No specific comments against this record in Phase 1
[7 empty] | S83 | RT_S83_END_CONSUMER_DETAILS
[7 empty] | S84 | RT_S84_SPECIAL_CONDITIONS | V2 | A |  |  | No specific comments against this record in Phase 1
[7 empty] | T05 | RT_T05_CONF_CANCELLATION_REQUEST | V2 |  |  | A
[7 empty] | U70 | RT_U70_NTS_OPTIONAL_RATE_REQ | V1 |  | A | CA | No specific comments against this record in Phase 2 SPECIFIED_ENTRY_POINT_NAME to be extended to 40 characters (Ph3 00613)
[7 empty] | U72 | RT_U72_LDZ_OPTIONAL_RATE_REQ | V1 |  | A | CA | No specific comments against this record in Phase 2
5 | CRF | Stakeholder, RGMA, SPA | CRF | V2 |  |  | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D | Hierarchy App'd D
[7 empty] | Q46 | RT_Q46_IGT_RESPONSE | V1 | D | D | D
[7 empty] | S05 | RT_S05_SP_CAPACITY_CHANGE | V2 |  |  | A
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U82 | RT_U82_NTS_OPT_RATE_CHAN_RESP | V1 |  |  | A
6 | DCF | Stakeholder, RGMA, SPA | DCF |  |  |  | S08 | RT_S08_LAPSED_CONFIRMATION_DETS | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
[7 empty] | S63 | RT_S63_NTFN_OF_RETAINED_RESPONS | V2 |  |  | A
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D | A | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | S76 | RT_S76_LAPSED_CONF_MP_DETAILS | V5 |  |  | A
[7 empty] | S88 | RT_S88_CEASED_RESPONSIBILITY | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
7 | DNE | Settlement | DNE | V1 |  |  | E89 | RT_E89_DAILY_ENERGY | V1 |  |  | Hierarchy App'd A
[7 empty] | E90 | RT_E90_SHIPPER_DETAILS | V1 |  |  | A
[7 empty] | E91 | RT_E91_ENERGY_REC_DATA | V1 |  |  | A
[7 empty] | E92 | RT_E92_SHIPPER_ALLOCATION | V1 |  |  | A
8 | DNR | Settlement | DNR | V1 |  |  | E87 | RT_E87_REC_ENERGY_SPLIT | V1 |  |  | Hierarchy App'd A
[7 empty] | E88 | RT_E88_SHIPPER_REC_ALLOCATION | V1 |  |  | A
9 | EXZ | Stakeholder, RGMA, SPA | EXZ |  |  |  | M13 | RT_M13_EXZ_LDZ_DETAILS | V1
[7 empty] | M15 |  |  |  |  | D | OMISSION FROM START OF DAY
[7 empty] | S31 | RT_S31_INVALID_OFFER_DETAILS | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D | A | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
10 | MIN | Stakeholder, RGMA, SPA | MIN | V2 |  |  | C73 | RT_C73_CHECK_READ_DUE_NOTFN | V1 |  |  | Hierarchy App'd A
[7 empty] | M96 | RT_M96_METER_INSPECT_DUE_NOTICE | V2 |  |  | A
[7 empty] | O52 | RT_O52_FAULT_NOTFN | V1 |  |  | A
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D | A | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
11 | NRL | Weather Variance Correction | NRL | V2 |  |  | S91 | RT_S91_NTFN_OF_SP_REVISION | V3 |  |  | Hierarchy App'd A
[7 empty] | T04 | RT_T04_NTFN_MP_AQ_REVISION | V3 |  |  | CA | EUC_Description will be added to the end of the record (Ph3 WT006) CLASS_1_THRESHOLD CROSSER description to be updated (Ph3 00030) FAILURE_REASON_CODE - list of warning codes to be provided (Ph3 00031)
[7 empty] | T50 | RT_T50_NTFN_MP_WC_REVISION | V2 |  |  | A
[7 empty] | T51 | RT_T51_WC_CALC_WARNINGS_REPORT | V1 |  |  | A
[7 empty] | T97 | RT_T97_REVISED_AQ_IMPACTS_INFO | V1 |  |  | D | Values that flag action being required - description to be updated to assist Users (Ph3 000563 / 564 / 565)
[7 empty] | T98 | RT_T98_AQ_CALC_FAILURE | V1 |  |  | A
12 | PNS | Billing & Invoicing | PNS | V1 | PNS | V1 | K86 | RT_K86_PRIME_AND_SUB_CHARGE_SUMMARY |  |  |  | Hierarchy App'd CA
[7 empty] | K87 | RT_K87_ PRIME_AND_SUB_CHARGE_DETAIL |  |  |  | CA
[7 empty] | Q28 | RT_Q28_STANDARD_INVOICE_SUMMARY |  |  | CA |  | Billing Month AVs to be amended (Ph2 00284) Deleted Field to be Reinstated as SAP Reference Number (Ph2 WT006)
[7 empty] | Q29 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  |  | CA / A (various) |  | No specific comments against this record in Phase 2
13 | RTO | Stakeholder, RGMA, SPA | RTO | V1 |  |  | ASSET | ASSET (DATASET-RGMA) | V13 | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | CONVE | CONVE (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | HEADR | HEADR (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | METER | METER (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | MTPNT | MTPNT (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | READG | READG (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | REGST | REGST (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | TRAIL | TRAIL (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
14 | RTR | Stakeholder, RGMA, SPA | RTR | V1 |  |  | HEADR | HEADR (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | REJFL | REJFL (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | REJRS | REJRS (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | TRAIL | TRAIL (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
[7 empty] | TROUT | TROUT (DATASET-RGMA) |  | D |  | D | Deferral in Phase 1 relates to JOB / UPD extension.
15 | SCR | Stakeholder, RGMA, SPA | SCR | V3 |  |  | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D | Hierarchy App'd D
[7 empty] | S03 | RT_S03_SP_MRF_AND_BATCH_FREQ_CHANGE | V3 |  |  | A
[7 empty] | S04 | RT_S04_SP_MRF_AND_BATCH_FREQ_CANCELLATION | V3 | A |  | CA | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2 BATCH_SUBMISSION_FREQUENCY description (to ref required for Class 3) - UKLC to note. (Ph3 00377)
[7 empty] | S05 | RT_S05_SP_CAPACITY_CHANGE | V2 |  |  | CA | COMMENTS field name to be updated to REFERRAL COMMENTS to provide context (Ph3 00570) Rates fields - rates to be added to description as required (Ph3 00092)
[7 empty] | S06 | RT_S06_SP_CAPACITY_CANCELLATION | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U82 | RT_U82_NTS_OPT_RATE_CHAN_RESP | V1 |  |  | A
[7 empty] | U83 | RT_U83_NTS_OPT_RATE_CAN_RESP | V1 |  |  | A
[7 empty] | X09 | RT_X09_SP_CLASS_CHANGE | V1 |  |  | A
[7 empty] | X10 | RT_X10_SP_CLASS_CHANGE_CANCELLATION | V1 |  |  | A
16 | SPC | Stakeholder, RGMA, SPA | SPC | V3.1 |  |  | C38 | RT_C38_CLASS_CHANGE | V1 | NR |  | Hierarchy App'd A
[7 empty] | C39 | RT_C39_CLASS_CHANGE_CANCELLATION | V1 | NR |  | A
[7 empty] | S34 | RT_S34_MRF_AND_BATCH_FREQ_CHANGE_REQUEST | V3 | NR |  | CA | Include additional context in Batch Submission Frequency description (Ph2 00277)
[7 empty] | S35 | RT_S35_CANCEL_MRF_AND_BATCH_FREQ_CHANGE_REQ | V3 | NR |  | CA | Include additional context in Batch Submission Frequency description (Ph2 00278)
[7 empty] | S36 | RT_S36_SP_CAPACITY_CHANGE_REQ | V2 | NR |  | A
[7 empty] | S37 | RT_S37_CANCEL_SP_CAPACITY_CHG | V2 | NR |  | A
[7 empty] | U80 | RT_U80_NTS_OPT_RATE_CHANGE | V1 | NR |  | A
[7 empty] | U81 | RT_U81_NTS_OPT_RATE_CANCEL | V1 | NR |  | A
17 | SPI | Stakeholder, RGMA, SPA | SPI |  |  |  | X99 | RT_X99_SHIPPER_SUPPLY_PORTFOLIO_INPUT | V2 |  |  | D | REF MOD0431
18 | SPO | Stakeholder, RGMA, SPA | SPO |  |  |  | X98 | RT_X98_SHIPPER_SUPPLY_PORTFOLIO_OUTPUT | V2 |  |  | D | COMMENTS field name to be updated to provide context (Ph3 00491)
19 | STN | Stakeholder, RGMA, SPA | STN | V1 |  |  | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D | Hierarchy App'd D
[7 empty] | U76 | RT_U76_NETWORK_CHANGE_DETAILS | V1 |  |  | D
[7 empty] | U79 | RT_U79_SUPPLY_METER_POINT_INFO | V1 |  |  | D
20 | TRF | Stakeholder, RGMA, SPA | TRF | V9 |  |  | K12 | RT_K12_MAM_GAO_DETAIL | V7 |  | A | Hierarchy App'd CA | No specific comments against this record in Phase 2
[7 empty] | K13 | RT_K13_SMP_CEASE_OWN_DETS | V7 |  |  | A | CORRECTS FOR COMPLIANCE WITH UNC G2.8.8
[7 empty] | K85 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 |  | CA | CA | Not yet implemented Mod 487 (Phase 2)
[7 empty] | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D | D
[7 empty] | Q45 | RT_Q45_DNI_INFO | V1 |  |  | A
[7 empty] | S08 | RT_S08_LAPSED_CONFIRMATION_DETS | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
[7 empty] | S15 | RT_S15_TRANSFER_OF_OWNERSHIP | V7 |  |  | D | Rates fields - rates to be added to description as required (Ph3 00115 / 116) WT007 APPLIES
[7 empty] | S63 | RT_S63_NTFN_OF_RETAINED_RESPONS | V2 |  |  | A
[7 empty] | S66 | RT_S66_CONTACT_DETAILS | V2 | A |  |  | No specific comments against this record in Phase 1
[7 empty] | S67 | RT_S67_ELECTRONIC_DEVICE | V2 | A |  | D | No specific comments against this record in Phase 1
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D | A | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | S75 | RT_S75_METER_POINT_DETAILS | V6 |  | CA |  | Name change to Operational Status EFD (Ph2 00223)
[7 empty] | S76 | RT_S76_LAPSED_CONF_MP_DETAILS | V5 |  |  | A
[7 empty] | S88 | RT_S88_CEASED_RESPONSIBILITY | V2 | A |  |  | No specific comments against this record in Phase 1 Noted as Previously Approved in Phase 2
[7 empty] | S98 | RT_S98_SMART_DATA | V2 | D | NR | A | Deferred in Phase 1 in error. U06/N90 deferred due to questions outstanding. No matters outstanding with respect to S98.
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA | A | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA | A | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U74 | RT_U74_CSO_DETAILS | V1 |  | CA | A | CSO Contact Tel Number to be Text, 15 (Ph2 00165)
[7 empty] | U75 | RT_U75_METER_ASSET_DETAILS | V6 |  | A | A | No specific comments against this record in Phase 1
| 20 |  | 20 |  |  |  | 144
[12 empty] | CA | Caveated Approval
[8 empty] | New Product for UKLP |  |  |  | A | Approved
[8 empty] | Product Amended for UKLP |  |  |  | D | Deferred
[8 empty] | Product Unchanged for UKLP |  |  |  | R | Reject
[12 empty] | A | Approved in previous phase, but amended format in subsequent phase
[12 empty] | NR | NR - Approval held until subsequent phase
Note: Amendment to Phase 2 Control Sheet | [12 empty] | Not Required
16 | NMR | Stakeholder, RGMA, SPA | NMR | V6 |  |  | K12 | RT_K12_MAM_GAO_DETAIL | V7 |  | A |  | No specific comments against this record in Phase 2
[7 empty] | K14 | RT_K14_ADDITIONAL_METERING INFORMATION | V4 |  | CA |  | Version control table to be amended (Ph2 00194)
[7 empty] | K85 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 |  | CA |  | Not yet implemented Mod 487 (Phase 2)
[7 empty] | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D
[7 empty] | Q51 | RT_Q51_CONSUMPTION_INFORMATION | V1
[7 empty] | S21 | RT_S21_CUR_SP_NOM_REJ_OR_REF | V3 |  |  |  | Outcome Code - amend description (Ph2 00044)
[7 empty] | S59 | RT_S59_ACCEPT_SMP_ENQUIRY | V5
[7 empty] | S64 | RT_S64_OFFER_DETAILS | V6 |  |  |  | Customer Capacity Rate will be removed from record (Ph2 00023). Add Supply Point Class AVs (Ph2 00045)
[7 empty] | S68 | RT_S68_ENQ_SUPPLY_METER_POINT | V2
[7 empty] | S69 | RT_S69_NOM_SUPPLY_METER_POINT | V3
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D |  | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | S75 | RT_S75_METER_POINT_DETAILS | V6 |  | CA |  | Name change to Operational Status EFD (Ph2 00223)
[7 empty] | S78 | RT_S78_REJECT_SMP_ENQUIRY | V2
[7 empty] | S98 | RT_S98_SMART_DATA | V2 | D | NR |  | Deferred in Phase 1 in error. U06/N90 deferred due to questions outstanding. No matters outstanding with respect to S98.
[7 empty] | U70 | RT_U70_NTS_OPTIONAL_RATE_REQ | V1 |  | A |  | NOTE: this record inserted into control sheet 24/11/14 "No specific comments against this record in Phase 2 SPECIFIED_ENTRY_POINT_NAME to be extended to 40 characters (Ph3 00613)
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U72 | RT_U72_LDZ_OPTIONAL_RATE_REQ | V1 |  | A |  | NOTE: this record inserted into control sheet 24/11/14 "No specific comments against this record in Phase 2
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U74 | RT_U74_CSO_DETAILS | V1 |  | CA |  | CSO Contact Tel Number to be Text, 15 (Ph2 00165)
[7 empty] | U75 | RT_U75_METER_ASSET_DETAILS | V1 |  | A |  | No specific comments against this record in Phase 1
18 | NRF | Stakeholder, RGMA, SPA | NRF | V6 |  |  | K12 | RT_K12_MAM_GAO_DETAIL | V7 |  | A |  | No specific comments against this record in Phase 2
[7 empty] | K14 | RT_K14_ADDITIONAL_METERING INFORMATION | V4 |  | CA |  | Version control table to be amended (Ph2 00194)
[7 empty] | K85 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 |  | CA |  | Not yet implemented Mod 487 (Phase 2)
[7 empty] | Q44 | RT_Q44_CSEP_DETAILS | V1 | D | D
[7 empty] | Q46 | RT_Q46_IGT_RESPONSE | V1 | D | D
[7 empty] | S21 | RT_S21_CUR_SP_NOM_REJ_OR_REF | V3 |  |  |  | Outcome Code - amend description (Ph2 00044)
[7 empty] | S64 | RT_S64_OFFER_DETAILS | V6 |  |  |  | Customer Capacity Rate will be removed from record (Ph2 00023). Add Supply Point Class AVs (Ph2 00045)
[7 empty] | S69 | RT_S69_NOM_SUPPLY_METER_POINT | V3
[7 empty] | S70 | RT_S70_ADDRESS | V2 | NR | D |  | Identified as being in Phase 3, therefore no approval requested in Phase 1. Deferred in Phase 2 - as above.
[7 empty] | S72 | RT_S72_REJECTION_DETAIL
[7 empty] | S75 | RT_S75_METER_POINT_DETAILS | V6 |  | CA |  | Name change to Operational Status EFD (Ph2 00223)
[7 empty] | S98 | RT_S98_SMART_DATA | V2 | D | NR |  | Deferred in Phase 1 in error. U06/N90 deferred due to questions outstanding. No matters outstanding with respect to S98.
[7 empty] | U70 | RT_U70_NTS_OPTIONAL_RATE_REQ | V1 |  | A |  | NOTE: this record inserted into control sheet 24/11/14 "No specific comments against this record in Phase 2 SPECIFIED_ENTRY_POINT_NAME to be extended to 40 characters (Ph3 00613)
[7 empty] | U71 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U72 | RT_U72_LDZ_OPTIONAL_RATE_REQ | V1 |  | A |  | NOTE: this record inserted into control sheet 24/11/14 "No specific comments against this record in Phase 2
[7 empty] | U73 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 |  | CA |  | Caveated - To include SOQ in Glossary (Phase 2)
[7 empty] | U74 | RT_U74_CSO_DETAILS | V1 |  | CA |  | CSO Contact Tel Number to be Text, 15 (Ph2 00165)
[7 empty] | U75 | RT_U75_METER_ASSET_DETAILS | V1 |  | A |  | No specific comments against this record in Phase 1

## Sheet2 (hidden)
AAI | Settlement | Existing files to be decommissioned
AAO | Settlement | Existing files to be decommissioned
INV | Billing & Invoicing | New File
MIF | Billing & Invoicing | New File
AJI | Billing & Invoicing | Existing files to be decommissioned
AMI | Billing & Invoicing | Existing files to be decommissioned
API | Settlement | Existing files to be decommissioned
APO | Settlement | Existing files to be decommissioned
ASI | Settlement | Out of Scope
ASO | Settlement | Out of Scope
ASP | Billing & Invoicing | New File
BCD | Billing & Invoicing | Existing files to be decommissioned
BID | Stakeholder, RGMA, SPA | Existing files to be decommissioned
BIS | Stakeholder, RGMA, SPA | Existing file with Changes required
BTF | Stakeholder, RGMA, SPA | Existing files to be decommissioned
CAA | Billing & Invoicing | Existing files to be decommissioned
CAN | Billing & Invoicing | Existing files to be decommissioned
CAR | Stakeholder, RGMA, SPA | Existing files to be decommissioned
CAZ | Billing & Invoicing | Existing files to be decommissioned
CEP | Billing & Invoicing | Existing files to be decommissioned
CFR | Stakeholder, RGMA, SPA | Existing file with Changes required
CNC | Stakeholder, RGMA, SPA | Existing file with Changes required
CNF | Stakeholder, RGMA, SPA | Existing file with Changes required
CNR | Stakeholder, RGMA, SPA | Existing file with Changes required
COA | Billing & Invoicing | Existing files to be decommissioned
COM | Billing & Invoicing | Existing file with Changes required
COY | Billing & Invoicing | Existing files to be decommissioned
CRC | Billing & Invoicing | Out of Scope
CRE | Billing & Invoicing | Existing files to be decommissioned
CRF | Stakeholder, RGMA, SPA | Existing file with Changes required
CSD | Billing & Invoicing | Existing files to be decommissioned
CTR | Stakeholder, RGMA, SPA | Existing file with changes required
Retro Adj | Billing & Invoicing | Out of Scope
ZCS | Billing & Invoicing | Existing file with Changes required
DCF | Stakeholder, RGMA, SPA | Existing file with changes required
DES | Stakeholder, RGMA, SPA | New File
DMI | Settlement | Existing files to be decommissioned
DMR | Settlement | Existing files to be decommissioned
DPP | Stakeholder, RGMA, SPA | Existing file with changes required
DPS | Stakeholder, RGMA, SPA | Existing file with Changes required
DRS | Stakeholder, RGMA, SPA | Existing file with changes required
ECB | Billing & Invoicing | Existing file with no changes but required
ECO | Billing & Invoicing | Existing file with no changes but required
EMC | Stakeholder, RGMA, SPA | Existing file with changes required
Energy summary | Billing & Invoicing | Existing files to be decommissioned
EOI | Billing & Invoicing | Existing file with Changes required
EPS | Stakeholder, RGMA, SPA | Existing file with Changes required
ERR | Stakeholder, RGMA, SPA | Existing file with no changes but required
UDR | Settlement | New File
EUC | Weather Variance Correction | Existing file with changes required
UBR | Settlement | New File
EXZ | Stakeholder, RGMA, SPA | Existing file with Changes required
FRJ | Stakeholder, RGMA, SPA | Existing file with no changes but required
FSI | Billing & Invoicing | Existing file with Changes required
GEA | Stakeholder, RGMA, SPA | Existing file with Changes required
GEO | Stakeholder, RGMA, SPA | Existing file with Changes required
GTR | Stakeholder, RGMA, SPA | Existing files to be decommissioned
IBC | Stakeholder, RGMA, SPA | Existing files to be decommissioned
ICE | Billing & Invoicing | Existing files to be decommissioned
IDB | Billing & Invoicing | Existing file with no changes but required
IDC | Billing & Invoicing | Existing files to be decommissioned
IDS | Billing & Invoicing | Existing files to be decommissioned
INT | Billing & Invoicing | Existing files to be decommissioned
JOB | Stakeholder, RGMA, SPA | Existing file with changes required
JRS | Stakeholder, RGMA, SPA | Existing file with no changes but required
LPA | Settlement | Existing file with changes required
LSE | Billing & Invoicing | Existing files to be decommissioned
MAM | Stakeholder, RGMA, SPA | Existing file with changes required
MAS | Stakeholder, RGMA, SPA | Existing file with changes required
MBR | Settlement | Existing file with Changes required
MDE | Settlement | Existing files to be decommissioned
MDR | Settlement | Existing file with Changes required
MID | Stakeholder, RGMA, SPA | Existing file with changes required
MIN | Stakeholder, RGMA, SPA | Existing file with changes required
MIO | Stakeholder, RGMA, SPA | Existing file with changes required
MIR | Stakeholder, RGMA, SPA | Existing file with changes required
MPD | Stakeholder, RGMA, SPA | Existing file with Changes required
MPE | Stakeholder, RGMA, SPA | Existing file with Changes required
MRI | Stakeholder, RGMA, SPA | Existing file with Changes required
MRT | Settlement | Existing files to be decommissioned
MSI | Stakeholder, RGMA, SPA | Existing file with changes required
MSL | Stakeholder, RGMA, SPA | Existing files to be decommissioned
MSO | Stakeholder, RGMA, SPA | Existing file with changes required
ADH | Billing & Invoicing | Existing files to be decommissioned
NSC | Billing & Invoicing | Existing file with Changes required
AML | Billing & Invoicing | New File
CZI | Billing & Invoicing | New File
COI | Billing & Invoicing | New File
GSOS | Billing & Invoicing | Out of Scope
DNI Contract | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SPI | Stakeholder, RGMA, SPA | Existing file with changes required
MAI | Stakeholder, RGMA, SPA | Existing file with changes required
NMR | Stakeholder, RGMA, SPA | Existing file with Changes required
NMS | Stakeholder, RGMA, SPA | New File
NOM | Stakeholder, RGMA, SPA | Existing file with Changes required
NRF | Stakeholder, RGMA, SPA | Existing file with Changes required
NRL | Weather Variance Correction | Existing file with Changes required
NRM | Settlement | Existing files to be decommissioned
NRO | Stakeholder, RGMA, SPA | Existing files to be decommissioned
NRQ | Settlement | Existing files to be decommissioned
NRS | Settlement | Existing files to be decommissioned
NTE | Billing & Invoicing | Existing file with no changes but required
NXC | Billing & Invoicing | Existing file with no changes but required
OOA | Billing & Invoicing | Existing files to be decommissioned
OTA | Billing & Invoicing | Existing file with no changes but required
PAC | Stakeholder, RGMA, SPA | Existing file with Changes required
PEM | Stakeholder, RGMA, SPA | Existing files to be decommissioned
PIR | Stakeholder, RGMA, SPA | Existing file with Changes required
PPN | Stakeholder, RGMA, SPA | Existing file with Changes required
PRN | Settlement | Existing file with Changes required
RA1 | Billing & Invoicing | Existing files to be decommissioned
RAT | Settlement | Existing file with Changes required
RCS | Billing & Invoicing | Existing files to be decommissioned
REC | Billing & Invoicing | Existing files to be decommissioned
RFA | Stakeholder, RGMA, SPA | Existing file with changes required
RFR | Stakeholder, RGMA, SPA | Existing file with changes required
RFS | Stakeholder, RGMA, SPA | Existing file with Changes required
RP1 | Stakeholder, RGMA, SPA | Existing files to be decommissioned
RP2 | Stakeholder, RGMA, SPA | Existing files to be decommissioned
RPO | Settlement | Existing files to be decommissioned
RSN | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SAR | Billing & Invoicing | Existing files to be decommissioned
SBF | Stakeholder, RGMA, SPA | Existing file with Changes required
SC8 | Settlement | Existing file with no changes but required
SC9 | Settlement | Existing file with no changes but required
SCE | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SCH | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SCI | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SCL | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SCM | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SCR | Stakeholder, RGMA, SPA | Existing file with Changes required
SDP | Settlement | Existing files to be decommissioned
SPC | Stakeholder, RGMA, SPA | Existing file with Changes required
SPO | Stakeholder, RGMA, SPA | Existing file with changes required
SRC | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SRN | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SRR | Stakeholder, RGMA, SPA | Existing files to be decommissioned
IIS | Billing & Invoicing | Existing file with Changes required
SSI | Stakeholder, RGMA, SPA | Existing files to be decommissioned
SUN | Stakeholder, RGMA, SPA | Existing files to be decommissioned
4 | Stakeholder, RGMA, SPA | New File identified in HLD and now no longer required
TAP | Stakeholder, RGMA, SPA | Existing file with Changes required
TDS | Billing & Invoicing | Existing file with Changes required
TFR | Stakeholder, RGMA, SPA | Existing files to be decommissioned
OSG | Billing & Invoicing | Existing file with Changes required
TRF | Stakeholder, RGMA, SPA | Existing file with Changes required
UGC | Billing & Invoicing | Existing files to be decommissioned
UMR | Settlement | Existing file with Changes required
UNR | Stakeholder, RGMA, SPA | Existing file with no changes but required
UPD | Stakeholder, RGMA, SPA | Existing file with changes required
UPN | Stakeholder, RGMA, SPA | Existing files to be decommissioned
UPR | Stakeholder, RGMA, SPA | Existing file with no changes but required
URN | Settlement | Existing file with Changes required
URS | Settlement | Existing file with Changes required
USI | Billing & Invoicing | Existing files to be decommissioned
UPI | Billing & Invoicing | Existing file with Changes required
USR | Billing & Invoicing | Existing files to be decommissioned
WAO | Stakeholder, RGMA, SPA | Existing file with changes required
WOI | Weather Variance Correction | Existing files to be decommissioned
WOO | Weather Variance Correction | Existing files to be decommissioned
WOR | Stakeholder, RGMA, SPA | Existing file with changes required
WSI | Weather Variance Correction | Out of Scope
WSN | Weather Variance Correction | Existing files to be decommissioned
WSO | Weather Variance Correction | Out of Scope
FGI | Billing & Invoicing | Existing files to be decommissioned
interest | Billing & Invoicing | Existing files to be decommissioned
Invalid Query | Billing & Invoicing | Existing files to be decommissioned
late paid sup info | Billing & Invoicing | Existing files to be decommissioned
LPF eoy sub | Billing & Invoicing | Existing files to be decommissioned
Meter Liq damage | Billing & Invoicing | Existing files to be decommissioned
(MOD565 supp info) | Billing & Invoicing | Existing files to be decommissioned
PNS | Billing & Invoicing | Existing file with Changes required
P&S supp info no cyclic | Billing & Invoicing | Existing files to be decommissioned
P&S supp info no OPNT | Billing & Invoicing | Existing files to be decommissioned
P&S supp info no OPNT supp info | Billing & Invoicing | Existing files to be decommissioned
RTB supp info | Billing & Invoicing | Existing files to be decommissioned
RTO | Stakeholder, RGMA, SPA | New File
RTR | Stakeholder, RGMA, SPA | New File
Ancillary supp info | Billing & Invoicing | New File identified in HLD and now no longer required
DUS | Billing & Invoicing | Existing files to be decommissioned
SCD | Billing & Invoicing | Existing files to be decommissioned
AAE | Stakeholder, RGMA, SPA | Existing files to be decommissioned
AAP | Stakeholder, RGMA, SPA | Existing files to be decommissioned
AES | Stakeholder, RGMA, SPA | New File
SWN | Stakeholder, RGMA, SPA | New File
AQI | Stakeholder, RGMA, SPA | New File
AQR | Stakeholder, RGMA, SPA | New File
SFN | Settlement | New File
SFR | Settlement | New File
DNR | Settlement | New File
DNE | Settlement | New File
LIA | Billing & Invoicing | New File

## Sheet3 (hidden)
AML | V1
ASP | V1
CFR | V7
CNF | V3
CRF | V2
DNE | V1
DNR | V1
MIN | V2
NRL | V2
PNS | V1
RTO | V1
RTR | V1
SCR | V3
SPC | V3.1
STN | V1
TRF | V9

## Sheet4 (hidden)
ASSET | V13
ASSET | V13
C37 | V1
C38 | V1
C39 | V1
C41 | V1
C42 | V1
C43 | V1
C45 | V1
C50 | V1
C52 | V1
G40 | V2
I68 | V3
K08 | V6
K09 | V6
K15 | V4
M00 | V6
M12 | V3
M15 | V2
M79 | V6
M80 | V5
M81 | V6
M82 | V6
M83 | V6
M84 | V6
M93 | V2
M96 | V2
N11 | V2
N44 | V2
N45 | V2
N90 | V6
N93 | V3
N94 | V3
N95 | V4
N99 | V1
O15 | V1
O17 | V1
O20 | V1
O22 | V1
P17 | V3
Q01 | V6
Q02 | V3
Q03 | V6
Q04 | V6
Q05 | V5
Q06 | V5
Q23 | V6
Q44 | V1
S04 | V3
S06 | V2
S08 | V2
S24 | V2
S31 | V2
S34 | V3
S35 | V3
S36 | V2
S37 | V2
S51 | V2
S66 | V2
S67 | V2
S70 | V2
S81 | V2
S82 | V2
S84 | V2
S85 | V2
S86 | V2
S88 | V2
S89 | V2
S90 | V2
S93 | V2
S94 | V2
S98 | V2
T08 | V2
T67 | V3
T73 | V2
T74 | V2
U01 | V5
U02 | V5
U03 | V5
U04 | V5
U06 | V10
U10 | V5
U12 | V1
U13 | V1
U14 | V1
C70 | V1
C71 | V1
K12 | V7
K14 | V2
K85 | V1
M03 | V9
Q46 | V1
Q51 | V1
S11 | V2
S12 | V3
S13 | V2
S14 | V2
S21 | V3
S26 | V2
S30 | V5
S39 | V2
S40 | V3
S41 | V2
S47 | V2
S48 | V3
S54 | V2
S59 | V5
S64 | V6
S65 | V2
S68 | V2
S69 | V3
S73 | V2
S74 | V2
S75 | V6
S78 | V2
S96 | V2
S97 | V2
U70 | V1
U71 | V1
U72 | V1
U73 | V1
U74 | V1
U75 | V6
C73 | V1
E87 | V1
E88 | V1
E89 | V1
E90 | V1
E91 | V1
E92 | V1
K12 | V7
K13 | V7
M15 | V2
O52 | V1
Q45 | V1
S03 | V3
S05 | V2
S07 | V7
S09 | V3
S10 | V8
S15 | V7
S16 | V4
S38 | V3
S42 | V4
S63 | V2
S76 | V5
S77 | V6
S91 | V3
T04 | V3
T05 | V2
T06 | V2
T07 | V7
T50 | V2
T51 | V1
T97 | V1
T98 | V1
U76 | V1
U79 | V1
U80 | V1
U81 | V1
U82 | V1
U83 | V1
X09 | V1
X10 | V1
X98 | V2
X99 | V2
RTO Dataset | V1
RTR Dataset | V1