## Slide 1: Change Overview Board Change Horizon Quarterly Review
5 October 2015

## Slide 2: Gas Central Services Change Horizon October 2015
1-2 yrs.
2-5 yrs.
> 5 yrs.
Ones to
watch
Policy
undefined
Deliverables Undefined
Deliverables
in Definition
Firm
Deliverables
DCC Day 1
[Q2/3 2016]
High
I
Nexus/UKLP
[Q3 2016]
High
I
EU Reform #1
[Q4 2015]
High
R
SCR Cashout
[Q4 2015]
Medium
R
TRAS
[Q1 2016]
Medium
I
PAF
[Q3 2016]
High
I
Energy Market Investigation
R
Constitutional Reform
L
GB Shale
Gas
Low
I
FGO Part 2
[Q1 2017]
High
R
Tariffs Reform
[Q3 2017]
Medium
R
Settlement
Evolution
High
I
Beyond EU 3rd Energy Package
Medium
R
Gemini
Rewrite
High
I
Contact Mgt
[2018]
I
Medium
Medium
NDS & Central Reg’n [2019]
High
R
UK Membership of EU
High
L
PSR
[from Q2 2017}
High
R
Key | 
 | Legislative Change
 | Regulatory Change
 | Industry Change
 | Level of impact
 | Movement since previous report
High
Medium
Low
L
R
I
ZONE 3
ZONE 2
ZONE 1
Industry Governance
Low
R
EU Reform #2
[Q2/3 2016]
High
R
Medium
X
X
FGO Part 1
[Q1 2016]
High
R
X

## Slide 3: Change Horizon Updates
Zone 3 | EU Reform #1 – implemented and proposed for closure SCR Gas Cashout – implemented and proposed for closure TRAS – proposed for closure PAF – implementation assumed to be in line with Project Nexus FGO – phased implementation in April 2016 and April 2017
Zone 2 | Priority Services Register - implementation date uncertain, but moved out to no earlier than Q2 2017, i.e. at least 6 months after Nexus go live; topic paper to be reviewed following Ofgem policy update at this meeting Next Day Switching and Centralised Registration Service – Ofgem update of CRS TOM expected before end 2015
Zone 1 | Energy Market Investigation – timetable for final decision extended to April 2016