## Shipper
Process | Sub Process | File Type | Inbound/ Outbound | Stakeholder | Last received time in legacy | Last processed time in legacy | Last response time (approx.) in legacy | Post Go Live first received time | Post Go Live first processed time | Post Go Live first response time (approx.) | Key Notes | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-28 | 2017-05-29 | 2017-05-30 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-03 | 2017-06-04 | 2017-06-05 | 2017-06-06 | 2017-06-07
[12 empty] | Business As Usual |  | 7 Non Effective Days | [8 empty] | 2 VNBD - Variable Non Business days |  | Business As Usual
Implementation Window
Supply Point Registration (GT Sites) | Nominations | NOM | Inbound | Shipper | 2017-05-22 23:14 | 2017-05-22 23:15 | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA | Last processing batch schedule for NOM file will be at 23:15. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | NMR | Outbound | Shipper | NA | NA | 2017-05-22 23:45 | NA | NA | 2017-06-01 12:15 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | NRF | Outbound | Shipper | NA | NA | 2017-05-22 18:00 | NA | NA | 2017-06-01 16:00 | All the outstanding nomination referrals which have not been cleared by DNs by 22nd May 2017 will be pulled back and invalidated. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Confirmations | CNF | Inbound | Shipper | 2017-05-22 23:00 | 2017-05-22 23:15 | NA | 2017-06-01 00:01 | 2017-06-01 11:00 | NA | Last processing batch schedule for CNF file will be at 23:15. The previous day batch cycles should be used to avoid any delays/rejection issues.Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CFR | Outbound | Shipper | NA | NA | 2017-05-22 23:45 | NA | NA | 2017-06-01 12:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Objections | WAO | Inbound | Shipper | 2017-05-22 23:19 | 2017-05-22 23:20 | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA | Last processing batch schedule for WAO file will be at 23:15. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | WOR | Outbound | Shipper | NA | NA | 2017-05-22 23:45 | NA | NA | 2017-06-01 12:15 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | DCF | Outbound | Shipper | NA | NA | 2017-05-22 01:30 | NA | NA | 2017-06-01 02:10 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Voluntary Withdrawals | WAO | Inbound | Shipper | 2017-05-22 23:14 | 2017-05-22 23:15 | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA | Last processing batch schedule for WAO file will be at 23:15. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | WOR | Outbound | Shipper | NA | NA | 2017-05-22 23:45 | NA | NA | 2017-06-01 12:15 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MPE | Outbound | Shipper | NA | NA | 2017-05-22 01:30 | NA | NA | 2017-06-01 02:10 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Transfer of Ownership | TRF | Outbound | Shipper | NA | NA | 2017-05-22 02:00 | NA | NA | 2017-06-01 02:00 | Files for sites effective from 23rd May to 1st Jun will be sent on single day (i.e. 19th May) Files for sites effective on 2nd Jun will be sent on 22nd May. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Asset Porfolio notification | MRI | Outbound | Shipper | NA | NA | 2017-05-22 04:30 | NA | NA | 2017-06-01 05:30 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | GCC | Outbound | DMSP | NA | NA | 2017-05-22 01:30 | NA | NA | 2017-06-01 12:00 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| NDM Opening Read Estimates | MBR | Outbound | Shipper | NA | NA | 2017-05-22 21:30 | NA | NA | 2017-06-01 18:00 | MBR would be sent last via email on 4th June 2017 from legacy in old file format. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | EFF/NFF | NFF | NFF | NFF
Supply Point Registration (Unique Sites) | Nominations | NOM | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA | Legacy system there are no file exchanges instead the details are sent in email/fax. TRF files in the new world will start only from 01st Jun '17, notifying sites effective on 3rd , 4th and 5th Jun '17. It would be flexible and will be inline with GTs. Inflight confirmation might be impacted. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | NMR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 12:15 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | NRF | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 16:00 |  | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Confirmations | CNF | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 11:00 | NA |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CFR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 12:00 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Objections | WAO | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | WOR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 12:15 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | DCF | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 02:10 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Voluntary Withdrawals | WAO | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 11:15 | NA |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | WOR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 12:15 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MPE | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 02:10 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Transfer of Ownership | TRF | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 02:00 |  | NA | MAN | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Asset Porfolio notification | MRI | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 05:30 |  | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | GCC | Outbound | DMSP | NA | NA | NA | NA | NA | 2017-06-01 12:00 |  | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
Metering (Unique Sites) | Daily Metering | SCK | Inbound | iGMS | 2017-06-05 10:30 | 2017-06-05 10:31 | NA | NA | NA | NA | File is decommissioned in new world | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA
|  | DRD | Inbound | DMSP | 2017-06-01 08:40 | 2017-06-01 08:41 | NA | NA | NA | NA |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA
Review of Gas Metering Arrangement (UK Link) | Connection and Disconnection Datasets | JOB | Inbound | Shipper | 2017-05-22 18:59 | 2017-05-22 19:00 | NA | 2017-06-01 00:01 | 2017-06-01 07:00 | NA | In new world, JOB files will be processed on successful processing of UPD files. Also, the processing of JOB files will be at different schedule compared to legacy system. Timings are mentioned in the to-be batch schedule. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | JRS | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 08:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | UPD | Inbound | Shipper | 2017-05-22 18:59 | 2017-05-22 19:00 | NA | 2017-06-01 00:01 | 2017-06-01 06:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | UPR | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 07:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | PAC | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 08:00 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | DRS | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 08:00 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | UPN | Outbound | Shipper | NA | NA | 2017-05-22 23:00 | NA | NA | NA | File is decommissioned in new world | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | NA | NA | NA | NA | NA | NA
|  | UNR | Outbound | Shipper | NA | NA | 2017-05-22 08:00 | NA | NA | 2017-06-01 08:00 | These notification files are generated from Tuesday to Saturday in the current world (or only if RGMA suite has run the previous day) In new world, these files will be generated on all days after successful completion of RGMA suite. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | ENW | ENW | ENW | ENW | ENW | ENW | ENW
| Connection and Disconnection Notification | CDN | Inbound | Shipper & Network | 2017-05-22 17:59 | 2017-05-22 18:00 | NA | 2017-06-01 00:01 | 2017-06-01 20:45 | NA | In the new world, CDN files will be processed on successful processing of JOB files. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CDR | Outbound | Shipper & Network | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 21:15 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Meter Asset Manager Updates | MAM | Inbound | Shipper | 2017-05-22 19:59 | 2017-05-22 20:00 | NA | 2017-06-01 00:01 | 2017-06-01 19:00 | NA | In the new world, MAM files will be processed on successful processing of GEA files. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MAS | Outbound | Shipper | NA | NA | 2017-05-22 21:00 | NA | NA | 2017-06-01 20:00 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
Metering (UKLink) | Daily Metering (DM) | SC2 | Inbound | iGMS | 2017-06-05 11:29 | 2017-06-05 11:30 | NA | NA | NA | NA | Received from iGMS. This file will be decommissioned from 6th Jun 2017 | NA | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA
|  | DLC (Early) | Inbound | DMSP | 2017-06-01 08:29 | 2017-06-01 08:30 | NA | 2017-06-02 00:01 | 2017-06-02 08:30 | NA | These files will be accepted throughout NED period before switching to new file formats on 2nd Jun 2017.DLC will be received three times from 02nd Jun onwards and accordingly the MDR, DDR, DEL and RPA files would be sent out thrice a day. It has been agreed via survey monkey that the MDR file would be sent out to shippers through email. Should the DDR be sent through email from D day ? It needs to be agreed if the DDR, RPA, RPB and RPC files need to be sent through email during the NED window. | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | DLC (Late) | Inbound | DMSP | 2017-06-01 16:44 | 2017-06-01 16:45 | NA | 2017-06-02 08:31 | 2017-06-02 15:00 | NA |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MDR | Outbound | Shipper | NA | NA | 2017-06-01 18:00 | NA | NA | 2017-06-02 10:30 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | DDR | Outbound | DMSP | NA | NA | 2017-06-01 18:00 | NA | NA | 2017-06-02 11:00 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | RPA | Outbound | DMSP | NA | NA | 2017-06-01 18:00 | NA | NA | 2017-06-02 11:00 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | RPB | Outbound | DMSP | NA | NA | 2017-06-01 10:30 | NA | NA | NA | These file are decommissioned in new world | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA
|  | RPC | Outbound | DMSP | NA | NA | 2017-06-01 18:00 | NA | NA | NA |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA
|  | RAT | Outbound | Shipper | NA | NA | 2017-06-01 17:00 | NA | NA | 2017-06-02 19:00 | Ratchets process runs only during period 1st Oct to 6th Jun every gas year. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | EFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | PRN | Outbound | Shipper | NA | NA | 2017-06-01 17:00 | NA | NA | 2017-06-02 19:00 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | EFF | NFF | NFF | NFF | NFF | NFF | NFF
| Non Daily Metering (NDM) | UMR | Inbound | Shipper | 2017-05-22 17:59 | 2017-05-22 18:00 | NA | 2017-06-01 00:01 | 2017-06-01 18:00 | NA | In legacy system, there is a daily limit of 400,000 transactions for the files received on that day or rolled over from previous day. Any files over this limit on 22nd May 2017 will be rejected with NED-FR on 23rd May 2017 at 07:00. So it is adviced to use the previous batch day runs to avoid rejections. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. URS will be processed by AMT after URN is sent | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | URS | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-02 00:30 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | NFF | NFF | NFF | NFF | NFF | NFF
|  | URN | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 23:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | RD1 | Inbound | Proteus | 2017-03-31 19:59 | 2017-03-31 20:00 | NA | 2017-06-01 00:01 | 2017-06-01 20:00 | NA | RD1 files for prime and sub should not be sent post 31st March 2017. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | MBR | Outbound | Shipper | NA | NA | 2017-05-22 21:30 | NA | NA | 2017-06-01 18:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Meter Inspection Details | MID | Inbound | Shipper | 2017-05-22 17:59 | 2017-05-22 18:00 | NA | 2017-06-01 00:01 | 2017-06-01 18:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. Current world, this is processed only on Saturdays. Adhoc last run is performed on Monday instead. New world this file will be processed on all days as MIN notification will be generated on all days. | NA | EFF* | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MIO | Outbound | Shipper | NA | NA | 2017-05-22 19:00 | NA | NA | 2017-06-01 19:00 |  | NA | EFF* | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MIN | Outbound | Shipper | NA | NA | 2017-05-22 10:00 | NA | NA | 2017-06-01 23:59 | Current world, this is generated only on Sundays. Adhoc last run is performed on Monday instead. New world this file will be generated on all days as check read and fault notification information is added onto the file. | NA | EFF* | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
AQ Review Project 2016 | AQ/WC Speculative Calculations | ASI | Inbound | Shipper | 2016-08-14 18:59 | 2016-08-14 19:00 | NA | NA | NA | NA | These files are decommissioned in new world | bar: NA NA to NFF NFF
|  | ASO | Outbound | Shipper | NA | NA | 2016-08-14 20:00 | NA | NA | NA | bar: NA NA to NFF NFF
|  | WSI | Inbound | Shipper | 2016-08-14 18:59 | 2016-08-14 19:00 | NA | NA | NA | NA | bar: NA NA to NFF NFF
|  | WSO | Outbound | Shipper | NA | NA | 2016-08-14 20:00 | NA | NA | NA | bar: NA NA to NFF NFF
| AQ Amendments | AAI | Inbound | Shipper | 2016-08-14 18:59 | 2016-08-14 19:00 | NA | NA | NA | NA | AQ Amendment window closes as usual on 14th Aug 2016. These files are decommissioned in new world | bar: NA NA to NFF NFF
|  | AAO | Outbound | Shipper | NA | NA | 2016-08-19 20:00 | NA | NA | NA | bar: NA NA to NFF NFF
|  | WOI | Inbound | Shipper | 2016-08-14 18:59 | 2016-08-14 19:00 | NA | NA | NA | NA | bar: NA NA to NFF NFF
|  | WOO | Outbound | Shipper | NA | NA | 2016-08-19 20:00 | NA | NA | NA | bar: NA NA to NFF NFF
|  | AAE | Outbound | Shipper | NA | NA | 2016-08-19 20:00 | NA | NA | NA | bar: NA NA to NFF NFF
| AQ Notification | NRS | Outbound | Shipper | NA | NA | 2016-09-24 10:00 | NA | NA | NA | These daily AQ files are decommissioned in new world | NA | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA | NA
|  | NRQ | Outbound | Shipper | NA | NA | 2016-09-24 10:00 | NA | NA | NA |  | NA | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA | NA
|  | NRM | Outbound | Shipper | NA | NA | 2016-09-24 10:00 | NA | NA | NA |  | NA | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA | NA
|  | EUC | Outbound | Shipper | NA | NA | 2016-08-27 | NA | NA | Yearly (1st week of September) + Adhoc | bar: NA NA to NFF NFF
|  | NRL | Outbound | Shipper | NA | NA | 2016-09-12 | NA | NA | 2016-10-25 06:00 | These annual files will be delivered to Shippers by 12th Sep 2016 (as per UNC). The firm date will be confirmed as part of AQR 2016. This file is mentioned here for completeness. These files will be issued monthly post go live in new file formats | bar: NA NA to NFF NFF
| Offer Addendum | NRO | Outbound | Shipper | NA | NA | 2016-09-23 12:00 | NA | NA | NA | This file is decommissioned in new world | NA | EFF | EFF | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| AQ Appeals | API | Inbound | Shipper | 2017-03-31 22:59 | 2017-03-31 23:00 | NA | NA | NA | NA | These files are decommissioned in new world. The last day to send them in is 31st Mar 2017. Current world, these files are last processed at 2300 hrs, but the response is last generated at 1900 hrs. Hence the response for any files processed between 1900 and 2300 hrs will be sent on next day at 1900 hrs. On 1st Apr 2017, an adhoc run will be performed to provide response to files processed after 1900hrs on last day of appeals (31st Jul 2016) | bar: NA NA to NFF NFF
|  | APO | Outbound | Shipper | NA | NA | 2017-04-01 19:00 | NA | NA | NA | bar: NA NA to NFF NFF
Demand Estimation (UK Link) | Composite Weather Variable (CWV) | AWV | Inbound | WSP | 2017-06-01 07:00 | 2017-06-01 07:01 | NA | 2017-06-01 07:00 | 2017-06-01 07:01 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. All these file formats have not changed from current to new world and will be accepted/processed throughout NED period. Xoserve will manage switching the routing from legacy to new world. The date times mentioned here are that of the last times when these files (for gas day 31st May 2017) will be generated from legacy systems. Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | AIA | Outbound | MIPI & iGMS | NA | NA | 2017-06-01 11:00 | NA | NA | 2017-06-01 11:00 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | FWV | Inbound | WSP | 2017-06-01 04:29 | 2017-06-01 04:30 | NA | 2017-06-01 08:00 | 2017-06-01 08:01 | NA |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | CWF | Outbound | MIPI & iGMS | NA | NA | 2017-06-01 06:15 | NA | NA | 2017-06-01 08:00 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | AFR | Outbound | WSP | NA | NA | 2017-06-01 10:30 | NA | NA | 2017-06-01 07:41 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
|  | ARR | Outbound | WSP | NA | NA | 2017-06-01 10:30 | NA | NA | 2017-06-01 07:41 |  | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF/ENW | ENW | ENW | ENW | ENW | ENW | ENW
Address Administration | Address Notification | NAC | Outbound | Shipper | NA | NA | 2017-05-22 22:00 | NA | NA | 2017-06-02 08:00 | Adhoc instance would be run to capture the updates prior to NED. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | NFF | NFF | NFF | NFF | NFF | NFF
| Exit Zone Change Notification | EXZ | Outbound | Shipper | NA | NA | 2017-05-22 22:00 | NA | NA | 2017-06-02 06:00 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | ENW | ENW | ENW | ENW | ENW | ENW
Distribution Network Interruptions (DNI) | Eligible Interruption Supply Point List | EPS | Outbound | Shipper | NA | NA | NA | NA | NA | NA | DNI process will not be triggered during the cutover period and the annual DNI auction during the month of Feb, Mar and April. | bar: NA NA to NFF ENW
| Publish Interruption Requirements | PIR | Outbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
| Shipper Bids | SBF | Inbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
|  | RFS | Outbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
| Bid Information | BIS | Outbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
| Summary Reports by Location Id / LDZ | SRL | Outbound | Shipper & GT | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
|  | SRZ | Outbound | Shipper & GT | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
| DN Contract Notification Reports - Impacted / Cancelled | RIC | Outbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
|  | RCC | Outbound | Shipper | NA | NA | NA | NA | NA | NA | bar: NA NA to NFF ENW
Meter Point / Supply Point Amendments | DM Capacity and Meter Reading Frequency changes | SPC | Inbound | Shipper | 2017-05-22 23:09 | 2017-05-22 23:10 | NA | 2017-06-01 00:01 | 2017-06-01 19:00 | NA | Last processing batch schedule for SPC file will be at 23:10. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | SCR | Outbound | Shipper | NA | NA | 2017-05-23 00:10 | NA | NA | 2017-06-01 20:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CRF | Outbound | Shipper | NA | NA | 2017-05-22 19:15 | NA | NA | 2017-06-01 19:00 | All the outstanding capacity referrals which have not been cleared by DNs by 22nd May 2017 will be pulled back and accepted with prevailing capacity. An adhoc instance will be triggered to pick these up. | NA | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Contact / Consumer changes | CNC | Inbound | Shipper | 2017-05-22 16:29 | 2017-05-22 16:30 | NA | 2017-06-01 00:01 | 2017-06-01 19:30 | NA | Last processing batch schedule for CNC file will be at 16:30. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CNR | Outbound | Shipper | NA | NA | 2017-05-22 17:30 | NA | NA | 2017-06-01 20:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Emergency / Interruptible Contacts changes | EMC | Inbound | Shipper | 2017-05-22 18:29 | 2017-05-22 18:30 | NA | 2017-06-01 00:01 | 2017-06-01 18:30 | NA | Last processing batch schedule for EMC file will be at 18:30. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | CTR | Outbound | Shipper | NA | NA | 2017-05-22 19:30 | NA | NA | 2017-06-01 19:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Shipper Reference Changes | RFA | Inbound | Shipper | 2017-05-22 18:59 | 2017-05-22 19:00 | NA | 2017-06-01 00:01 | 2017-06-01 17:00 | NA | Last processing batch schedule for RFA file will be at 19:00. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | RFR | Outbound | Shipper | NA | NA | 2017-05-22 20:00 | NA | NA | 2017-06-01 17:30 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Market Sector Code Changes | MSI | Inbound | Shipper | 2017-05-22 09:29 | 2017-05-22 09:30 | NA | 2017-06-01 00:01 | 2017-06-01 18:00 | NA | Last processing batch schedule for MSI file will be at 09:30. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MSO | Outbound | Shipper | NA | NA | 2017-05-22 10:30 | NA | NA | 2017-06-01 18:30 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Meter Access Instruction Changes | MAI | Inbound | Shipper | 2017-05-22 17:59 | 2017-05-22 18:00 | NA | 2017-06-01 00:01 | 2017-06-01 17:30 | NA | Last processing batch schedule for MAI file will be at 18:00. The previous day batch cycles should be used to avoid any delays/rejection issues. Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | MIR | Outbound | Shipper | NA | NA | 2017-05-22 19:00 | NA | NA | 2017-06-01 18:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Meter Point Duplicate Notification | MPD | Outbound | Shipper | NA | NA | 2017-05-22 02:00 | NA | NA | 2017-06-01 02:10 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| SMSO, ISS and Supplier Changes | GEA | Inbound | Shipper | 2017-05-22 19:29 | 2017-05-22 19:30 | NA | 2017-06-01 00:01 | 2017-06-01 12:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
|  | GEO | Outbound | Shipper | NA | NA | 2017-05-22 20:30 | NA | NA | 2017-06-01 13:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Change of shipper notification on IGT Supply Meter Points to one or more shippers | AES | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 20:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Change of shipper notification on IGT Supply Meter Points to de-elected shipper | DES | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 20:00 |  | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| IGT unregistered site notification to shippers | SWN | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 07:00 |  | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Site Visit and asset fault notification | SFN | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 16:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | EFF | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Site visit and asset fault response | SFR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 22:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Class 2 Reads File | UDR | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 12:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. These files are not expected to be received on the first few weeks of Jun 2017, as there will not be any Class2,3 sites. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Class 3 Reads File | UBR | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 12:00 | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Profile Allocation Invoice | LPA | Outbound | Shipper | NA | NA | 2017-05-22 23:00 | NA | NA | 2017-06-06 13:00 | LPA file would be sent from legacy via email from the start of NEDs till closeout of GFD 31st May 2017. | NA | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | EFF | NFF
| Notification to Shipper following a change to the CSEP owner | STN | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 09:30 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Notify shipper of MP status change | NMS | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 23:30 |  | NA | EFF | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| AQ Correction | AQI | Inbound | Shipper | NA | NA | NA | 2017-06-01 00:01 | 2017-06-01 07:00 | NA | Based on the implementation time, the post go-live first received time and post go-live first processed time might differ from the time mentioned in the plan. | NA | NA | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| AQ Correction Response | AQR | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 10:00 | Based on the catch up process and nexus MOD, post go-live, the response time might differ from the time mentioned in the plan. | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Connection / Disconnection Job File | CDJ | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-01 08:00 |  | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NFF | NFF | NFF | NFF | NFF | NFF | NFF
| Domestic Portfolio | DPS | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-05 12:00 | Portfolio reports would be generated from 5th June 2017. | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | NA | NA | NA | NFF | NFF | NFF
| Daily Energy Notification | DNE | Outbound | Shipper | NA | NA | NA | NA | NA | 2017-06-02 16:00 | The daily processes in ISU commences from 2nd June 2017 | NA | NA | NED | NED | NED | NED | NED | NED | NED | NED | NED | NA | NFF | NFF | NFF | NFF | NFF | NFF
| Rec Energy Allocation | DNR | Inbound | Shipper | NA | NA | NA | 2017-06-02 00:01 | NA | NA | Email file - Run adhoc | NA | NA | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NED-FR | NA | NFF | NFF | NFF | NFF | NFF | NFF
VNBD | Variable Non Business days
Legend
EFF | Existing file formats in legacy world
NFF | New file formats in new world
ENW | Existing file formats in new world
NA | File will not be generated/accepted - Not applicable
NED | Existing file stopped and not processed
NED - FR | Existing file stopped processing during NEDs and file rejection is sent out
MAN | Existing manual email/fax in legacy world