## 1st June 2017 (12 +2)
Proposed Solution - [12] NEDs / 2 VnBDs WITH Extended Minimum Switching
Confirmation Processes around Project Nexus Implementation Date | [45 empty] | Count of RQ Days
Non Effective Days (amber shading). The [19th May] is the last day SPA and SPR files can be sent to the iGT. [12] Non-Effective days are required, with [2] additional [Variant non-Business Days] Note the diagram only shows the confirmation file to show when D is. Other SPA files e.g. objection files are subject to the same outage
Note: change of shipper timescales show the minimum timescale, longer timescales are available
Arrow shows the D+10 opening meter reading submission timescale. A supply point registration can go live in the iGT systems and the read can be provided to either the iGT (by [19th May]) or Xoserve (from [1st June] onwards)
| S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
| 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  |  | RQ | RQ | RQ | CO | CO | D
Opening read provision from D (read taken between D-5 and D+5, to be submitted by D+10) | M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D
|  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
| M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7 | Extension only required for red cells
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| M: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 7 |  | Total CDs
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 6
| W: CFR; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; W: D | 5
| T: CFR; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 4
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; F: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| M: CFR; T: RQ; W: RQ; T: CO; F: CO; M: D | 2
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | Total CDs
| T: CFR; W: RQ; T: CO; F: CO; W: D | 1 |  | 16
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | 17
| T: CFR; W: RQ; T: CO; F: CO; F: D | 1 |  | 18
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 19
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 20
| T: CFR; W: RQ; T: CO; F: CO; M: D | 1 |  | 21
| W: CFR; T: RQ; F: CO; M: CO; T: D | 1 |  | 21
| T: CFR; F: RQ; M: CO; T: CO; W: D | 1 |  | 21
| F: CFR; M: RQ; T: CO; W: CO; T: D | 1 |  | 21
| F: CFR; M: RQ; T: RQ; W: CO; T: CO; F: D | 2 |  | 22
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3 |  | 23
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3 |  | 24
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 3 |  | 25
| F: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: CO; M: CO; T: D | 4 |  | 26
| F: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: CO; T: CO; W: D | 5 |  | 27
| T: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 6 |  | 15
| F: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7 |  | 15
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8 |  | 15
[13 empty] | Minimum Confirmation timescale extension no longer required | [6 empty] | Non Effective Days - No Code Communications and System Not Effective
[13 empty] | Minimum Confirmation timescale extension required to provide 1 objection day | [6 empty] | NED - Code Comms allowed, BDs not to increment
NEDs that would have been non SPSBDs
[20 empty] | RQ | Additional RQ days created by extending switching timeline
Non Effective Days - No Code Communications and System Not Effective (ADDITIONAL DAYS)
Further Option NEDs as per TPG discussion

## 1st June 2017 (12+3)
Proposed Solution - [12] NEDs / [3] VnBDs WITH Extended Minimum Switching
Confirmation Processes around Project Nexus Implementation Date | [45 empty] | Count of RQ Days
Non Effective Days (amber shading). The [19th May] is the last day SPA and SPR files can be sent to the iGT. [12] Non-Effective days are required, with [3] additional [Variant non-Business Days] Note the diagram only shows the confirmation file to show when D is. Other SPA files e.g. objection files are subject to the same outage
Note: change of shipper timescales show the minimum timescale, longer timescales are available
Arrow shows the D+10 opening meter reading submission timescale. A supply point registration can go live in the iGT systems and the read can be provided to either the iGT (by [19th May]) or Xoserve (from [1st June] onwards)
| S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
| 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  |  | RQ | RQ | RQ | CO | CO | D
Opening read provision from D (read taken between D-5 and D+5, to be submitted by D+10) | M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D
|  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
| M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7 | Extension only required for red cells
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| M: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 7 |  | Total CDs
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 6
| W: CFR; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; W: D | 5
| T: CFR; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 4
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; F: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| M: CFR; T: RQ; W: RQ; T: CO; F: CO; M: D | 2
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | Total CDs
| T: CFR; W: RQ; T: CO; F: CO; W: D | 1 |  | 16
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | 17
| T: CFR; W: RQ; T: CO; F: CO; F: D | 1 |  | 18
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 19
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 20
| T: CFR; W: RQ; T: CO; F: CO; M: D | 1 |  | 21
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | 22
| W: CFR; T: RQ; F: CO; T: CO; W: D | 1 |  | 22
| T: CFR; F: RQ; T: CO; W: CO; T: D | 1 |  | 22
| F: CFR; T: RQ; W: CO; T: CO; F: D | 1 |  | 22
| F: CFR; T: RQ; W: RQ; T: CO; F: CO; S: D | 2 |  | 23
| F: CFR; T: RQ; W: RQ; T: CO; F: CO; S: D | 2 |  | 24
| F: CFR; T: RQ; W: RQ; T: CO; F: CO; M: D | 2 |  | 25
| F: CFR; T: RQ; W: RQ; T: RQ; F: CO; M: CO; T: D | 3 |  | 26
| F: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: CO; T: CO; W: D | 4 |  | 27
| T: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 5 |  | 15
| F: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 6 |  | 15
| S: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 7 |  | 15
[13 empty] | Minimum Confirmation timescale extension no longer required | [6 empty] | Non Effective Days - No Code Communications and System Not Effective
[13 empty] | Minimum Confirmation timescale extension required to provide 1 objection day | [6 empty] | NED - Code Comms allowed, BDs not to increment
NEDs that would have been non SPSBDs
[20 empty] | RQ | Additional RQ days created by extending switching timeline
Non Effective Days - No Code Communications and System Not Effective (ADDITIONAL DAYS)
Further Option NEDs as per TPG discussion

## 1st June 2017 (12+4)
Proposed Solution - [12] NEDs / [4] VnBDs WITH Extended Minimum Switching
Confirmation Processes around Project Nexus Implementation Date | [47 empty] | Count of RQ Days
Non Effective Days (amber shading). The [19th May] is the last day SPA and SPR files can be sent to the iGT. [12] Non-Effective days are required, with [4] additional [Variant non-Business Days] Note the diagram only shows the confirmation file to show when D is. Other SPA files e.g. objection files are subject to the same outage
Note: change of shipper timescales show the minimum timescale, longer timescales are available
Arrow shows the D+10 opening meter reading submission timescale. A supply point registration can go live in the iGT systems and the read can be provided to either the iGT (by [19th May]) or Xoserve (from [1st June] onwards)
| S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
| 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  |  | RQ | RQ | RQ | CO | CO | D
Opening read provision from D (read taken between D-5 and D+5, to be submitted by D+10) | M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D
|  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
| M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7 | Extension only required for red cells
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| M: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 7 |  | Total CDs
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 6
| W: CFR; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; W: D | 5
| T: CFR; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; T: D | 4
| F: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; F: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| S: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| M: CFR; T: RQ; W: RQ; T: CO; F: CO; M: D | 2
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | Total CDs
| T: CFR; W: RQ; T: CO; F: CO; W: D | 1 |  | 16
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | 17
| T: CFR; W: RQ; T: CO; F: CO; F: D | 1 |  | 18
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 19
| T: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 20
| T: CFR; W: RQ; T: CO; F: CO; M: D | 1 |  | 21
| T: CFR; W: RQ; T: CO; F: CO; T: D | 1 |  | 22
| T: CFR; W: RQ; T: CO; F: CO; W: D | 1 |  | 23
| W: CFR; T: RQ; F: CO; W: CO; T: D | 1 |  | 23
| T: CFR; F: RQ; W: CO; T: CO; F: D | 1 |  | 23
| F: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 23
| F: CFR; W: RQ; T: CO; F: CO; S: D | 1 |  | 24
| F: CFR; W: RQ; T: CO; F: CO; M: D | 1 |  | 25
| F: CFR; W: RQ; T: RQ; F: CO; M: CO; T: D | 2 |  | 26
| F: CFR; W: RQ; T: RQ; F: RQ; M: CO; T: CO; W: D | 3 |  | 27
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 4 |  | 15
| F: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 5 |  | 15
| S: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 6 |  | 15
[13 empty] | Minimum Confirmation timescale extension no longer required | [6 empty] | Non Effective Days - No Code Communications and System Not Effective
[13 empty] | Minimum Confirmation timescale extension required to provide 1 objection day | [6 empty] | NED - Code Comms allowed, BDs not to increment
NEDs that would have been non SPSBDs
[20 empty] | RQ | Additional RQ days created by extending switching timeline
Non Effective Days - No Code Communications and System Not Effective (ADDITIONAL DAYS)
Further Option NEDs as per TPG discussion